## Sheet1
Ref | Status | Location | Name | Created | Type | Status Changed | Open Actions | Total Actions | Association | OverDue | Images | Comments | Documents | Project | Report Forms Status | Report Forms Group
F145185.4 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 15/09/2020 | 6 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F1.495500 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 15/09/2020 | 12 | 15/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495499 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 15/09/2020 | 12 | 15/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495498 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 15/09/2020 | 12 | 15/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495496 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 15/09/2020 | 12 | 15/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495479 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 15/09/2020 | 12 | 15/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F124541.22 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F124541.21 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495343 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.495319 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495317 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495311 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495286 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F116412.544 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.495253 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495210 | Opened | 1328 - Townsend St | Permit to Excavate | 14/09/2020 | 5 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F141663.2 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/09/2020 | 9 | 14/09/2020 | 10 | 14 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 2
F116412.532 | Open / Ongoing Works | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.531 | Open / Ongoing Works | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.533 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.534 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.535 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.536 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.537 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.538 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.539 | Open / Ongoing Works | 5th to 6th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.540 | Open / Ongoing Works | 5th to 6th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.543 | Open / Ongoing Works | 6th to 7th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.542 | Open / Ongoing Works | 6th to 7th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.541 | Open / Ongoing Works | 6th to 7th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.495174 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495149 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495145 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F131475.124 | Open / Ongoing Works | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 14/09/2020 | 8 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.123 | Open / Ongoing Works | RM.2.221>Rooms>2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 14/09/2020 | 8 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.122 | Open / Ongoing Works | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 14/09/2020 | 8 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.384 | Open / Ongoing Works | RM.2.213>Rooms>2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 14/09/2020 | 8 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.382 | Open / Ongoing Works | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 14/09/2020 | 8 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.495070 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.495069 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F116412.530 | Closed JPC Reviewed | QC Training Records>Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F118982.32 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F131475.121 | Open / Ongoing Works | RM.03.332>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 14/09/2020 | 8 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.119 | Open / Ongoing Works | RM.03.330>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 14/09/2020 | 8 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.380 | Open / Ongoing Works | RM.05.634 - Corridor>Common Areas>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 14/09/2020 | 8 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.494417 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F113721.280 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/09/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.494370 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.494367 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.494364 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.494358 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.494278 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/09/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.494207 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/09/2020 | 12 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F124541.20 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/09/2020 | 12 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.494156 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/09/2020 | 12 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F118318.381 | Open / Ongoing Works | 4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ME-401 Services Test | 14/09/2020 | 1 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.529 | Open / Ongoing Works | 2nd to 3rd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.528 | Open / Ongoing Works | 3rd to 4th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.527 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F145185.1 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F145185.2 | Open / Ongoing Works | 3rd to 4th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F145185.3 | Open / Ongoing Works | 3rd to 4th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.118 | Open / Ongoing Works | EHS Management>JPC Project Management | CM-EHS-FRM-009 Temporary Electrics Inspection | 11/9/2020 | 9 | 11/9/2020 | 11 | 11 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 2
F113721.278 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 3
F1.492634 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/9/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.19 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F124541.18 | Open / Ongoing Works | Items to be Deleted | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F124541.17 | Open / Ongoing Works | Items to be Deleted | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F124541.16 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F124541.15 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.492530 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.492500 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.492490 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.492485 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.492481 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.492480 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.492475 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.492470 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.492469 | Open / Ongoing Works | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F1.492465 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.492459 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.492446 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.492443 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.492440 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F116412.520 | Open / Ongoing Works | JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/9/2020 | 9 | 10/9/2020 | 10 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F102497.30 | Open / Ongoing Works | JPC Project Management | JPC-PM-FRM-001 - Minutes of Meeting | 10/9/2020 | 4 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 1
F131475.117 | Open / Ongoing Works | RM.03.302>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.116 | Open / Ongoing Works | RM.04.458>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.115 | Open / Ongoing Works | RM.04.468>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.114 | Open / Ongoing Works | RM.04.543 - Corridor>Common Areas>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.113 | Open / Ongoing Works | R.01.240 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.112 | Open / Ongoing Works | R.01.238 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.492238 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.492196 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.492148 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 12/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.491905 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F113721.277 | Open / Ongoing Works | RM.05.564>Area 3>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.276 | Open / Ongoing Works | RM.05.566>Area 3>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.275 | Open / Ongoing Works | Area 3>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.274 | Open / Ongoing Works | RM.05.570>Area 3>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.273 | Open / Ongoing Works | RM.05.572>Area 3>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.272 | Open / Ongoing Works | 5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.271 | Open / Ongoing Works | 5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118982.30 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F128229.12 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F113721.270 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F131475.111 | Open / Ongoing Works | RM.04.450>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.493934 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/9/2020 | 12 | 12/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.493876 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/9/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.493632 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/9/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.493621 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/9/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.493607 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.493598 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/9/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F116412.526 | Open / Ongoing Works | Roof GA>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-211 Paralon Roof Inspection | 11/9/2020 | 8 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.525 | Closed | Roof GA>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 11/9/2020 | 10 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.493498 | Open / Ongoing Works | 6th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 11/9/2020 | 10 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F1.493497 | Open / Ongoing Works | Quality Review - Forms & Checklists>Training Area | CM-EHS-FRM-110 EHS Weekly Inspection | 11/9/2020 | 9 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F1.493484 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/9/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.493391 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/9/2020 | 12 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F102497.31 | Open / Ongoing Works | JPC Project Management | JPC-PM-FRM-001 - Minutes of Meeting | 11/9/2020 | 4 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 1
F107663.72 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/9/2020 | 9 | 11/9/2020 | 1 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F107663.71 | JPC Sign Off / Closed | 5th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 11/9/2020 | 11 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118982.31 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F116412.524 | Closed | Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 11/9/2020 | 8 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.523 | Open / Ongoing Works | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/9/2020 | 10 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.522 | Open / Ongoing Works | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/9/2020 | 10 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.491372 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.491361 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/9/2020 | 12 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.14 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.491026 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.491003 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 12/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.490950 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.490943 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.490932 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.490926 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.490894 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.490889 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.490878 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.490874 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.490870 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.490860 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F131475.110 | Open / Ongoing Works | RM.04.448>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.108 | Open / Ongoing Works | RM.04.446>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.107 | Open / Ongoing Works | RM.04.444>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.519 | Open / Ongoing Works | RM.03.433 - Corridor>Common Areas>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ME-401 Services Test | 10/9/2020 | 1 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.106 | Rejected / Action Required | RM.04.440>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.105 | Open / Ongoing Works | RM.04.442>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.104 | Open / Ongoing Works | RM.04.438>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.103 | Open / Ongoing Works | RM.04.436>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.102 | Open / Ongoing Works | RM.04.432>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 10/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F131475.101 | Open / Ongoing Works | RM.04.403>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 9/9/2020 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.100 | Open / Ongoing Works | RM.04.401>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 9/9/2020 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.99 | Open / Ongoing Works | RM.04.427>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 9/9/2020 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.490680 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F118982.29 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F141007.7 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 9/9/2020 | 9 | 9/9/2020 | 8 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F141007.6 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 9/9/2020 | 9 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F1.490655 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.490643 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F141007.3 | Open / Ongoing Works | 04 Staturatury Forms>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 9/9/2020 | 9 | 9/9/2020 | 6 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F1.490403 | Closed | 1328 - Townsend St | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 9/9/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F122196.103 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F116412.515 | Open / Ongoing Works | Roof GA>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-211 Paralon Roof Inspection | 9/9/2020 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.490277 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F131475.98 | Open / Ongoing Works | RM.03.326>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 9/9/2020 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.490028 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 9/9/2020 | 12 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489772 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.489756 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 12/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489753 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489736 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489735 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489733 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489729 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489726 | Open / Ongoing Works | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/9/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F1.489695 | JPC Sign Off | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 8/9/2020 | 13 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.489657 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489654 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489653 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489650 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489623 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489621 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.489619 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F131475.97 | Open / Ongoing Works | RM.04.405>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.96 | Open / Ongoing Works | RM.04.407>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F124541.13 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F131475.95 | Open / Ongoing Works | RM.04.409>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.94 | Open / Ongoing Works | RM.04.411>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.93 | Open / Ongoing Works | RM.04.413>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.92 | Open / Ongoing Works | RM.04.415>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F129620.8 | Open / Ongoing Works | Audits & Assessments>Quality Management>JPC Project Management | QM-FRM-QC-012 Quality Leadership Walk | 8/9/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.91 | Open / Ongoing Works | RM.04.417>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.90 | Open / Ongoing Works | RM.04.419>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.89 | Open / Ongoing Works | RM.04.421>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.88 | Open / Ongoing Works | RM.04.410>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F131475.87 | Works Complete / Resolved | RM.04.408>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.86 | Works Complete / Resolved | RM.04.404>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.85 | Works Complete / Resolved | RM.04.402>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F131475.84 | Open / Ongoing Works | RM.04.406>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.83 | Open / Ongoing Works | RM.04.406>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.489513 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F118318.379 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 8/9/2020 | 8 | 9 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 2
F1.489409 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.489389 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.28 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.489110 | Open / Ongoing Works | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 8/9/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F131475.82 | Open / Ongoing Works | R.01.209 - Room>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.81 | Open / Ongoing Works | R.01.230 - Laundry>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.488907 | Open / Ongoing Works | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/9/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F113721.265 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 3
F1.488802 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 8/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.488754 | JPC Sign Off / Closed | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 8/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F124541.12 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.488626 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.488565 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488564 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488560 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488551 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488523 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.488458 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488456 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488455 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488451 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488419 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488386 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488368 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.27 | Subcontractor Signed Off | 1328 - Townsend St | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488279 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.488276 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.488262 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F131475.80 | Open / Ongoing Works | QC & BC(A)R | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/9/2020 | 9 | 7/9/2020 | 5 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F113721.264 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.489167 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/9/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F131475.79 | Open / Ongoing Works | RM.02.230>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/9/2020 | 8 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.257 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F113721.256 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F107663.69 | Closed JPC Sign Off | 5th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.70 | Closed JPC Sign Off | 5th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.269 | Open / Ongoing Works | 2nd to 3rd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/9/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.516 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.267 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/9/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.268 | Open / Ongoing Works | 2nd to 3rd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/9/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.510 | Open / Ongoing Works | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 8/9/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.514 | Open / Ongoing Works | Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/9/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.509 | Open / Ongoing Works | Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 8/9/2020 | 10 | 8/9/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.511 | Open / Ongoing Works | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 8/9/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.512 | Open / Ongoing Works | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 8/9/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.502 | Open / Ongoing Works | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/9/2020 | 10 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.513 | Open / Ongoing Works | Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 8/9/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.508 | Open / Ongoing Works | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/9/2020 | 10 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.505 | Open / Ongoing Works | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/9/2020 | 10 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.507 | Open / Ongoing Works | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/9/2020 | 10 | 7/9/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.506 | Open / Ongoing Works | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/9/2020 | 10 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.504 | Open / Ongoing Works | Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/9/2020 | 10 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.503 | Open / Ongoing Works | Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/9/2020 | 10 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.487550 | JPC Sign Off / Closed | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.487547 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/9/2020 | 12 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.487408 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 6/9/2020 | 12 | 6/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F74906.106 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 6/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F74906.105 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 6/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F74906.104 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 6/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F74906.103 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 6/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.487098 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 5/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.487097 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 5/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.487094 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 5/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.487093 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 5/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.11 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 5/9/2020 | 12 | 5/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F116412.501 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/9/2020 | 6 | 5/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.487087 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 5/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.486813 | Closed | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 4/9/2020 | 10 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.486657 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 4/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.486620 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 4/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118318.378 | Open / Ongoing Works | Site Management>JPC Project Management | CM-EHS-FRM-009 Temporary Electrics Inspection | 4/9/2020 | 9 | 4/9/2020 | 4 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 2
F118982.26 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 4/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.255 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 8/9/2020 | 7 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.486344 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 4/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118318.376 | Open / Ongoing Works | RM.04.412>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 4/9/2020 | 8 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.375 | Open / Ongoing Works | RM.04.414>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 4/9/2020 | 8 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.374 | Open / Ongoing Works | RM.04.416>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 4/9/2020 | 8 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.373 | Open / Ongoing Works | RM.04.418>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 4/9/2020 | 8 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.500 | Closed JPC Reviewed | QC Training Records>Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 4/9/2020 | 10 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.486005 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F1.485934 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 4/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485924 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 4/9/2020 | 12 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.485856 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.10 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485782 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485772 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485747 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485740 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485724 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F1.485718 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485714 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485712 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485706 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485697 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485675 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F84104.860 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 3/9/2020 | 9 | 4/9/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118982.25 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F116412.498 | Closed | 3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 3/9/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.497 | Closed | 3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 3/9/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90895.102 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 3/9/2020 | 9 | 4/9/2020 | 0 | 7 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F116412.496 | Closed | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-225 Firestopping Inspection Checklist | 3/9/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.484996 | JPC Sign Off / Closed | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 3/9/2020 | 11 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.484607 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484550 | Open / Ongoing Works | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/9/2020 | 10 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F1.484537 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.484534 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F119055.22 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.484532 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484492 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484488 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484483 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484480 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484431 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484429 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484422 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484369 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484362 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118318.372 | Open / Ongoing Works | RM.04.420>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 2/9/2020 | 8 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.484264 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.17 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 2/9/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F137980.16 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 2/9/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F128229.11 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/9/2020 | 9 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F137980.15 | Closed | Roof Plan>Block 4>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 2/9/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90895.101 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 2/9/2020 | 9 | 4/9/2020 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F118982.24 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.9 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.484028 | Open / Ongoing Works | 5th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 2/9/2020 | 13 | 2/9/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.484000 | Closed JPC Sign Off | 5th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 2/9/2020 | 11 | 9/9/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.483983 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.483955 | Open / Ongoing Works | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/9/2020 | 10 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F113721.242 | Open / Ongoing Works | RM.02.234>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.241 | Open / Ongoing Works | RM.02.236>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.240 | Open / Ongoing Works | RM.02.238>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.239 | Open / Ongoing Works | RM.02.240>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.238 | Open / Ongoing Works | RM.02.242>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.237 | Open / Ongoing Works | RM.02.244>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.236 | Open / Ongoing Works | RM.02.246>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.235 | Open / Ongoing Works | RM.02.248>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.234 | Open / Ongoing Works | RM.02.250>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.483162 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.233 | Open / Ongoing Works | RM.02.252>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.232 | Open / Ongoing Works | RM.02.262>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.231 | Open / Ongoing Works | RM.02.264>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.230 | Open / Ongoing Works | RM.02.266>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.229 | Open / Ongoing Works | RM.02.268>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.483150 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.228 | Open / Ongoing Works | RM.02.270>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.483149 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.227 | Open / Ongoing Works | RM.02.272>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.483145 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.226 | Open / Ongoing Works | RM.02.274>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.483142 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.483141 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.225 | Open / Ongoing Works | RM.02.276>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.483136 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.483131 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.483119 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.483111 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F116412.493 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 1/9/2020 | 9 | 4/9/2020 | 0 | 10 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F118982.23 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482911 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482887 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118318.370 | Open / Ongoing Works | RM.04.423>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 1/9/2020 | 8 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.369 | Open / Ongoing Works | RM.04.422>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 1/9/2020 | 8 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.368 | Works Complete / Resolved | RM.04.425>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 1/9/2020 | 8 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.367 | Open / Ongoing Works | RM.04.424>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 1/9/2020 | 8 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.366 | Open / Ongoing Works | RM.04.426>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 1/9/2020 | 8 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.482458 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 1/9/2020 | 6 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.482334 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.7 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482240 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F119055.20 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F119055.19 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.482218 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482217 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482213 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482212 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482211 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482209 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482208 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482203 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482201 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.482183 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F84104.859 | JPC Sign Off / Closed | 5th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 31/08/2020 | 11 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.482150 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F102497.26 | Open | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 31/08/2020 | 9 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F1.482092 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F140923.1 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 4/9/2020 | 0 | 20 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F113721.224 | Open / Ongoing Works | RM.01.146>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.223 | Open / Ongoing Works | RM.01.148>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.221 | Open / Ongoing Works | RM.01.158>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.220 | Open / Ongoing Works | RM.01.160>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.219 | Open / Ongoing Works | RM.01.162>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.218 | Open / Ongoing Works | RM.01.164>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.217 | Open / Ongoing Works | RM.01.166>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.482082 | Open / Ongoing Works | 1st to 2nd Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 31/08/2020 | 8 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F113721.216 | Open / Ongoing Works | RM.01.168>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.215 | Open / Ongoing Works | RM.01.170>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.213 | Open / Ongoing Works | RM.01.172>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.482049 | In Process / Manufactor | Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F1.482030 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 3
F1.481979 | Closed | 2nd to 3rd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.481974 | Closed | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.481967 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481930 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F1.481929 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 3
F1.481921 | JPC Sign Off / Closed | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 31/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.481919 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481918 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481913 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 31/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.6 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 30/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481793 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 30/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481636 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 29/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F131475.78 | Open / Ongoing Works | RM.05.519>Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/08/2020 | 8 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.77 | Open / Ongoing Works | RM.05.518>Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/08/2020 | 8 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.75 | Open / Ongoing Works | RM.05.520>Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/08/2020 | 8 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.73 | Open / Ongoing Works | RM.05.525>Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/08/2020 | 8 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.72 | Open / Ongoing Works | RM.05.527>Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/08/2020 | 8 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.71 | Open / Ongoing Works | RM.05.529>Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/08/2020 | 8 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.70 | Open / Ongoing Works | RM.05.526>Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/08/2020 | 8 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.481434 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481374 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481308 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481226 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481215 | Open / Ongoing Works | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 28/08/2020 | 10 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F1.481205 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481196 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481195 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481193 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481189 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.481188 | Open / Ongoing Works | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 28/08/2020 | 10 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F107663.68 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/08/2020 | 9 | 1/9/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.481140 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.22 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118318.365 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-009 Temporary Electrics Inspection | 28/08/2020 | 9 | 1/9/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.480919 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 28/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 3
F90895.100 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 28/08/2020 | 9 | 4/9/2020 | 0 | 11 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.480575 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480573 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 28/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.5 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480390 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480258 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480243 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480188 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480181 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480167 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480165 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480154 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.480131 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F119055.18 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 27/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.479955 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 27/08/2020 | 9 | 1/9/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F116412.494 | Open / Ongoing Works | RM.01.144>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/9/2020 | 10 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.483718 | JPC Sign Off / Closed | 5th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 2/9/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.483712 | JPC Sign Off / Closed | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 2/9/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.483634 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.483488 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 2/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.8 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.483267 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.483264 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F119055.21 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 1/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.483222 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 1/9/2020 | 12 | 1/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F113721.252 | Open / Ongoing Works | RM.02.252>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.251 | Open / Ongoing Works | RM.02.264>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.250 | Open / Ongoing Works | RM.02.268>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.249 | Open / Ongoing Works | RM.02.272>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.248 | Open / Ongoing Works | RM.02.274>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.245 | Open / Ongoing Works | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.244 | Open / Ongoing Works | RM.02.232>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.485571 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.485565 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.485450 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 3/9/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.479151 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.479148 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F119055.17 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F107663.67 | JPC Sign Off / Closed | 4th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 26/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.478906 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F129620.7 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 26/08/2020 | 9 | 1/9/2020 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.478803 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.478783 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.21 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 27/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F116412.483 | JPC Sign Off | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 27/08/2020 | 1 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.482 | Open / Ongoing Works | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 27/08/2020 | 1 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.479579 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.479228 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.479165 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.478769 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.478726 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F131475.69 | Open / Ongoing Works | R.01.238 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.68 | Open / Ongoing Works | RM.01.111>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118982.20 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.478484 | Open / Ongoing Works | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 26/08/2020 | 13 | 26/08/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.478456 | Open / Ongoing Works | Roof Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 26/08/2020 | 13 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.478450 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 26/08/2020 | 13 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F113721.208 | Open / Ongoing Works | 6th to 7th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 26/08/2020 | 10 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.254 | Open / Ongoing Works | 7th floor to Roof>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/9/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.480 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 26/08/2020 | 10 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.253 | Open / Ongoing Works | 1st to 2nd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/9/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.495 | Open / Ongoing Works | 1st to 2nd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/9/2020 | 10 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.499 | Open / Ongoing Works | 1st to 2nd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/9/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.243 | Open / Ongoing Works | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.487 | Closed | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/08/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.486 | Open / Ongoing Works | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/08/2020 | 10 | 27/08/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.484 | Open / Ongoing Works | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/08/2020 | 10 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.488 | Closed | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/08/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.490 | Open / Ongoing Works | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/08/2020 | 10 | 27/08/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.489 | Closed | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/08/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.492 | Open / Ongoing Works | Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/08/2020 | 10 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.491 | Closed | Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/08/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.481 | Open / Ongoing Works | Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 26/08/2020 | 10 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.478445 | JPC Sign Off | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 26/08/2020 | 13 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.478419 | Open / Ongoing Works | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 26/08/2020 | 13 | 26/08/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.478371 | Open / Ongoing Works | Roof GA>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 26/08/2020 | 13 | 26/08/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.478324 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.478319 | Open / Ongoing Works | 3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 26/08/2020 | 13 | 26/08/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F74906.102 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.478304 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.478297 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.478286 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.478273 | Open / Ongoing Works | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 26/08/2020 | 13 | 26/08/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F118982.19 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.477935 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.477933 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 26/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.4 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.477007 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476991 | Closed | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 25/08/2020 | 10 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.476985 | Closed | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 25/08/2020 | 10 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.476973 | Closed | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 25/08/2020 | 10 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F84104.858 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 25/08/2020 | 9 | 26/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F119055.16 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 25/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.476897 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476895 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476888 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476883 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476882 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F74906.101 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476874 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476871 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.14 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 25/08/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F137980.13 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 25/08/2020 | 10 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F128229.8 | Open / Ongoing Works | EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/08/2020 | 9 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F116412.476 | Open / Ongoing Works | Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 25/08/2020 | 10 | 25/08/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.476679 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476576 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.476494 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476493 | JPC Inspected | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/08/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F1.476483 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476471 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 25/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.476467 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F119055.15 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 24/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.476315 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476310 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476291 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.12 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.11 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.10 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.9 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 25/08/2020 | 12 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F141663.1 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 25/08/2020 | 9 | 26/08/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.476205 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 24/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.475878 | Open / Ongoing Works | QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 24/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F118982.18 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.475721 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F131475.67 | Open / Ongoing Works | RM.01.161>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 24/08/2020 | 8 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.66 | Open / Ongoing Works | RM.01.163>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 24/08/2020 | 8 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.199 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F124541.3 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.2 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.475198 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.475192 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.17 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.475182 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.475170 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.475168 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.475167 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F74906.99 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 23/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.475002 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 23/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.475001 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/08/2020 | 6 | 23/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F1.474788 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 21/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.474786 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 21/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.474782 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 21/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.474780 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 21/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.474778 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 21/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.474771 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 21/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F141007.2 | Open / Ongoing Works | QC & BC(A)R | QM-FRM-QC-012 Quality Leadership Walk | 21/08/2020 | 10 | 21/08/2020 | 9 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.198 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 21/08/2020 | 9 | 26/08/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.474221 | Closed | 5th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 21/08/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.474213 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 21/08/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.474207 | Closed | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 21/08/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F90895.99 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 21/08/2020 | 9 | 1/9/2020 | 0 | 8 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.474000 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 21/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.197 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.473727 | Open / Ongoing Works | EHS Management>JPC Project Management | CM-EHS-FRM-104 - Method Statement Sign In Sheet | 21/08/2020 | 9 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F1.473709 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 21/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118318.364 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 21/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473514 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473506 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473505 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473500 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F119055.14 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473497 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473492 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473451 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473441 | 3rd Party Sign Off - Closed | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 20/08/2020 | 13 | 1/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.473400 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473388 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473387 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476062 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476060 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.476057 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F74906.100 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 24/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473372 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473366 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F124541.1 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.473065 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.16 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.15 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F116412.473 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 20/08/2020 | 9 | 26/08/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F74906.98 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472876 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 20/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472660 | JPC Sign Off / Closed | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 20/08/2020 | 11 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.472454 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472437 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.7 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 19/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.472424 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472416 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472411 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472409 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472407 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472363 | Closed JPC Reviewed | JPC Project Management | QM-FRM-QC-002 Off Site Inspection | 19/08/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F1.472344 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.6 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 19/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.472276 | JPC Sign Off / Closed | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 19/08/2020 | 11 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F119055.10 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.472250 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472047 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472028 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F141007.1 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 19/08/2020 | 9 | 20/08/2020 | 0 | 16 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F131475.65 | Open / Ongoing Works | RM.04.543 - Corridor>Common Areas>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 19/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.471934 | Open / Ongoing Works | Site Management>JPC Project Management | CM-EHS-FRM-105 - Daily Safe Start | 19/08/2020 | 9 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F131475.64 | Open / Ongoing Works | RM.04.475>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 19/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.471930 | Open / Ongoing Works | 1328 - Townsend St | CM-EHS-FRM-105 - Daily Safe Start | 19/08/2020 | 9 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F1.471928 | Open / Ongoing Works | 1328 - Townsend St | CM-EHS-FRM-105 - Daily Safe Start | 19/08/2020 | 9 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F131475.63 | Open / Ongoing Works | RM.04.533 - Corridor>Common Areas>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 19/08/2020 | 8 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118982.14 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.471082 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.13 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 19/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470891 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470844 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470836 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F1.470830 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470824 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470809 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.5 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 18/08/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F119055.9 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.470676 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.472967 | Open / Ongoing Works | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F116412.468 | Open / Ongoing Works | Roof GA>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 19/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.470586 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470584 | Open / Ongoing Works | 02 Drainage>ITP 03 External Works>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 18/08/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F113721.185 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F113721.183 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 3
F1.470566 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470528 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470461 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470450 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470444 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118318.363 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470428 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118318.362 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.470331 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470312 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.470275 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F128229.7 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 18/08/2020 | 9 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F131475.62 | Open / Ongoing Works | R.01.225 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/08/2020 | 8 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.61 | Open / Ongoing Works | R.01.224 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 18/08/2020 | 8 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.151 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/08/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.469620 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469610 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 18/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F137980.3 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 18/08/2020 | 9 | 20/08/2020 | 0 | 16 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F1.469404 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469368 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469364 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469361 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469359 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469357 | Open / Ongoing Works | 4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 17/08/2020 | 8 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F1.469355 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469349 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469216 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469201 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469193 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469179 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118318.361 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 17/08/2020 | 9 | 20/08/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F119055.7 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.469074 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469052 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469051 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.468963 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.468950 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.133 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.468512 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.468506 | JPC Sign Off / Closed | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 17/08/2020 | 11 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.468392 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.468298 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 16/08/2020 | 6 | 16/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F1.468083 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 15/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.468082 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 15/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.468081 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 15/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467923 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467922 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467920 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467919 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467917 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467916 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467914 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467912 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467822 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F84104.856 | JPC Sign Off / Closed | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 14/08/2020 | 11 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.467603 | Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 14/08/2020 | 10 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.467594 | Closed | 02 Drainage>ITP 03 External Works>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 14/08/2020 | 10 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.467525 | Closed | 4th Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 14/08/2020 | 10 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F1.467510 | Closed | Roof GA>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 14/08/2020 | 10 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.467503 | Closed | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 14/08/2020 | 10 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.467488 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.467458 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.467411 | Closed | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 14/08/2020 | 10 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.467301 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-010 Free Issue Item Form | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 3
F107663.65 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/08/2020 | 9 | 20/08/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F90895.97 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 14/08/2020 | 9 | 20/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.467019 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.12 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.11 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.132 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.466828 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.466818 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.466708 | JPC Sign Off / Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 14/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.466667 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 14/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F119055.6 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.469187 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 17/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.136 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-004 QC Observation Report | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F1.468685 | Closed JPC Reviewed | ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC005 - Training Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.466366 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.466358 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.466352 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.466348 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.466346 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.466302 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.466219 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F90895.96 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/08/2020 | 9 | 14/08/2020 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.466047 | Open / Ongoing Works | 1328 - Townsend St | JPC-QA-RP-003 - Site Audit Report | 13/08/2020 | 2 | 13/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F118982.10 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.465990 | Open / Ongoing Works | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 13/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F128229.6 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 13/08/2020 | 9 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F1.465734 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.465724 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 5
F1.465721 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.465715 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.465709 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.465698 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 5
F116412.456 | Open / Ongoing Works | Roof GA>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-211 Paralon Roof Inspection | 13/08/2020 | 8 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.465651 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 13/08/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.115 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/08/2020 | 6 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.465088 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.465056 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.465046 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.464936 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.6 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.464914 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118982.5 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.464889 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.464862 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.464859 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F119055.5 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F84104.855 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/8/2020 | 9 | 14/08/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.464828 | JPC Sign Off / Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 12/8/2020 | 11 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.464800 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F128229.5 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F131475.60 | Open / Ongoing Works | RM.04.475>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.59 | Open / Ongoing Works | RM.04.473>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118982.1 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.95 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F116412.404 | Closed | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-MEP-404 Electrical Inspection Report | 10/8/2020 | 1 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.403 | Closed | 4th to 5th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.402 | Closed | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.401 | Closed | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.400 | Closed | 3rd to 4th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.399 | Closed | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.462584 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F116412.398 | Closed | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 10/8/2020 | 10 | 10/9/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.462528 | Closed | Roof Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462518 | Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462506 | Closed | 1328 - Townsend St | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.462500 | Closed | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462488 | Closed | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462479 | Closed | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462456 | Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462412 | Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462404 | Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462395 | Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462391 | Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462383 | Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462379 | Closed | 3rd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462377 | Closed | 02 Drainage>ITP 03 External Works>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462371 | Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462364 | Closed | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462358 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462339 | Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462332 | Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462325 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462323 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462317 | Closed | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462314 | Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462310 | Closed | Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462268 | Closed | Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.462260 | Closed | Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F119055.1 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/8/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.462202 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.462193 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F118994.7 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/8/2020 | 12 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.462059 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 10/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F131475.56 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/8/2020 | 9 | 14/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.461985 | Open / Ongoing Works | 4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 10/8/2020 | 8 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F113721.94 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/8/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F1.461401 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/8/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F137980.2 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 7/8/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F137980.1 | Open / Ongoing Works | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 7/8/2020 | 10 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.460894 | Closed | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 7/8/2020 | 10 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F90895.95 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 7/8/2020 | 9 | 14/08/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.460612 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 7/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.93 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F113721.92 | Open / Ongoing Works | General Site Plan>JPC Project Management | QM-FRM-QC-009 Quality Control Record | 7/8/2020 | 10 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.91 | Open / Ongoing Works | General Site Plan>JPC Project Management | QM-FRM-QC-009 Quality Control Record | 7/8/2020 | 10 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F128229.2 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 6/8/2020 | 9 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F113721.90 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/8/2020 | 6 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F1.458249 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 5/8/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.458228 | Open / Ongoing Works | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 5/8/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.456329 | Open / Ongoing Works | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-400 Mechancial BCAR Inspection | 4/8/2020 | 13 | 4/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F116412.416 | Open / Ongoing Works | Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.415 | Open / Ongoing Works | 4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.464299 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 13/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F113721.96 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.464196 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.464133 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.464130 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.463926 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.463902 | Open / Ongoing Works | 1328 - Townsend St | CM-EHS-FRM-103 - Toolbox Training Record & Sign In Sheet | 11/8/2020 | 9 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F1.463880 | Opened | 1328 - Townsend St | Permit to Excavate | 11/8/2020 | 5 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F84104.854 | Closed | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 11/8/2020 | 9 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F131475.58 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/8/2020 | 9 | 14/08/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.463812 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F119055.3 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/8/2020 | 12 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F131475.57 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/8/2020 | 9 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F116412.414 | Open / Ongoing Works | RM.02.335 - Corridor>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 11/8/2020 | 1 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.463735 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F116412.413 | JPC Sign Off | Rooms>2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 11/8/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118982.3 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F1.463568 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 11/8/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.463528 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 11/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.463375 | Subcontractor Signed Off | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 11/8/2020 | 12 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F116412.412 | Closed | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-225 Firestopping Inspection Checklist | 11/8/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.411 | Open / Ongoing Works | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.410 | Open / Ongoing Works | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.409 | Open / Ongoing Works | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.408 | Open / Ongoing Works | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.407 | Open / Ongoing Works | 3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.406 | Open / Ongoing Works | 3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.465021 | JPC Signed Off / Closed | 02 Daily Work Plan>Site Management>JPC Project Management | SM-FRM-SUB-101 Daily Work Plan | 12/8/2020 | 12 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 5
F107663.66 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 19/08/2020 | 11 | 19/08/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F113721.116 | Open / Ongoing Works | 4th to 5th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.153 | Open / Ongoing Works | 4th to 5th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F113721.187 | Open / Ongoing Works | 5th to 6th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 19/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F113721.139 | Open / Ongoing Works | 5th to 6th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 17/08/2020 | 8 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.140 | Open / Ongoing Works | 5th to 6th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.137 | Open / Ongoing Works | 6th to 7th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.134 | Open / Ongoing Works | 7th floor to Roof>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.466 | Open / Ongoing Works | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.124 | Open / Ongoing Works | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.464 | Open / Ongoing Works | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 13/08/2020 | 8 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.123 | Open / Ongoing Works | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.465 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.125 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.126 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.100 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.101 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.423 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.204 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.127 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.424 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.206 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.203 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.128 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.426 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.117 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.425 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.202 | Open / Ongoing Works | 5th to 6th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.129 | Open / Ongoing Works | 5th to 6th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.428 | Open / Ongoing Works | 5th to 6th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.103 | Open / Ongoing Works | 5th to 6th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.102 | Open / Ongoing Works | 5th to 6th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.427 | Open / Ongoing Works | 5th to 6th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.201 | Open / Ongoing Works | 6th to 7th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.130 | Open / Ongoing Works | 6th to 7th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.105 | Open / Ongoing Works | 6th to 7th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.104 | Open / Ongoing Works | 6th to 7th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.138 | Open / Ongoing Works | 6th to 7th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.429 | Open / Ongoing Works | 6th to 7th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.200 | Open / Ongoing Works | 7th floor to Roof>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.131 | Open / Ongoing Works | 7th floor to Roof>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.106 | Open / Ongoing Works | 7th floor to Roof>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.135 | Open / Ongoing Works | 7th floor to Roof>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.430 | Open / Ongoing Works | 7th floor to Roof>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.196 | Open / Ongoing Works | 2nd to 3rd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.155 | Open / Ongoing Works | 2nd to 3rd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.156 | Open / Ongoing Works | 2nd to 3rd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/08/2020 | 8 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.478 | Open / Ongoing Works | 3rd to 4th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 25/08/2020 | 10 | 25/08/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.154 | Open / Ongoing Works | 3rd to 4th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/08/2020 | 8 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.405 | Open / Ongoing Works | 3rd to 4th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.207 | Open / Ongoing Works | 4th to 5th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.194 | Open / Ongoing Works | 4th to 5th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.143 | Open / Ongoing Works | 4th to 5th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.144 | Open / Ongoing Works | 4th to 5th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 17/08/2020 | 8 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.145 | Open / Ongoing Works | 4th to 5th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.192 | Open / Ongoing Works | 5th to 6th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.141 | Open / Ongoing Works | 5th to 6th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.142 | Open / Ongoing Works | 5th to 6th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 17/08/2020 | 8 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.190 | Open / Ongoing Works | 6th to 7th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.157 | Open / Ongoing Works | 6th to 7th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.158 | Open / Ongoing Works | 6th to 7th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/08/2020 | 8 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.159 | Open / Ongoing Works | 6th to 7th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.189 | Open / Ongoing Works | 7th floor to Roof>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.160 | Open / Ongoing Works | 7th floor to Roof>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.161 | Open / Ongoing Works | 7th floor to Roof>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/08/2020 | 8 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.162 | Open / Ongoing Works | 7th floor to Roof>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.431 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.432 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.434 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.433 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.438 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.437 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.436 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.439 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.107 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.435 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.205 | Open / Ongoing Works | 4th to 5th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.195 | Open / Ongoing Works | 4th to 5th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.442 | Open / Ongoing Works | 4th to 5th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.441 | Open / Ongoing Works | 4th to 5th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.146 | Open / Ongoing Works | 4th to 5th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.108 | Open / Ongoing Works | 4th to 5th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.475 | Open / Ongoing Works | 4th to 5th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 21/08/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.147 | Open / Ongoing Works | 4th to 5th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.440 | Open / Ongoing Works | 4th to 5th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.193 | Open / Ongoing Works | 5th to 6th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.445 | Open / Ongoing Works | 5th to 6th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.444 | Open / Ongoing Works | 5th to 6th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.446 | Open / Ongoing Works | 5th to 6th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.447 | Open / Ongoing Works | 5th to 6th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.110 | Open / Ongoing Works | 5th to 6th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.109 | Open / Ongoing Works | 5th to 6th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.443 | Open / Ongoing Works | 5th to 6th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.191 | Open / Ongoing Works | 6th to 7th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.450 | Open / Ongoing Works | 6th to 7th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.451 | Open / Ongoing Works | 6th to 7th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.449 | Open / Ongoing Works | 6th to 7th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.112 | Open / Ongoing Works | 6th to 7th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.111 | Open / Ongoing Works | 6th to 7th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.448 | Open / Ongoing Works | 6th to 7th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.188 | Open / Ongoing Works | 7th floor to Roof>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.453 | Open / Ongoing Works | 7th floor to Roof>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.454 | Open / Ongoing Works | 7th floor to Roof>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.114 | Open / Ongoing Works | 7th floor to Roof>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.113 | Open / Ongoing Works | 7th floor to Roof>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.452 | Open / Ongoing Works | 7th floor to Roof>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.152 | Open / Ongoing Works | 3rd to 4th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.417 | Open / Ongoing Works | 5th to 6th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.418 | Open / Ongoing Works | 6th to 7th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.474 | Open / Ongoing Works | 6th to 7th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.148 | Open / Ongoing Works | 7th floor to Roof>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.122 | Open / Ongoing Works | 3rd to 4th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.118 | Open / Ongoing Works | 4th to 5th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.419 | Open / Ongoing Works | 5th to 6th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.120 | Open / Ongoing Works | 5th to 6th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.459 | Open / Ongoing Works | 5th to 6th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.458 | Open / Ongoing Works | 6th to 7th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.150 | Open / Ongoing Works | 6th to 7th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.461 | Open / Ongoing Works | 6th to 7th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.121 | Open / Ongoing Works | 6th to 7th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.460 | Open / Ongoing Works | 6th to 7th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.149 | Open / Ongoing Works | 7th floor to Roof>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.462 | Open / Ongoing Works | 7th floor to Roof>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.421 | Open / Ongoing Works | 1st to 2nd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.180 | Open / Ongoing Works | 1st to 2nd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.99 | Open / Ongoing Works | 2nd to 3rd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.422 | Open / Ongoing Works | 3rd to 4th Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.97 | Open / Ongoing Works | 4th to 5th Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.98 | Open / Ongoing Works | 6th to 7th Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.165 | Open / Ongoing Works | 1st to 2nd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.164 | Open / Ongoing Works | 1st to 2nd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.166 | Open / Ongoing Works | 2nd to 3rd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.163 | Open / Ongoing Works | 2nd to 3rd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.181 | Open / Ongoing Works | 2nd to 3rd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/08/2020 | 8 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.170 | Open / Ongoing Works | 3rd to 4th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.167 | Open / Ongoing Works | 3rd to 4th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.169 | Open / Ongoing Works | 3rd to 4th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.168 | Open / Ongoing Works | 3rd to 4th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.174 | Open / Ongoing Works | 4th to 5th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.171 | Open / Ongoing Works | 4th to 5th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.173 | Open / Ongoing Works | 4th to 5th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.172 | Open / Ongoing Works | 4th to 5th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.179 | Open / Ongoing Works | 5th to 6th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.175 | Open / Ongoing Works | 5th to 6th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.178 | Open / Ongoing Works | 5th to 6th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.177 | Open / Ongoing Works | 5th to 6th Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.467 | Open / Ongoing Works | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.457 | Open / Ongoing Works | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.477 | Open / Ongoing Works | Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 25/08/2020 | 10 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.472 | Open / Ongoing Works | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.471 | Open / Ongoing Works | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.470 | Open / Ongoing Works | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/08/2020 | 10 | 20/08/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.469 | Open / Ongoing Works | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 19/08/2020 | 10 | 19/08/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.479 | Open / Ongoing Works | Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 25/08/2020 | 10 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.420 | Closed | Area 1>6th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/8/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.455 | Closed | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/08/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.471196 | Open / Ongoing Works | 7th Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 19/08/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.453878 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/07/2020 | 6 | 31/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F1.444282 | Closed JPC Sign Off | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444281 | Closed JPC Sign Off | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444275 | Closed JPC Sign Off | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444273 | Closed JPC Sign Off | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444268 | Closed JPC Sign Off | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444259 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444255 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444251 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444241 | Closed JPC Sign Off | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444231 | Closed JPC Sign Off | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444152 | Closed JPC Sign Off | Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444144 | Closed JPC Sign Off | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444136 | Closed JPC Sign Off | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444121 | Closed JPC Sign Off | Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444089 | Closed JPC Sign Off | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.444068 | Closed JPC Sign Off | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/07/2020 | 11 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.443145 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/07/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F1.443122 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 21/07/2020 | 11 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.845 | Opened | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/07/2020 | 9 | 16/07/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F84104.844 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/07/2020 | 9 | 7/8/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F116412.397 | Open / Ongoing Works | Roof GA>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 14/07/2020 | 8 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F1.436269 | Closed | 4th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 13/07/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.435992 | Open / Ongoing Works | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-400 Mechancial BCAR Inspection | 13/07/2020 | 13 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.435988 | Open / Ongoing Works | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-400 Mechancial BCAR Inspection | 13/07/2020 | 13 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.435985 | Open / Ongoing Works | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-400 Mechancial BCAR Inspection | 13/07/2020 | 13 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.435979 | Open / Ongoing Works | ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-400 Mechancial BCAR Inspection | 13/07/2020 | 13 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F118318.359 | Open / Ongoing Works | RM.03.364>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 13/07/2020 | 8 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.358 | Open / Ongoing Works | RM.03.362>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 13/07/2020 | 8 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.357 | Open / Ongoing Works | RM.03.360>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 13/07/2020 | 8 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.356 | Open / Ongoing Works | RM.03.358>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 13/07/2020 | 8 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.355 | Open / Ongoing Works | RM.03.356>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 13/07/2020 | 8 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.353 | Open / Ongoing Works | RM.03.354>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 13/07/2020 | 8 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.842 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/07/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F1.434912 | Opened | 01 Inspections>EHS Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/7/2020 | 6 | 11/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F1.434751 | Open / Ongoing Works | Roof Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 10/7/2020 | 13 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.434744 | Open / Ongoing Works | 02 Drainage>ITP 03 External Works>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 10/7/2020 | 13 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.434738 | Open / Ongoing Works | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 10/7/2020 | 13 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.434693 | Closed JPC Sign Off | Roof Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/7/2020 | 11 | 17/08/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F122196.94 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F113721.89 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/7/2020 | 9 | 16/07/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F90895.93 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 10/7/2020 | 9 | 7/8/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.440439 | Open / Ongoing Works | ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F90895.94 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 17/07/2020 | 9 | 7/8/2020 | 0 | 8 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.440366 | Open / Ongoing Works | Quality Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.440331 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F1.440213 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F131475.55 | Open / Ongoing Works | 4th Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 17/07/2020 | 11 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.395 | Closed | RM.02.334 - Corridor>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-MEP-404 Electrical Inspection Report | 10/7/2020 | 1 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.392 | Closed | RM.03.440 - Corridor>Common Areas>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-MEP-404 Electrical Inspection Report | 10/7/2020 | 1 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.374 | Closed | Roof GA>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-211 Paralon Roof Inspection | 10/7/2020 | 8 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.433760 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 9/7/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F116412.373 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/7/2020 | 9 | 10/7/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F116412.372 | 3rd Party Sign Off - Closed | RM.01.113>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 9/7/2020 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.371 | JPC Sign Off | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 9/7/2020 | 1 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.370 | JPC Sign Off | RM.2.205>Rooms>2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 9/7/2020 | 1 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.432627 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/7/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F74906.96 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2020 | 9 | 10/7/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.432418 | Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/7/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.432150 | Closed JPC Sign Off | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 8/7/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F90895.92 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/7/2020 | 9 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F116412.367 | Open / Ongoing Works | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 8/7/2020 | 10 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.101 | Ready to be delivered | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 8/7/2020 | 8 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.100 | Ready to be delivered | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 8/7/2020 | 8 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.99 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 8/7/2020 | 8 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.98 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 8/7/2020 | 8 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.96 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 8/7/2020 | 8 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.95 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 8/7/2020 | 8 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.92 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F118318.352 | Open / Ongoing Works | RM.03.311>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.351 | Open / Ongoing Works | RM.02.202>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.350 | Open / Ongoing Works | RM.02.204>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.366 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/7/2020 | 9 | 10/7/2020 | 0 | 7 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F84104.841 | Open / Ongoing Works | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 9/7/2020 | 11 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F122196.93 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F131475.54 | Open / Ongoing Works | RM.04.474>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.53 | Open / Ongoing Works | RM.04.476>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.363 | Open / Ongoing Works | 1st to 2nd Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.52 | Open / Ongoing Works | RM.04.470>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.360 | Closed | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.429904 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/7/2020 | 9 | 10/7/2020 | 0 | 10 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.429841 | Closed | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 6/7/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.832 | Closed | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/7/2020 | 11 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.831 | Closed | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 6/7/2020 | 11 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F128229.1 | Open / Ongoing Works | EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 6/7/2020 | 9 | 6/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F102497.23 | Open / Ongoing Works | JPC Project Management | JPC-PM-FRM-001 - Minutes of Meeting | 6/7/2020 | 4 | 6/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 1
F84104.830 | Open / Ongoing Works | QC & BC(A)R | QM-FRM-QC-012 Quality Leadership Walk | 6/7/2020 | 10 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F102497.21 | Open / Ongoing Works | JPC Project Management | JPC-PM-FRM-001 - Minutes of Meeting | 6/7/2020 | 4 | 6/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 1
F131475.51 | Open / Ongoing Works | RM.04.472>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.50 | Open / Ongoing Works | RM.04.468>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.49 | Open / Ongoing Works | RM.04.466>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.48 | Open / Ongoing Works | RM.04.467>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.47 | Open / Ongoing Works | RM.04.465>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.46 | Open / Ongoing Works | RM.04.464>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.45 | Open / Ongoing Works | RM.04.462>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.44 | Open / Ongoing Works | RM.04.460>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.43 | Open / Ongoing Works | RM.04.458>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.42 | Open / Ongoing Works | RM.04.456>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.105 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 6/7/2020 | 8 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.104 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 6/7/2020 | 8 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.41 | Open / Ongoing Works | RM.04.454>Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.341 | Open / Ongoing Works | RM.03.336>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.340 | Open / Ongoing Works | RM.03.334>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.339 | Open / Ongoing Works | RM.03.304>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.90 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/7/2020 | 6 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F1.428889 | JPC Sign Off / Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 6/7/2020 | 11 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F122196.89 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/7/2020 | 6 | 4/7/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F122196.88 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/7/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.87 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/7/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.86 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/7/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.85 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/7/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.84 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/7/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.83 | Closed | Site Management>JPC Project Management | SM-FRM-006A Element Handover | 4/7/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.82 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/7/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.348 | Open / Ongoing Works | RM.03.350>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.347 | Open / Ongoing Works | RM.03.348>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.346 | Open / Ongoing Works | RM.03.346>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.345 | Open / Ongoing Works | RM.03.344>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.344 | Open / Ongoing Works | RM.03.342>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.343 | Open / Ongoing Works | RM.03.340>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.342 | Open / Ongoing Works | RM.03.338>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 7/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.349 | Open / Ongoing Works | R.01.240 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ME-401 Services Test | 7/7/2020 | 1 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.430599 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F122196.91 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F116412.352 | 3rd Party Sign Off - Closed | RM.01.136>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 3/7/2020 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F1.428018 | Open / Ongoing Works | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 3/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F84104.829 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/7/2020 | 9 | 10/7/2020 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F90895.91 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 3/7/2020 | 9 | 10/7/2020 | 0 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.828 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F1.427518 | Open / Ongoing Works | Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/7/2020 | 10 | 2/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F1.428542 | Open / Ongoing Works | Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 3/7/2020 | 10 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.356 | Closed JPC Reviewed | Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 3/7/2020 | 10 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F122196.81 | Opened | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/7/2020 | 9 | 2/7/2020 | 1 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F1.426567 | Open / Ongoing Works | ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 2/7/2020 | 13 | 2/7/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.426563 | Open / Ongoing Works | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 2/7/2020 | 13 | 2/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F122196.80 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/7/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F84104.827 | Closed JPC Sign Off | 3rd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 2/7/2020 | 11 | 20/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.426147 | Open / Ongoing Works | 3rd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 1/7/2020 | 10 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.342 | JPC Sign Off | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 1/7/2020 | 8 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F118318.338 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 1/7/2020 | 9 | 3/7/2020 | 0 | 23 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F131475.40 | Open / Ongoing Works | RM.04.450>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 1/7/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.94 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 1/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.93 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 1/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.337 | Open / Ongoing Works | RM.03.327>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 1/7/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.323 | Closed | RM.03.434 - Corridor>Common Areas>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-MEP-405 Mechanical Inspection Report | 30/06/2020 | 1 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.322 | Closed | RM.02.344 - Corridor>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-MEP-404 Electrical Inspection Report | 30/06/2020 | 1 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.321 | Closed | RM.02.344 - Corridor>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-MEP-405 Mechanical Inspection Report | 30/06/2020 | 1 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.336 | Open / Ongoing Works | RM.03.306>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.335 | Open / Ongoing Works | RM.03.308>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.334 | Open / Ongoing Works | RM.03.309>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.333 | Open / Ongoing Works | RM.03.307>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.332 | Open / Ongoing Works | RM.03.305>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.331 | Open / Ongoing Works | RM.02.344 - Corridor>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ME-401 Services Test | 30/06/2020 | 1 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.92 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 30/06/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.91 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 30/06/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.330 | Open / Ongoing Works | RM.03.303>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.329 | Open / Ongoing Works | RM.03.301>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.39 | Open / Ongoing Works | RM.04.446>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.826 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 30/06/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.825 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 30/06/2020 | 11 | 19/08/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F122196.77 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F1.424036 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 30/06/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F74906.95 | Closed | Site Management>JPC Project Management | CM-EHS-FRM-009 Temporary Electrics Inspection | 29/06/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.823 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 29/06/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F131475.38 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 29/06/2020 | 9 | 3/7/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F131475.37 | Open / Ongoing Works | RM.04.452>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.36 | Open / Ongoing Works | RM.04.448>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.35 | Open / Ongoing Works | RM.04.444>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.34 | Open / Ongoing Works | RM.04.442>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.33 | Open / Ongoing Works | RM.04.440>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.32 | Open / Ongoing Works | RM.04.438>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.90 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 29/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.89 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 29/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.31 | Open / Ongoing Works | RM.04.430>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.88 | In Manufactor | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F131475.30 | Open / Ongoing Works | RM.04.432>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.29 | Open / Ongoing Works | RM.04.436>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.28 | Open / Ongoing Works | RM.04.434>Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.87 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 29/06/2020 | 8 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.86 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 29/06/2020 | 8 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.84 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 29/06/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.83 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 29/06/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.74 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 29/06/2020 | 6 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F84104.822 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/06/2020 | 6 | 27/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F1.422136 | JPC Sign Off / Closed | 3rd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 26/06/2020 | 11 | 17/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.821 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/06/2020 | 11 | 6/7/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90895.90 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 26/06/2020 | 9 | 3/7/2020 | 0 | 8 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F131475.27 | Open / Ongoing Works | RM.04.403>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.26 | Open / Ongoing Works | RM.04.402>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.25 | Open / Ongoing Works | RM.04.406>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.23 | Open / Ongoing Works | RM.04.405>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.22 | Open / Ongoing Works | RM.04.407>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.21 | Open / Ongoing Works | RM.04.404>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.86 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/06/2020 | 9 | 26/06/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F122196.73 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F84104.820 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/06/2020 | 11 | 16/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.421425 | JPC Sign Off / Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 26/06/2020 | 11 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.421294 | Open / Ongoing Works | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 25/06/2020 | 10 | 25/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.425427 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.79 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F1.425239 | JPC Sign Off / Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 1/7/2020 | 11 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.330 | Open / Ongoing Works | RM.2.217>Rooms>2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 30/06/2020 | 1 | 30/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F122196.78 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 30/06/2020 | 9 | 3/7/2020 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F116412.329 | Closed | Roof GA>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 30/06/2020 | 10 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.824 | Closed JPC Sign Off | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 29/06/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.819 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/06/2020 | 9 | 26/06/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.818 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/06/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F113721.85 | Open / Ongoing Works | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/06/2020 | 11 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.318 | Closed | Roof GA>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 25/06/2020 | 10 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.817 | JPC Sign Off / Closed | 3rd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 25/06/2020 | 11 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.328 | Open / Ongoing Works | RM.03.310>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.327 | Open / Ongoing Works | RM.03.312>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.326 | Open / Ongoing Works | RM.03.313>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.325 | Open / Ongoing Works | RM.03.314>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.324 | Open / Ongoing Works | RM.03.315>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.323 | Open / Ongoing Works | RM.03.316>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.322 | Open / Ongoing Works | RM.03.319>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.321 | Open / Ongoing Works | RM.03.317>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.320 | Open / Ongoing Works | RM.03.318>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.318 | Open / Ongoing Works | RM.03.311>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 25/06/2020 | 10 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.82 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 25/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.81 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 25/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.317 | Open / Ongoing Works | RM.02.340 - Risers>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ME-401 Services Test | 25/06/2020 | 1 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.67 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F120172.80 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 23/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.19 | Open / Ongoing Works | RM.04.408>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.18 | Open / Ongoing Works | RM.04.410>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.79 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 23/06/2020 | 8 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.17 | Open / Ongoing Works | RM.04.409>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.16 | Open / Ongoing Works | RM.04.411>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.15 | Open / Ongoing Works | RM.04.415>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.14 | Open / Ongoing Works | RM.04.413>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.13 | Open / Ongoing Works | RM.04.412>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.316 | Open / Ongoing Works | RM.03.325>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.315 | Open / Ongoing Works | RM.03.321>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.314 | Open / Ongoing Works | RM.03.320>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.312 | Open / Ongoing Works | RM.03.322>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.311 | Open / Ongoing Works | RM.03.324>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F74906.94 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | DRAFT_CM-EHS-FRM-009 Temporary Electrics Inspection | 23/06/2020 | 9 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 2
F84104.814 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/06/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.417685 | Closed | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 22/06/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.417667 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 22/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F129620.6 | Open / Ongoing Works | Audits & Assessments>Quality Management>JPC Project Management | QM-FRM-QC-012 Quality Leadership Walk | 22/06/2020 | 10 | 22/06/2020 | 3 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F74906.93 | Open / Ongoing Works | EHS Management>JPC Project Management | DRAFT_CM-EHS-FRM-009 Temporary Electrics Inspection | 22/06/2020 | 9 | 22/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F84104.813 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 22/06/2020 | 11 | 6/7/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.310 | JPC Sign Off / Closed | RM.04.533 - Corridor>Common Areas>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 22/06/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F118318.309 | Open / Ongoing Works | RM.03.433 - Corridor>Common Areas>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.308 | Open / Ongoing Works | RM.03.323>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.12 | Open / Ongoing Works | RM.04.414>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.11 | Open / Ongoing Works | RM.04.416>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.9 | Open / Ongoing Works | RM.04.417>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.307 | Open / Ongoing Works | RM.02.273>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.8 | Open / Ongoing Works | RM.04.543 - Corridor>Common Areas>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.7 | Open / Ongoing Works | RM.04.419>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.306 | Open / Ongoing Works | RM.02.267>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.6 | Open / Ongoing Works | RM.04.418>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.305 | Open / Ongoing Works | RM.02.265>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.78 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 22/06/2020 | 8 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.77 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 22/06/2020 | 8 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.420275 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 24/06/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.420269 | Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 24/06/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F113721.84 | Open / Ongoing Works | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 24/06/2020 | 11 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.315 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/06/2020 | 9 | 26/06/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F122196.66 | Open | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 24/06/2020 | 9 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F122196.65 | Opened | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 24/06/2020 | 9 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F1.419427 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 24/06/2020 | 11 | 6/7/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F131475.20 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/06/2020 | 9 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.816 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.419197 | Open / Ongoing Works | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 24/06/2020 | 11 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F113721.83 | JPC Sign Off / Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 24/06/2020 | 11 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.418948 | Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 23/06/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.417015 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 22/06/2020 | 11 | 6/7/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.812 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 22/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F131475.4 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 20/06/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.811 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 20/06/2020 | 11 | 6/7/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F131475.2 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/06/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F118318.304 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 19/06/2020 | 9 | 26/06/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F116412.303 | Closed JPC Reviewed | Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 19/06/2020 | 10 | 19/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F116412.302 | Closed | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-MEP-405 Mechanical Inspection Report | 19/06/2020 | 1 | 10/9/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.301 | Closed | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-MEP-405 Mechanical Inspection Report | 19/06/2020 | 1 | 10/9/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.300 | Closed | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 19/06/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.299 | Closed | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 19/06/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90895.89 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 19/06/2020 | 9 | 7/8/2020 | 0 | 8 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F120172.76 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 19/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.75 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 19/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.810 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/06/2020 | 6 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.415667 | Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 19/06/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.415646 | Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 19/06/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.415567 | Open / Ongoing Works | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 18/06/2020 | 13 | 18/06/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F116412.296 | 3rd Party Sign Off - Closed | RM.01.132>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 18/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.809 | JPC Sign Off / Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 18/06/2020 | 11 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.303 | Open / Ongoing Works | RM.02.276>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/06/2020 | 8 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.302 | Open / Ongoing Works | RM.02.274>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/06/2020 | 8 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.301 | Open / Ongoing Works | RM.02.272>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/06/2020 | 8 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.415195 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 18/06/2020 | 10 | 9/7/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F129620.5 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/06/2020 | 9 | 26/06/2020 | 0 | 16 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.300 | Open / Ongoing Works | RM.02.270>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/06/2020 | 8 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.299 | Open / Ongoing Works | RM.02.270>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | JPC-QC-CL-204 Void Closure Sign Off (Walls and Ceilings) | 18/06/2020 | 8 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.415025 | Closed | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 18/06/2020 | 10 | 9/7/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F120172.74 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 18/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.73 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 18/06/2020 | 8 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.414916 | Closed JPC Sign Off | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 18/06/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.808 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/06/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F84104.807 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/06/2020 | 9 | 26/06/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F120172.72 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 17/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.71 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 17/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.413763 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 17/06/2020 | 13 | 17/06/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.413757 | Open / Ongoing Works | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 17/06/2020 | 13 | 17/06/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.413748 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.413700 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.413625 | JPC Sign Off / Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 17/06/2020 | 11 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.806 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.413403 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/06/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.413402 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/06/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F108023.103 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.102 | Ready to be delivered | ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 22/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.416982 | Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 22/06/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.413343 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/06/2020 | 10 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.413327 | JPC Sign Off / Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 16/06/2020 | 11 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.298 | Open / Ongoing Works | RM.04.420>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.413293 | Closed JPC Sign Off | 7th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/06/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F118318.297 | Open / Ongoing Works | RM.04.421>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.296 | Open / Ongoing Works | RM.04.423>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.295 | Open / Ongoing Works | RM.04.422>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.294 | Open / Ongoing Works | RM.04.425>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.293 | Open / Ongoing Works | RM.04.424>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.292 | In Manufactor | RM.04.424>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | B-Pod - Bathroom Pod ITP Inspection. | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.290 | Open / Ongoing Works | RM.04.427>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.289 | Open / Ongoing Works | RM.04.426>Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.288 | Completed and signed off | ITP 02 Architectural & M&E Services>QC & BC(A)R | EHS Managment Inspection - Daily | 16/06/2020 | 9 | 18/06/2020 | 0 | 15 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F118318.287 | Open / Ongoing Works | RM.02.268>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.286 | Open / Ongoing Works | RM.02.266>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.285 | Open / Ongoing Works | RM.02.264>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.284 | Open / Ongoing Works | RM.02.262>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/06/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.804 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/06/2020 | 11 | 6/7/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.289 | 3rd Party Sign Off - Closed | RM.01.109>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 16/06/2020 | 1 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F118318.283 | Open / Ongoing Works | RM.02.274>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/06/2020 | 10 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.282 | Open / Ongoing Works | RM.01.132>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/06/2020 | 10 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.281 | Open / Ongoing Works | RM.01.171>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/06/2020 | 10 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.803 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 16/06/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F122196.64 | Open / Ongoing Works | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/06/2020 | 11 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F113721.79 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/06/2020 | 11 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.63 | Open / Ongoing Works | QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 15/06/2020 | 10 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.280 | Open / Ongoing Works | RM.01.101>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 15/06/2020 | 10 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.802 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/06/2020 | 9 | 18/06/2020 | 0 | 12 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F122196.61 | Open / Ongoing Works | Quality Management>JPC Project Management | Draft QM-FRM-QC-012 Quality Leadership Walk | 15/06/2020 | 10 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.78 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/6/2020 | 9 | 18/06/2020 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.800 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/6/2020 | 11 | 16/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90895.88 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 12/6/2020 | 9 | 18/06/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90895.87 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.799 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F113721.77 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/6/2020 | 11 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F84104.798 | JPC Sign Off / Closed | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 11/6/2020 | 11 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.797 | Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 11/6/2020 | 11 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.410154 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 11/6/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F90895.86 | Closed | 1328 - Townsend St | CM-EHS-FRM-007 COVID-19 Inspection | 11/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F116412.286 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2020 | 9 | 12/6/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F116412.285 | Closed | RM.01.106>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.284 | Closed JPC Reviewed | Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 11/6/2020 | 10 | 17/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F118318.279 | Open / Ongoing Works | RM.02.252>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.278 | Open / Ongoing Works | RM.02.250>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.277 | Open / Ongoing Works | RM.02.248>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.276 | Open / Ongoing Works | RM.02.244>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.796 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 11/6/2020 | 11 | 20/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90895.85 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.409022 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/6/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F74906.92 | Open / Ongoing Works | 6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/6/2020 | 10 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.413352 | Closed | 2nd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/06/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.411548 | JPC Sign Off / Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 15/06/2020 | 11 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.801 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 15/06/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F74906.89 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/6/2020 | 9 | 12/6/2020 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.408507 | JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 10/6/2020 | 13 | 8/9/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.408428 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/6/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.274 | Open / Ongoing Works | R.01.225 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 10/6/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.408372 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.408221 | Open / Ongoing Works | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/6/2020 | 11 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F90895.84 | Closed | 1328 - Townsend St | CM-EHS-FRM-007 COVID-19 Inspection | 10/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.408623 | Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 10/6/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.408087 | Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 9/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.407859 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 9/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.407846 | Closed | 1328 - Townsend St | QM-FRM-QC-008 Non Conformance Record (NCR) | 9/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F90895.83 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F108023.101 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 9/6/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F131475.1 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/6/2020 | 9 | 12/6/2020 | 0 | 5 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F1.407402 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 9/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F122196.59 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.407305 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 9/6/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.407279 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 9/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.407151 | Open / Ongoing Works | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/6/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F1.407149 | JPC Sign Off / Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 8/6/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.407110 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/6/2020 | 9 | 12/6/2020 | 0 | 14 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F116412.275 | JPC Sign Off | 5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/6/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.407096 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 8/6/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.793 | Closed | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F90895.81 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.792 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 8/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.406588 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 8/6/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F108023.100 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 8/6/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.272 | Open / Ongoing Works | RM.02.246>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/6/2020 | 8 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.99 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 8/6/2020 | 8 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.271 | Open / Ongoing Works | RM.02.242>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/6/2020 | 8 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.791 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/6/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.406036 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/6/2020 | 6 | 6/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F129620.4 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 5/6/2020 | 10 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F129620.3 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 5/6/2020 | 10 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.273 | Open / Ongoing Works | Quality Management>JPC Project Management | Draft QM-FRM-QC-012 Quality Leadership Walk | 5/6/2020 | 10 | 5/6/2020 | 3 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F90895.80 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.405544 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 5/6/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.272 | Closed | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 5/6/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90895.79 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 5/6/2020 | 9 | 12/6/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.790 | Closed JPC Sign Off | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 5/6/2020 | 11 | 16/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F108023.98 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 5/6/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.97 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 5/6/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.405332 | JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 5/6/2020 | 13 | 8/9/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.405331 | Open / Ongoing Works | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 5/6/2020 | 13 | 5/6/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F84104.789 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/6/2020 | 9 | 12/6/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F122196.58 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/6/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.404986 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 4/6/2020 | 10 | 4/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.404976 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 4/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.404829 | Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 4/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.404801 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 4/6/2020 | 10 | 4/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F122196.57 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/6/2020 | 9 | 12/6/2020 | 0 | 20 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F118318.270 | Open / Ongoing Works | R.01.226 - Plant Room>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.269 | Open / Ongoing Works | RM.02.240>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.268 | Open / Ongoing Works | RM.02.238>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.267 | Open / Ongoing Works | RM.02.236>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.266 | Open / Ongoing Works | RM.02.234>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.265 | Open / Ongoing Works | RM.02.232>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.264 | Open / Ongoing Works | RM.02.230>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.78 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.404562 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 4/6/2020 | 13 | 4/6/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.404560 | Open / Ongoing Works | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 4/6/2020 | 13 | 4/6/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F108023.96 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 4/6/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.95 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 4/6/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.788 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/6/2020 | 6 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.408099 | Closed JPC Sign Off | 1328 - Townsend St | 1328 QM-CL-CS-116 Concrete Cube Record | 9/6/2020 | 11 | 9/6/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.408100 | Closed JPC Sign Off | 1328 - Townsend St | 1328 QM-CL-CS-116 Concrete Cube Record | 9/6/2020 | 11 | 9/6/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.408101 | Closed JPC Sign Off | 1328 - Townsend St | 1328 QM-CL-CS-116 Concrete Cube Record | 9/6/2020 | 11 | 9/6/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.408102 | Closed JPC Sign Off | 1328 - Townsend St | 1328 QM-CL-CS-116 Concrete Cube Record | 9/6/2020 | 11 | 9/6/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.408103 | Closed JPC Sign Off | 1328 - Townsend St | 1328 QM-CL-CS-116 Concrete Cube Record | 9/6/2020 | 11 | 9/6/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F116412.316 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/06/2020 | 11 | 24/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F116412.317 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/06/2020 | 11 | 24/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.68 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/06/2020 | 11 | 25/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.69 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/06/2020 | 11 | 25/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.70 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/06/2020 | 11 | 25/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.71 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/06/2020 | 11 | 25/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.72 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/06/2020 | 11 | 25/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.75 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 29/06/2020 | 11 | 29/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.95 | Closed JPC Sign Off | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/07/2020 | 11 | 16/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.96 | Closed JPC Sign Off | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/07/2020 | 11 | 16/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.97 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/07/2020 | 11 | 16/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.98 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/07/2020 | 11 | 16/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.99 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/07/2020 | 11 | 16/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.100 | Closed JPC Sign Off | Roof Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 21/07/2020 | 11 | 21/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.101 | Closed JPC Sign Off | Roof Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 21/07/2020 | 11 | 21/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F122196.102 | Closed JPC Sign Off | Roof Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 21/07/2020 | 11 | 21/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.794 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/6/2020 | 11 | 8/6/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.795 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/6/2020 | 11 | 8/6/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.815 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/06/2020 | 11 | 23/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.833 | Closed JPC Sign Off | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 6/7/2020 | 11 | 6/7/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.834 | Closed JPC Sign Off | 3rd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/7/2020 | 11 | 7/7/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.835 | Closed JPC Sign Off | 3rd Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/7/2020 | 11 | 7/7/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.836 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/7/2020 | 11 | 8/7/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.837 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/7/2020 | 11 | 8/7/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.838 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/7/2020 | 11 | 8/7/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.839 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/7/2020 | 11 | 16/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.805 | Open / Ongoing Works | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 16/06/2020 | 10 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F116412.291 | Open / Ongoing Works | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 16/06/2020 | 10 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F116412.292 | Open / Ongoing Works | 3rd to 4th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 16/06/2020 | 10 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F116412.346 | Open / Ongoing Works | 4th to 5th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/7/2020 | 10 | 2/7/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.268 | Closed | 4th to 5th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 4/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F113721.81 | Open / Ongoing Works | 4th to 5th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 22/06/2020 | 10 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.288 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 15/06/2020 | 10 | 15/06/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.281 | Closed | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/6/2020 | 10 | 10/9/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.280 | Closed | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.344 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/7/2020 | 10 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.279 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 10/6/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.278 | Closed | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.76 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/6/2020 | 10 | 10/6/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.82 | Open / Ongoing Works | 5th to 6th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 23/06/2020 | 10 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.355 | Open / Ongoing Works | 7th floor to Roof>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/7/2020 | 10 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.369 | Closed | 1st to 2nd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.88 | Open / Ongoing Works | 2nd to 3rd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/7/2020 | 10 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.87 | Open / Ongoing Works | 3rd to 4th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/7/2020 | 10 | 2/7/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.341 | Open / Ongoing Works | 3rd to 4th Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/7/2020 | 10 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.368 | Closed | 1st to 2nd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/7/2020 | 10 | 10/9/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.74 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 9/6/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.75 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/6/2020 | 10 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.274 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 8/6/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.293 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/06/2020 | 10 | 18/06/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.340 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/7/2020 | 10 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.339 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/7/2020 | 10 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.287 | Closed | 1st to 2nd Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.362 | Open / Ongoing Works | 2nd to 3rd Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.283 | Open / Ongoing Works | 2nd to 3rd Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/6/2020 | 10 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.319 | Open / Ongoing Works | 3rd to 4th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 29/06/2020 | 10 | 29/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.377 | Open / Ongoing Works | 4th to 5th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.276 | Open / Ongoing Works | 1st to 2nd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/6/2020 | 10 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F116412.364 | Open / Ongoing Works | 1st to 2nd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F74906.90 | Closed | 2nd to 3rd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/6/2020 | 10 | 8/9/2020 | 4 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.365 | Open / Ongoing Works | 2nd to 3rd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/7/2020 | 10 | 7/7/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.277 | Open / Ongoing Works | 3rd to 4th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/6/2020 | 10 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.320 | Open / Ongoing Works | 4th to 5th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 29/06/2020 | 10 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.358 | Open / Ongoing Works | 2nd to 3rd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.357 | Open / Ongoing Works | 2nd to 3rd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.314 | Open / Ongoing Works | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/06/2020 | 10 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.313 | Open / Ongoing Works | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/06/2020 | 10 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.325 | Closed JPC Sign Off | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 30/06/2020 | 11 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.326 | Closed JPC Sign Off | Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 30/06/2020 | 11 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.351 | Open / Ongoing Works | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/7/2020 | 10 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.347 | Open / Ongoing Works | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/7/2020 | 10 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.394 | Open / Ongoing Works | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.350 | Closed | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.396 | Open / Ongoing Works | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.327 | Closed JPC Sign Off | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 30/06/2020 | 11 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.348 | Closed | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.324 | Closed JPC Sign Off | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 30/06/2020 | 11 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.349 | Open / Ongoing Works | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/7/2020 | 10 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.328 | Closed JPC Sign Off | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 30/06/2020 | 11 | 30/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F116412.393 | Closed | Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.310 | Closed JPC Sign Off | Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 22/06/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.390 | Open / Ongoing Works | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.391 | Closed | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.389 | Closed | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.267 | Closed | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 4/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F116412.311 | Closed JPC Sign Off | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 22/06/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.386 | Open / Ongoing Works | Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.388 | Open / Ongoing Works | Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.385 | Closed | Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.387 | Closed | Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.312 | Closed JPC Sign Off | Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 22/06/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.381 | Open / Ongoing Works | Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.382 | Open / Ongoing Works | Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.271 | Closed | Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 5/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F116412.304 | Closed JPC Sign Off | Area 1>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 22/06/2020 | 11 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.383 | Open / Ongoing Works | Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.376 | Closed | Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F116412.305 | Closed JPC Sign Off | Area 2>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 22/06/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.384 | Closed | Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.375 | Closed | Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F116412.306 | Closed JPC Sign Off | Area 3>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 22/06/2020 | 11 | 23/06/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.380 | Open / Ongoing Works | Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.309 | Closed JPC Sign Off | Area 1>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 22/06/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.378 | Open / Ongoing Works | Area 2>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.308 | Closed JPC Sign Off | Area 2>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 22/06/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.379 | Open / Ongoing Works | Area 3>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.307 | Closed JPC Sign Off | Area 3>5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 22/06/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.337 | Closed JPC Sign Off | Area 1>6th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.338 | Closed JPC Sign Off | Area 2>6th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.431181 | Open / Ongoing Works | Area 3>6th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.354 | Closed JPC Sign Off | Area 3>6th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/7/2020 | 11 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.336 | Open / Ongoing Works | Area 1>7th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.331 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 1/7/2020 | 11 | 6/7/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.431191 | Open / Ongoing Works | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.359 | Closed | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.361 | Open / Ongoing Works | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 7/7/2020 | 8 | 7/7/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.332 | Closed JPC Sign Off | 2nd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.353 | Closed JPC Sign Off | 3rd Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/7/2020 | 11 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.333 | Closed JPC Sign Off | 4th Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.334 | Closed JPC Sign Off | 5th Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 1/7/2020 | 11 | 6/7/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.335 | Closed JPC Sign Off | 6th Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 1/7/2020 | 11 | 19/08/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.428704 | Open / Ongoing Works | 7th Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 4/7/2020 | 10 | 4/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F122196.56 | Closed JPC Sign Off | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 4/6/2020 | 11 | 9/6/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.786 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.73 | Open / Ongoing Works | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.72 | Open / Ongoing Works | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.71 | Open / Ongoing Works | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.70 | Open / Ongoing Works | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.69 | Open / Ongoing Works | 5th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.68 | Open / Ongoing Works | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.67 | Open / Ongoing Works | 2nd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.66 | Open / Ongoing Works | 2nd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.65 | Open / Ongoing Works | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.64 | Open / Ongoing Works | 4th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.403916 | Open / Ongoing Works | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 3/6/2020 | 10 | 3/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F90895.77 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.784 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 3/6/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F108023.94 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 3/6/2020 | 8 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.93 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 3/6/2020 | 8 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.92 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 3/6/2020 | 8 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.91 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 3/6/2020 | 8 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.90 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 3/6/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.89 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 3/6/2020 | 8 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.55 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/6/2020 | 9 | 12/6/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.783 | Closed | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 3/6/2020 | 11 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F113721.62 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/6/2020 | 6 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.402965 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.402953 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/6/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F116412.259 | 3rd Party Sign Off - Closed | ITP 04 M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 2/6/2020 | 1 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.76 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.781 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/6/2020 | 9 | 12/6/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F108023.88 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 2/6/2020 | 8 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.87 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 2/6/2020 | 8 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.402545 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 2/6/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.257 | Open / Ongoing Works | 1328 - Townsend St | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/6/2020 | 10 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.258 | Open / Ongoing Works | ITP 04 M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/6/2020 | 10 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.256 | Open / Ongoing Works | RM.01.104>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/6/2020 | 10 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F122196.54 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/6/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.401134 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 29/05/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.399291 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/05/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F90895.72 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.399106 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 27/05/2020 | 11 | 16/07/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F122196.50 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/05/2020 | 9 | 12/6/2020 | 0 | 15 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F122196.49 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F118318.253 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.398110 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/05/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.398008 | Closed | Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 26/05/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F1.398005 | Closed | 5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 26/05/2020 | 10 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F1.397996 | Closed | 6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 26/05/2020 | 10 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F129620.2 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/05/2020 | 9 | 12/6/2020 | 0 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F108023.83 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 26/05/2020 | 8 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.397654 | Closed JPC Sign Off | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/05/2020 | 11 | 21/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F108023.82 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 26/05/2020 | 8 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.252 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F108023.81 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 25/05/2020 | 8 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.80 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 25/05/2020 | 8 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F129620.1 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F108023.79 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/05/2020 | 8 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.78 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/05/2020 | 8 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.251 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.249 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F116412.246 | Open / Ongoing Works | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 21/05/2020 | 11 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.245 | Open / Ongoing Works | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 21/05/2020 | 11 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F116412.244 | Open / Ongoing Works | 5th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 21/05/2020 | 11 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F116412.243 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 3
F116412.242 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F1.395430 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/05/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.248 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/05/2020 | 9 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F116412.241 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F1.394563 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/05/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.247 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 19/05/2020 | 9 | 19/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F116412.240 | Open / Ongoing Works | General Site Plan>JPC Project Management | QM-FRM-QC-009 Quality Control Record | 19/05/2020 | 10 | 19/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.393494 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/05/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F118318.246 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 18/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F74906.88 | Opened | Site Management>JPC Project Management | CM-EHS-FRM-008 Daily Site Access Register | 18/05/2020 | 9 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F1.392404 | Closed | 6th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 15/05/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.388934 | Closed | 1328 - Townsend St | JPC-HR-FRM-001 - Training Record | 11/5/2020 | 2 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.388902 | Closed | 1328 - Townsend St | JPC-HR-FRM-001 - Training Record | 11/5/2020 | 2 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F77029.52 | Completed and signed off | 1328 - Townsend St | CM-EHS-FRM-008 Daily Site Access Register | 1/5/2020 | 9 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F113721.63 | JPC Sign Off / Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 3/6/2020 | 11 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F118318.262 | Open / Ongoing Works | RM.03.360>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 3/6/2020 | 8 | 3/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.261 | Open / Ongoing Works | RM.03.358>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 3/6/2020 | 8 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.260 | Open / Ongoing Works | RM.03.356>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 3/6/2020 | 8 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.259 | Open / Ongoing Works | RM.03.354>Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 3/6/2020 | 8 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.258 | Open / Ongoing Works | RM.03.315>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 3/6/2020 | 10 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F122196.53 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/05/2020 | 9 | 12/6/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F90895.75 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90895.74 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 29/05/2020 | 9 | 12/6/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F108023.86 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/05/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.85 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/05/2020 | 8 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.52 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 29/05/2020 | 6 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F116412.250 | Open / Ongoing Works | 2nd to 3rd Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 28/05/2020 | 10 | 28/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F84104.780 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 28/05/2020 | 11 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.73 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.255 | Completed and signed off | ITP 02 Architectural & M&E Services>QC & BC(A)R | EHS Managment Inspection - Daily | 28/05/2020 | 9 | 12/6/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F108023.84 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 28/05/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.399586 | JPC Sign Off | ITP 04 M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 28/05/2020 | 1 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F1.399583 | JPC Sign Off | ITP 04 M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 28/05/2020 | 1 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F118318.254 | Open / Ongoing Works | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 28/05/2020 | 10 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.399573 | Closed | ITP 04 M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 28/05/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.399554 | Closed | ITP 04 M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 28/05/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F122196.51 | Opened | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 28/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 3
F1.374435 | Open / Ongoing Works | 1328 - Townsend St | QM-FRM-QC-008 Non Conformance Record (NCR) | 9/4/2020 | 10 | 9/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.372975 | Open / Ongoing Works | 1328 - Townsend St | QM-FRM-QC-008 Non Conformance Record (NCR) | 7/4/2020 | 10 | 7/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F1.370738 | JPC Sign Off / Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-ME-405 Lightning Protection & Earthing Inspection | 2/4/2020 | 1 | 6/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.370401 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 1/4/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.370356 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 1/4/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.370340 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 1/4/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.370325 | JPC Sign Off / Closed | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 1/4/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.370313 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 1/4/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.368275 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/03/2020 | 9 | 31/03/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F120172.69 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 27/03/2020 | 8 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.67 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 27/03/2020 | 8 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.66 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 27/03/2020 | 8 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.32 | JPC Sign Off / Closed | Roof Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 27/03/2020 | 11 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.764 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/03/2020 | 9 | 31/03/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F113721.31 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/03/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F90895.71 | Closed | 1328 - Townsend St | EHS Inspection. | 27/03/2020 | 9 | 31/03/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.367936 | JPC Sign Off / Closed | 2nd Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 27/03/2020 | 11 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90895.70 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 27/03/2020 | 9 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.245 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 27/03/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.367705 | 3rd Party Sign Off - Closed | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 26/03/2020 | 13 | 18/08/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.367704 | 3rd Party Sign Off - Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 26/03/2020 | 13 | 19/08/2020 | 0 | 1 | parent | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 6
F1.367689 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/03/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F110032.27 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/03/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F110032.26 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 26/03/2020 | 11 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.763 | Closed JPC Sign Off | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/03/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.761 | Open / Ongoing Works | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 26/03/2020 | 10 | 26/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F84104.760 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 26/03/2020 | 10 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90895.69 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 26/03/2020 | 9 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.759 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 26/03/2020 | 10 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.244 | Open / Ongoing Works | RM.02.207>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/03/2020 | 8 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.243 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 26/03/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.758 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/03/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.369844 | 3rd Party Sign Off - Closed | 5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 31/03/2020 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.369749 | JPC Sign Off / Closed | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 31/03/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.368310 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/03/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.367032 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/03/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.367030 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/03/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F90895.68 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 25/03/2020 | 9 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.242 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 25/03/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.45 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/03/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F90895.67 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 24/03/2020 | 9 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.366237 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 24/03/2020 | 11 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.28 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/03/2020 | 9 | 27/03/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F120172.61 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 24/03/2020 | 8 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.60 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 24/03/2020 | 8 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.59 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 24/03/2020 | 8 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.58 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 24/03/2020 | 8 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.366033 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 24/03/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.241 | Open / Ongoing Works | RM.02.206>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/03/2020 | 8 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.240 | Open / Ongoing Works | RM.02.215>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/03/2020 | 8 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.239 | Open / Ongoing Works | RM.02.211>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/03/2020 | 8 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.238 | Open / Ongoing Works | RM.02.209>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/03/2020 | 8 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.237 | Open / Ongoing Works | RM.02.201>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/03/2020 | 8 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.43 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/03/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 3
F118318.236 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 24/03/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.365742 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/03/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.365712 | Open / Ongoing Works | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 23/03/2020 | 10 | 23/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F90895.66 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 23/03/2020 | 9 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.235 | Open / Ongoing Works | RM.03.350>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.234 | Open / Ongoing Works | RM.03.348>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.233 | Open / Ongoing Works | RM.03.346>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.232 | Open / Ongoing Works | RM.03.344>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.231 | Open / Ongoing Works | RM.03.342>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.230 | Open / Ongoing Works | RM.03.340>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.228 | Open / Ongoing Works | RM.03.338>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.227 | Open / Ongoing Works | RM.03.334>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.365571 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 23/03/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.225 | Open / Ongoing Works | RM.03.336>Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.39 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/03/2020 | 9 | 27/03/2020 | 0 | 17 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F118318.209 | Completed and signed off | Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1328 CM-SM-FRM-001 Site Diary | 20/03/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F90895.61 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/03/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F122196.38 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 19/03/2020 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.364036 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/03/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F122196.37 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 19/03/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.364002 | JPC Sign Off / Closed | Precast Walls>Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 19/03/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F90895.60 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/03/2020 | 9 | 29/04/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F90895.59 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/03/2020 | 9 | 29/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F120172.57 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/03/2020 | 8 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.56 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/03/2020 | 8 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.58 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 19/03/2020 | 9 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.208 | Open / Ongoing Works | RM.03.327>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 19/03/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.207 | Open / Ongoing Works | RM.03.325>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 19/03/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.206 | Open / Ongoing Works | RM.03.323>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 19/03/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.205 | Open / Ongoing Works | RM.03.321>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 19/03/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.204 | Open / Ongoing Works | RM.03.319>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 19/03/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.203 | Open / Ongoing Works | RM.03.317>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 19/03/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.202 | Open / Ongoing Works | RM.03.315>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 19/03/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.201 | Open / Ongoing Works | RM.03.313>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 19/03/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.36 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 19/03/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F90895.57 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/03/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F118318.200 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 19/03/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.363107 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/03/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F122196.32 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 18/03/2020 | 6 | 25/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.31 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 18/03/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.199 | Open / Ongoing Works | RM.03.311>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/03/2020 | 8 | 18/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.198 | Open / Ongoing Works | RM.03.326>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/03/2020 | 8 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.197 | Open / Ongoing Works | RM.03.324>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/03/2020 | 8 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.196 | Open / Ongoing Works | RM.03.322>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/03/2020 | 8 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.195 | Open / Ongoing Works | RM.03.320>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/03/2020 | 8 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.194 | Open / Ongoing Works | RM.03.318>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/03/2020 | 8 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.193 | Open / Ongoing Works | RM.03.316>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/03/2020 | 8 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.56 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/03/2020 | 9 | 20/03/2020 | 0 | 15 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F118318.192 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 18/03/2020 | 9 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90895.55 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/03/2020 | 9 | 8/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F110032.24 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 18/03/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F113721.21 | JPC Sign Off / Closed | 6th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 18/03/2020 | 11 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.362849 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 18/03/2020 | 11 | 20/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.751 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/03/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.362357 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 18/03/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F120172.55 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 18/03/2020 | 8 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.54 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 18/03/2020 | 8 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.53 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 18/03/2020 | 8 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.25 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 18/03/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.191 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 18/03/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F110032.25 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 23/03/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.224 | Open / Ongoing Works | RM.02.205>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.223 | Open / Ongoing Works | RM.02.203>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.221 | Open / Ongoing Works | RM.02.208>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.65 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 23/03/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.220 | Open / Ongoing Works | RM.02.210>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.64 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 23/03/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90895.63 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/03/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F118318.219 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 23/03/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.364853 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/03/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F118318.218 | Open / Ongoing Works | RM.02.214>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.217 | Open / Ongoing Works | RM.02.213>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.216 | Open / Ongoing Works | RM.02.212>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.215 | Open / Ongoing Works | RM.02.216>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.214 | Open / Ongoing Works | RM.02.217>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.213 | Open / Ongoing Works | RM.02.215>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.212 | Open / Ongoing Works | RM.02.218>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.211 | Open / Ongoing Works | RM.02.219>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.24 | JPC Sign Off / Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 20/03/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.364719 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 20/03/2020 | 11 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.364676 | 3rd Party Sign Off - Closed | 6th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 20/03/2020 | 13 | 28/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F113721.23 | JPC Sign Off / Closed | 6th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 20/03/2020 | 10 | 8/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.64 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/03/2020 | 9 | 27/03/2020 | 0 | 7 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F90895.62 | Closed | 1328 - Townsend St | EHS Inspection. | 20/03/2020 | 9 | 31/03/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.364453 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 20/03/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.210 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 20/03/2020 | 9 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F113721.22 | Closed JPC Sign Off | 6th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 20/03/2020 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F122196.48 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 25/03/2020 | 9 | 27/03/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F122196.47 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 25/03/2020 | 6 | 25/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.752 | 3rd Party Sign Off - Closed | 2nd to 3rd Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 25/03/2020 | 10 | 5/5/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F122196.46 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 25/03/2020 | 6 | 25/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F120172.64 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 25/03/2020 | 8 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.63 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 25/03/2020 | 8 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.62 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 25/03/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.366812 | JPC Inspected | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 25/03/2020 | 10 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F120172.52 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.51 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.50 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.49 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.48 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.47 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.46 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.45 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.44 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.43 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 16/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F122196.24 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 13/03/2020 | 6 | 18/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.23 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 13/03/2020 | 6 | 13/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.22 | Closed | Site Management>JPC Project Management | SM-FRM-006A Element Handover | 13/03/2020 | 6 | 18/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.21 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 13/03/2020 | 6 | 13/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.360150 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/03/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F122196.20 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 13/03/2020 | 6 | 13/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.19 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 13/03/2020 | 6 | 13/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.190 | Closed | 1328 - Townsend St | EHS Inspection. | 13/03/2020 | 9 | 31/03/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.360070 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 13/03/2020 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.233 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/03/2020 | 9 | 20/03/2020 | 0 | 11 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F118318.189 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 13/03/2020 | 9 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F118318.188 | Open / Ongoing Works | RM.03.309>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.187 | Open / Ongoing Works | RM.03.307>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.185 | Open / Ongoing Works | RM.03.305>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.184 | Open / Ongoing Works | RM.03.303>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.183 | Open / Ongoing Works | RM.03.301>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.182 | Open / Ongoing Works | RM.02.220>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.181 | Open / Ongoing Works | RM.02.221>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.180 | Open / Ongoing Works | RM.02.222>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.179 | Open / Ongoing Works | RM.02.223>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.178 | Open / Ongoing Works | RM.02.225>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.176 | Open / Ongoing Works | RM.02.224>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.175 | Open / Ongoing Works | RM.02.226>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.174 | Open / Ongoing Works | RM.02.227>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.359605 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 13/03/2020 | 11 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.359505 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-010 Free Issue Item Form | 13/03/2020 | 6 | 13/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F84104.750 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/03/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 3
F1.359240 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/3/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.359238 | Open / Ongoing Works | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 12/3/2020 | 13 | 12/3/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.359232 | 3rd Party Sign Off - Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 12/3/2020 | 13 | 18/08/2020 | 0 | 1 | parent | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 6
F118318.172 | Open / Ongoing Works | 1328 - Townsend St | QM-FRM-QC-008 Non Conformance Record (NCR) | 12/3/2020 | 10 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.171 | Closed | 1328 - Townsend St | CM-EHS-FRM-006 Site Welfare Inspection | 12/3/2020 | 9 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F122196.18 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/3/2020 | 9 | 20/03/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.359228 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 12/3/2020 | 13 | 28/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F118318.173 | Open / Ongoing Works | 1328 - Townsend St | QM-FRM-QC-008 Non Conformance Record (NCR) | 12/3/2020 | 10 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.170 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 12/3/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.749 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.358458 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/3/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F90895.51 | Open / Ongoing Works | Quality Management>JPC Project Management | QM-FRM-GEN-001 Non Conformance Record (NCR) | 11/3/2020 | 10 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F90895.50 | JPC Sign Off / Closed | Quality Management>JPC Project Management | QM-FRM-GEN-001 Non Conformance Record (NCR) | 11/3/2020 | 10 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.169 | Open / Ongoing Works | ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 11/3/2020 | 10 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.223 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/3/2020 | 9 | 20/03/2020 | 0 | 8 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F120172.42 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 11/3/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.41 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 11/3/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.40 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 11/3/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.39 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 11/3/2020 | 8 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.37 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 11/3/2020 | 8 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.168 | Open / Ongoing Works | RM.01.154>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.167 | Works Complete / Resolved | RM.01.156>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.166 | Works Complete / Resolved | RM.01.169>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.165 | Open / Ongoing Works | RM.01.171>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.164 | Open / Ongoing Works | RM.01.172>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.163 | Open / Ongoing Works | RM.01.170>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.162 | Open / Ongoing Works | RM.01.168>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.161 | Open / Ongoing Works | RM.01.166>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.160 | Open / Ongoing Works | RM.01.164>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.159 | Open / Ongoing Works | RM.01.162>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.158 | Open / Ongoing Works | RM.01.160>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.222 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 11/3/2020 | 10 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F122196.17 | Closed | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 11/3/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F122196.16 | Closed | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 11/3/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F122196.15 | Closed | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 11/3/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.157 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 11/3/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.748 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F110032.22 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 11/3/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.357441 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 10/3/2020 | 10 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.357431 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 10/3/2020 | 10 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.357414 | Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 10/3/2020 | 10 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F118318.156 | Open / Ongoing Works | RM.01.158>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 10/3/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.155 | Open / Ongoing Works | RM.02.229>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 10/3/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.219 | JPC Sign Off | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 10/3/2020 | 1 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.357329 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/3/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.357312 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/3/2020 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.357307 | Open / Ongoing Works | ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 10/3/2020 | 10 | 10/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Open | 4
F1.358789 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/3/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F110032.23 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/3/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.356999 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/3/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F1.356996 | Open / Ongoing Works | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 10/3/2020 | 10 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.356987 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/3/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 3
F110032.21 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/3/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.357238 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/3/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.747 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/3/2020 | 9 | 20/03/2020 | 0 | 10 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.745 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F118318.154 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 10/3/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.153 | Open / Ongoing Works | 1328 - Townsend St | QM-FRM-QC-008 Non Conformance Record (NCR) | 10/3/2020 | 10 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.152 | Open / Ongoing Works | RM.03.314>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 9/3/2020 | 8 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.151 | Open / Ongoing Works | RM.03.312>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 9/3/2020 | 8 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.150 | Open / Ongoing Works | RM.03.310>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 9/3/2020 | 8 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.40 | JPC Sign Off / Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 9/3/2020 | 11 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.149 | Open / Ongoing Works | RM.03.308>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 9/3/2020 | 8 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.148 | JPC Sign Off / Closed | RM.03.302>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 9/3/2020 | 8 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.356152 | JPC Sign Off / Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 9/3/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F110032.20 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 9/3/2020 | 11 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90895.43 | JPC Sign Off / Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 9/3/2020 | 11 | 8/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.744 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/3/2020 | 9 | 10/3/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.355773 | 3rd Party Sign Off - Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 9/3/2020 | 13 | 18/08/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F120172.36 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 9/3/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.35 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 9/3/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F110032.19 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 9/3/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.146 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 9/3/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.743 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.355640 | JPC Sign Off / Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 9/3/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.738 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F107663.53 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 7/3/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F122196.11 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 6/3/2020 | 6 | 18/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.10 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 6/3/2020 | 6 | 12/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.9 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 6/3/2020 | 6 | 12/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.355343 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/3/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 3
F1.355342 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/3/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.355283 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/3/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F110032.17 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 6/3/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.736 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F118318.145 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 6/3/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.8 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/3/2020 | 9 | 7/3/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F108023.77 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 5/3/2020 | 8 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.144 | Open / Ongoing Works | RM.01.148>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 5/3/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.143 | Open / Ongoing Works | RM.01.146>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 5/3/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.142 | Open / Ongoing Works | RM.01.144>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 5/3/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.141 | Open / Ongoing Works | RM.01.142>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 5/3/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.140 | Open / Ongoing Works | RM.01.140>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 5/3/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.201 | Closed | 1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 5/3/2020 | 10 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.200 | Closed | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 5/3/2020 | 10 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F118318.139 | Open / Ongoing Works | RM.01.138>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 5/3/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.199 | Closed | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 5/3/2020 | 10 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.198 | Closed | 2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 5/3/2020 | 10 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.196 | Closed | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 5/3/2020 | 10 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.195 | Closed | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 5/3/2020 | 10 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F120172.34 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 6/3/2020 | 8 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.33 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 6/3/2020 | 8 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.32 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 6/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.31 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 6/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.30 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 6/3/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.29 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 6/3/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.27 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 6/3/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.737 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/3/2020 | 9 | 12/3/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F116412.205 | Closed | 1328 - Townsend St | EHS Inspection. | 6/3/2020 | 9 | 31/03/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.136 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/3/2020 | 6 | 6/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.735 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F118318.135 | Open / Ongoing Works | RM.03.306>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 4/3/2020 | 8 | 4/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.134 | Open / Ongoing Works | RM.03.304>Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 4/3/2020 | 8 | 4/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.191 | Closed | R.01.235 - Stair Core 1>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 4/3/2020 | 10 | 4/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.353176 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 4/3/2020 | 11 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.352420 | 3rd Party Sign Off - Closed | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/3/2020 | 13 | 28/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.352417 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/3/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.352414 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/3/2020 | 13 | 28/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.352295 | Closed | 1328 - Townsend St | SM-FRM-010 Free Issue Item Form | 3/3/2020 | 6 | 6/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.733 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/3/2020 | 9 | 4/3/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90895.32 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 3/3/2020 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F120172.25 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 3/3/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.24 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 3/3/2020 | 8 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.732 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F118318.131 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/3/2020 | 6 | 6/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.351792 | Open / Ongoing Works | Items to be Deleted | QM-CL-CS-114 Blockwork / Brickwork Inspection | 3/3/2020 | 11 | 3/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.351778 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/3/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 3
F1.351774 | Notification | 1328 - Townsend St | BCAR Inspection Form | 3/3/2020 | 3 | 3/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.351631 | Open / Ongoing Works | Items to be Deleted | QM-FRM-QC-001 Benchmark / Sample Form | 2/3/2020 | 10 | 2/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.351630 | In Process / Manufactor | Items to be Deleted | QM-FRM-QC-002 Off Site Inspection | 2/3/2020 | 10 | 2/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.351629 | Open / Ongoing Works | Items to be Deleted | QM-FRM-QC-003 Protection of Finishes Inspection | 2/3/2020 | 10 | 2/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.351626 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-CS-114 Blockwork / Brickwork Inspection | 2/3/2020 | 11 | 2/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.351605 | JPC Inspected | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 2/3/2020 | 10 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 4
F110032.16 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 2/3/2020 | 11 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.133 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/3/2020 | 9 | 7/3/2020 | 0 | 26 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F90895.31 | Completed and signed off | General Site Plan>JPC Project Management | EHS Managment Inspection - Daily | 2/3/2020 | 9 | 4/3/2020 | 0 | 12 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F1.351221 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/3/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F1.351197 | Open / Ongoing Works | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/3/2020 | 10 | 2/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.351144 | Open / Ongoing Works | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 2/3/2020 | 13 | 2/3/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F110032.15 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 2/3/2020 | 11 | 3/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.129 | Open / Ongoing Works | RM.02.267>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.128 | Open / Ongoing Works | RM.02.265>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.127 | Open / Ongoing Works | RM.02.266>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.126 | Open / Ongoing Works | RM.02.268>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.125 | Open / Ongoing Works | RM.02.270>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.124 | Open / Ongoing Works | RM.02.272>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.123 | Open / Ongoing Works | RM.02.273>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.122 | Open / Ongoing Works | RM.02.274>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.132 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 4/3/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.734 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.352804 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/3/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.368302 | Closed JPC Sign Off | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/03/2020 | 11 | 21/05/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.356433 | Closed JPC Sign Off | 1328 - Townsend St | 1328 QM-CL-CS-116 Concrete Cube Record | 9/3/2020 | 11 | 9/3/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F107663.59 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/03/2020 | 11 | 17/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.60 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/03/2020 | 11 | 17/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.61 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/03/2020 | 11 | 17/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.62 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/03/2020 | 11 | 17/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.63 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/03/2020 | 11 | 17/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.54 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/3/2020 | 11 | 7/3/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F107663.55 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/03/2020 | 11 | 16/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.56 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/03/2020 | 11 | 16/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.57 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/03/2020 | 11 | 17/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.58 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/03/2020 | 11 | 17/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.33 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/03/2020 | 11 | 27/03/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F113721.34 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/03/2020 | 11 | 27/03/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.766 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.35 | Closed JPC Sign Off | 6th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/03/2020 | 11 | 27/03/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F113721.36 | Closed JPC Sign Off | 6th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/03/2020 | 11 | 27/03/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.739 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/3/2020 | 11 | 7/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.740 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/3/2020 | 11 | 7/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.741 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/3/2020 | 11 | 7/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.742 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/3/2020 | 11 | 7/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.753 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/03/2020 | 11 | 25/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.754 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/03/2020 | 11 | 25/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.755 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/03/2020 | 11 | 25/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.756 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/03/2020 | 11 | 25/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.757 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/03/2020 | 11 | 25/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.765 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/03/2020 | 11 | 27/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.767 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.768 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.769 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.770 | Closed JPC Sign Off | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.771 | Closed JPC Sign Off | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.772 | Closed JPC Sign Off | Ground Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.773 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.774 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.775 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.776 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.777 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.778 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/4/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.779 | Closed JPC Sign Off | 1st Floor Plan>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/05/2020 | 11 | 27/05/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.787 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.34 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 4/3/2020 | 11 | 4/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.35 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 4/3/2020 | 11 | 4/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.36 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 4/3/2020 | 11 | 4/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.44 | Closed JPC Sign Off | 5th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 9/3/2020 | 11 | 30/03/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F90895.45 | Closed JPC Sign Off | 5th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 9/3/2020 | 11 | 30/03/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F90895.47 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 9/3/2020 | 11 | 30/03/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F90895.48 | Closed JPC Sign Off | 7th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 9/3/2020 | 11 | 30/03/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F116412.206 | Closed | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 6/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.137 | Open / Ongoing Works | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 5/3/2020 | 10 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.260 | Closed | Area 2>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.187 | Open / Ongoing Works | 3rd to 4th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 2/3/2020 | 8 | 2/3/2020 | 1 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.203 | Open / Ongoing Works | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 6/3/2020 | 10 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.215 | Closed | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/3/2020 | 10 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90895.38 | Open / Ongoing Works | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/3/2020 | 10 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.220 | Open / Ongoing Works | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/3/2020 | 10 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.37 | Open / Ongoing Works | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 4/3/2020 | 10 | 4/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.202 | Open / Ongoing Works | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 6/3/2020 | 10 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.189 | Open / Ongoing Works | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 4/3/2020 | 10 | 4/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.227 | Closed | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.221 | Open / Ongoing Works | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/3/2020 | 10 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.225 | Open / Ongoing Works | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/3/2020 | 10 | 12/3/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.204 | Closed | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 6/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.356205 | Open / Ongoing Works | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 9/3/2020 | 8 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.216 | Closed | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.49 | Open / Ongoing Works | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/3/2020 | 10 | 10/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.194 | Closed | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 5/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F116412.238 | Open / Ongoing Works | 3rd to 4th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 6/4/2020 | 10 | 6/4/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.236 | Open / Ongoing Works | 3rd to 4th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 6/4/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.265 | Closed | 3rd to 4th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/6/2020 | 10 | 10/9/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.237 | Open / Ongoing Works | 3rd to 4th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 6/4/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F113721.29 | Open / Ongoing Works | 3rd to 4th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 25/03/2020 | 10 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.188 | Open / Ongoing Works | 4th to 5th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 3/3/2020 | 8 | 3/3/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.239 | Open / Ongoing Works | 4th to 5th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 6/4/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.193 | Closed | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 5/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F90895.39 | Open / Ongoing Works | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/3/2020 | 10 | 9/3/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.228 | Open / Ongoing Works | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/3/2020 | 10 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.192 | Closed | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 5/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.190 | Closed | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 4/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.25 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 23/03/2020 | 10 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.226 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/3/2020 | 10 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.54 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/03/2020 | 10 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.42 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/3/2020 | 10 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.266 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/6/2020 | 10 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F116412.217 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 10/3/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F113721.27 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/03/2020 | 10 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.230 | Open / Ongoing Works | 1st to 2nd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/3/2020 | 10 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.229 | Open / Ongoing Works | 1st to 2nd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 12/3/2020 | 8 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.231 | Open / Ongoing Works | 1st to 2nd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/3/2020 | 10 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.212 | Closed | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/3/2020 | 10 | 9/9/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.247 | Open / Ongoing Works | 1st to 2nd Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 28/05/2020 | 10 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F116412.214 | Open / Ongoing Works | 2nd to 3rd Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/3/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F116412.248 | Open / Ongoing Works | 3rd to 4th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 28/05/2020 | 10 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F116412.249 | Open / Ongoing Works | 4th to 5th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 28/05/2020 | 10 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F116412.255 | Closed | 1st to 2nd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 29/05/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F116412.256 | Closed | 1st to 2nd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 29/05/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F116412.251 | Open / Ongoing Works | 2nd to 3rd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 29/05/2020 | 10 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F116412.252 | Closed | 2nd to 3rd Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 29/05/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.213 | Closed | 3rd to 4th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/3/2020 | 10 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.257 | Closed | 3rd to 4th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 29/05/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F116412.253 | Open / Ongoing Works | 4th to 5th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 29/05/2020 | 10 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F116412.254 | Open / Ongoing Works | 4th to 5th Floor>6. Townsend Street (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 29/05/2020 | 10 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.42 | Open / Ongoing Works | 1st to 2nd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.40 | Open / Ongoing Works | 1st to 2nd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.37 | Open / Ongoing Works | 1st to 2nd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.41 | Open / Ongoing Works | 1st to 2nd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.38 | Open / Ongoing Works | 1st to 2nd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.48 | Open / Ongoing Works | 2nd to 3rd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.46 | Open / Ongoing Works | 2nd to 3rd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.43 | Open / Ongoing Works | 2nd to 3rd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.47 | Open / Ongoing Works | 2nd to 3rd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.45 | Open / Ongoing Works | 2nd to 3rd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.44 | Open / Ongoing Works | 2nd to 3rd Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.55 | Open / Ongoing Works | 3rd to 4th Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.53 | Open / Ongoing Works | 3rd to 4th Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.49 | Open / Ongoing Works | 3rd to 4th Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.54 | Open / Ongoing Works | 3rd to 4th Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.52 | Open / Ongoing Works | 3rd to 4th Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.50 | Open / Ongoing Works | 3rd to 4th Floor>8. Townsend Street (North Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.61 | Open / Ongoing Works | 1st to 2nd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.58 | Open / Ongoing Works | 1st to 2nd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F113721.60 | Open / Ongoing Works | 1st to 2nd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F113721.59 | Open / Ongoing Works | 1st to 2nd Floor>7. Coutyard (South Elevation)>Elevations>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/04/2020 | 10 | 27/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.370033 | Open / Ongoing Works | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/4/2020 | 10 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F116412.207 | Closed | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/3/2020 | 10 | 9/9/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F1.364288 | Open / Ongoing Works | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.357048 | Closed JPC Sign Off | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 10/3/2020 | 11 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.224 | Closed | Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/3/2020 | 10 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.208 | Closed | Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/3/2020 | 10 | 9/9/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F116412.210 | Closed | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.263 | Closed | Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.370138 | Open / Ongoing Works | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 1/4/2020 | 10 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.262 | Open / Ongoing Works | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/6/2020 | 10 | 3/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.211 | Closed | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 9/3/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F116412.261 | Closed | Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.232 | Closed | Area 1>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/03/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F116412.264 | Closed | Area 3>3rd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 3/6/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.184 | 3rd Party Sign Off - Closed | RM.01.109>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 27/02/2020 | 1 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.107 | Open / Ongoing Works | RM.01.136>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.106 | Open / Ongoing Works | RM.01.134>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.105 | Open / Ongoing Works | RM.01.132>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F107663.52 | JPC Sign Off / Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 27/02/2020 | 11 | 18/03/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.104 | Open / Ongoing Works | RM.01.130>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.103 | Open / Ongoing Works | RM.01.101>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.102 | Open / Ongoing Works | RM.01.104>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.101 | Open / Ongoing Works | RM.01.104>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.100 | Open / Ongoing Works | RM.01.105>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.99 | Open / Ongoing Works | RM.01.107>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.98 | Open / Ongoing Works | RM.01.103>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.183 | Closed | RM.02.335 - Corridor>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/02/2020 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.97 | Open / Ongoing Works | RM.01.113>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.96 | Open / Ongoing Works | RM.01.112>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.95 | Open / Ongoing Works | RM.01.106>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.94 | Open / Ongoing Works | RM.01.110>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.93 | Open / Ongoing Works | RM.01.111>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.92 | Open / Ongoing Works | RM.01.109>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.91 | Open / Ongoing Works | RM.01.108>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.23 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 27/02/2020 | 8 | 4/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.22 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 27/02/2020 | 8 | 4/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.21 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 27/02/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.20 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 27/02/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F110032.12 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 27/02/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.89 | Open / Ongoing Works | ITP 04 M&E Services>QC & BC(A)R | QM-FRM-MEP-405 Mechanical Inspection Report | 27/02/2020 | 1 | 27/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F84104.726 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F118318.88 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 27/02/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.348825 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F118318.87 | Opened | 1328 - Townsend St | EHS Managment Inspection - Daily | 26/02/2020 | 9 | 26/02/2020 | 1 | 15 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F84104.725 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F118318.86 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 26/02/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.347693 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F116412.182 | 3rd Party Sign Off - Closed | R.00.120 Reception Area>Common Areas>Ground Floor Plan>Block 1>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 25/02/2020 | 8 | 8/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F118318.121 | Open / Ongoing Works | RM.02.276>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.120 | Open / Ongoing Works | RM.02.275>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 2/3/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.186 | 3rd Party Sign Off - Closed | 3rd to 4th Floor>5. Moss Street (East Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 2/3/2020 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.731 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/3/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F118318.119 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 2/3/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.7 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 28/02/2020 | 6 | 4/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.6 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 28/02/2020 | 6 | 4/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F122196.5 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 28/02/2020 | 6 | 4/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F90895.30 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/02/2020 | 9 | 4/3/2020 | 0 | 15 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F122196.2 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 28/02/2020 | 6 | 28/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F122196.1 | Closed | Site Management>JPC Project Management | SM-FRM-006A Element Handover | 28/02/2020 | 6 | 4/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F110032.14 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/02/2020 | 11 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.185 | Closed JPC Reviewed | QC & BC(A)R | QM-FRM-QC005 - Training Record | 28/02/2020 | 10 | 28/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F82131.8 | 3rd Party Sign Off - Closed | R.00.105 Retail Space>Common Areas>Ground Floor Plan>Block 2>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 28/02/2020 | 13 | 26/06/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 6
F1.350081 | 3rd Party Sign Off - Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 28/02/2020 | 13 | 18/08/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F110032.13 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/02/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118318.117 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 28/02/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.730 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 28/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.349878 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 28/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.349670 | Closed | Audits & Assessments>Quality Management>JPC Project Management | JPC-QA-RP-003 - Site Audit Report | 27/02/2020 | 2 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.729 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/02/2020 | 9 | 4/3/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.116 | Open / Ongoing Works | RM.02.262>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.115 | Open / Ongoing Works | RM.02.260>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.114 | Open / Ongoing Works | RM.02.258>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.113 | Open / Ongoing Works | RM.02.256>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.28 | Closed | 1328 - Townsend St | EHS Inspection. | 27/02/2020 | 9 | 31/03/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.112 | Open / Ongoing Works | RM.02.254>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.111 | Open / Ongoing Works | RM.02.252>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.110 | Open / Ongoing Works | RM.02.250>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.109 | Open / Ongoing Works | RM.02.254>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.84 | Open / Ongoing Works | RM.02.252>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.83 | Open / Ongoing Works | RM.02.250>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.82 | Open / Ongoing Works | RM.02.248>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F90896.132 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/02/2020 | 9 | 26/02/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.81 | Open / Ongoing Works | RM.02.246>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.80 | Open / Ongoing Works | RM.02.244>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.79 | Open / Ongoing Works | RM.02.242>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.78 | Open / Ongoing Works | RM.02.240>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.77 | Open / Ongoing Works | RM.02.238>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.76 | Open / Ongoing Works | RM.02.236>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.75 | Open / Ongoing Works | RM.02.234>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.347477 | Test Results Required | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 25/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F120172.14 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 24/02/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.73 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/02/2020 | 9 | 4/3/2020 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F120172.13 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 24/02/2020 | 8 | 28/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.12 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 24/02/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.346579 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.722 | Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.720 | Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.719 | Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.718 | Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.717 | Closed | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.715 | Closed | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.714 | Closed | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F118318.72 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 24/02/2020 | 6 | 28/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F116412.175 | Open / Ongoing Works | ITP 04 M&E Services>QC & BC(A)R | QM-FRM-BCAR-300 Electrical BCAR Inspection | 24/02/2020 | 13 | 24/02/2020 | 1 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 6
F84104.713 | Closed JPC Sign Off | 5th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 24/02/2020 | 11 | 2/4/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.712 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.346115 | 3rd Party Sign Off - Closed | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 24/02/2020 | 13 | 28/04/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.346108 | 3rd Party Sign Off - Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 24/02/2020 | 13 | 19/08/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.346097 | JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 24/02/2020 | 13 | 8/9/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F118318.69 | Completed and signed off | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1328 CM-SM-FRM-001 Site Diary | 22/02/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.724 | Open / Ongoing Works | Quality Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 25/02/2020 | 10 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.723 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F110032.11 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/02/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.346806 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 24/02/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.346777 | Test Results Required | 02 Foul>02 Drainage>ITP 03 External Works>QC & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.346759 | 3rd Party Sign Off - Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 24/02/2020 | 13 | 28/04/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.346742 | Test Results Required | 02 Foul>02 Drainage>ITP 03 External Works>QC & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.20 | Test Results Required | 01 Storm water>02 Drainage>ITP 03 External Works>QC & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 24/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F107663.51 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/02/2020 | 9 | 4/3/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.345574 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.710 | Closed | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 21/02/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.709 | Closed | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 21/02/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.708 | Closed | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 21/02/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.707 | Closed | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 21/02/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.174 | Closed | 1328 - Townsend St | EHS Inspection. | 21/02/2020 | 9 | 26/02/2020 | 0 | 11 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F116412.173 | Closed JPC Reviewed | QC Training Records>Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 21/02/2020 | 10 | 21/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F120172.11 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/02/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.10 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/02/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.9 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.8 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.66 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/02/2020 | 6 | 6/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.706 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.716 | Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 20/02/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F113721.16 | JPC Inspected | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 20/02/2020 | 10 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F76201.715 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.714 | Closed | 5th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 20/02/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.704 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/02/2020 | 9 | 4/3/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.713 | Closed | 5th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 20/02/2020 | 11 | 2/4/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.165 | 3rd Party Sign Off - Closed | RM.01.116>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 20/02/2020 | 1 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.65 | Open / Ongoing Works | RM.02.230>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 20/02/2020 | 8 | 20/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.64 | Open / Ongoing Works | RM.02.232>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 20/02/2020 | 8 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F76201.710 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 20/02/2020 | 6 | 28/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.63 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 20/02/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.702 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.343756 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/02/2020 | 6 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F84104.700 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 19/02/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.709 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 19/02/2020 | 6 | 28/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.708 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 19/02/2020 | 6 | 28/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.343640 | 3rd Party Sign Off - Closed | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 19/02/2020 | 13 | 28/04/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F76201.707 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/02/2020 | 9 | 26/02/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.706 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 19/02/2020 | 6 | 20/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.696 | Closed | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 19/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.343145 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F118318.62 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 19/02/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.695 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F116412.164 | Closed JPC Reviewed | ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 19/02/2020 | 10 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.342908 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 18/02/2020 | 6 | 18/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.703 | JPC Sign Off / Closed | 4th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 18/02/2020 | 11 | 11/3/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.702 | JPC Sign Off / Closed | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 18/02/2020 | 11 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.701 | JPC Sign Off / Closed | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 18/02/2020 | 11 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.700 | Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 18/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.699 | Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 18/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.698 | Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 18/02/2020 | 11 | 8/9/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.61 | Open / Ongoing Works | RM.02.210>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/02/2020 | 8 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.60 | Open / Ongoing Works | RM.02.208>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/02/2020 | 8 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.59 | Open / Ongoing Works | RM.02.206>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/02/2020 | 8 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.58 | Open / Ongoing Works | RM.02.204>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/02/2020 | 8 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.57 | Open / Ongoing Works | RM.02.202>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 18/02/2020 | 8 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.144 | JPC Sign Off / Closed | RM.01.104>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.143 | JPC Sign Off / Closed | R.01.230 - Laundry>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.142 | JPC Sign Off / Closed | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.141 | JPC Sign Off / Closed | RM.01.112>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.140 | JPC Sign Off / Closed | RM.01.110>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.139 | JPC Sign Off / Closed | RM.01.113>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.138 | JPC Sign Off / Closed | RM.01.113>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.137 | JPC Sign Off / Closed | RM.01.111>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.136 | JPC Sign Off / Closed | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.135 | JPC Sign Off / Closed | RM.01.109>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.134 | JPC Sign Off / Closed | RM.01.109>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.133 | JPC Sign Off / Closed | RM.01.107>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.132 | JPC Sign Off / Closed | RM.01.105>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.131 | JPC Sign Off / Closed | RM.01.103>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.130 | JPC Sign Off / Closed | RM.01.103>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.129 | JPC Sign Off / Closed | R.01.226 - Plant Room>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.128 | JPC Sign Off / Closed | RM.01.101>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.127 | JPC Sign Off / Closed | RM.01.101>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.689 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F118318.56 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/02/2020 | 6 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.342161 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F107663.48 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 17/02/2020 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.47 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 17/02/2020 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.46 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 17/02/2020 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.45 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 17/02/2020 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.688 | Opened | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 17/02/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F84104.687 | Opened | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 17/02/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F118318.54 | Open / Ongoing Works | Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.50 | Open / Ongoing Works | RM.01.172>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.48 | Open / Ongoing Works | RM.01.119>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F118318.47 | Open / Ongoing Works | RM.02.212>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.46 | Open / Ongoing Works | RM.02.214>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.45 | Open / Ongoing Works | RM.02.216>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.44 | Open / Ongoing Works | RM.02.218>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.341952 | Closed | 1328 - Townsend St | JPC-HR-FRM-001 - Training Record | 17/02/2020 | 2 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.43 | Open / Ongoing Works | RM.02.220>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.42 | Open / Ongoing Works | RM.02.222>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.41 | Open / Ongoing Works | RM.02.224>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 17/02/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.341649 | Open / Ongoing Works | Ground Floor Plan>Block 2>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 17/02/2020 | 13 | 17/02/2020 | 1 | 4 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 6
F116412.119 | Closed JPC Sign Off | RM.04.534 - Corridor>Common Areas>4th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 17/02/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.682 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F107663.44 | JPC Sign Off / Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 16/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.43 | Closed JPC Sign Off | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 14/02/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.341063 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F116412.118 | JPC Sign Off / Closed | 5th Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 14/02/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F118318.40 | Open / Ongoing Works | RM.02.201>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.39 | Open / Ongoing Works | RM.02.203>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.38 | Open / Ongoing Works | RM.02.205>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.37 | Open / Ongoing Works | RM.02.207>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.36 | Open / Ongoing Works | RM.02.209>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.35 | Open / Ongoing Works | RM.02.211>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.34 | Open / Ongoing Works | RM.02.213>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.33 | Open / Ongoing Works | RM.02.215>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.32 | Open / Ongoing Works | RM.02.217>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.681 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/02/2020 | 9 | 26/02/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F118318.31 | Open / Ongoing Works | RM.02.226>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F90895.19 | Closed | 1328 - Townsend St | EHS Inspection. | 14/02/2020 | 9 | 31/03/2020 | 0 | 14 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F118318.30 | Open / Ongoing Works | RM.02.219>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.29 | Open / Ongoing Works | RM.02.221>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.28 | Open / Ongoing Works | RM.02.223>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.27 | Open / Ongoing Works | RM.02.225>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.26 | Open / Ongoing Works | RM.02.227>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 14/02/2020 | 8 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.4 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 14/02/2020 | 8 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.3 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 14/02/2020 | 8 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F76201.688 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 14/02/2020 | 6 | 19/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.675 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.687 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 13/02/2020 | 6 | 14/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F1.340101 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/02/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.340038 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 13/02/2020 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.686 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 13/02/2020 | 6 | 13/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.683 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 13/02/2020 | 6 | 13/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.674 | JPC Inspected | 1st Floor Plan>Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 13/02/2020 | 10 | 8/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.107 | 3rd Party Sign Off - Closed | R.01.225 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 13/02/2020 | 1 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F110032.10 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 13/02/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F110032.9 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 13/02/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.679 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 13/02/2020 | 6 | 14/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F116412.106 | Closed | R.01.225 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 13/02/2020 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F120172.2 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 13/02/2020 | 8 | 19/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F120172.1 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 13/02/2020 | 8 | 19/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.23 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/02/2020 | 6 | 6/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.678 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.671 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 13/02/2020 | 9 | 4/3/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.338824 | Closed | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 12/2/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.338799 | Open / Ongoing Works | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 12/2/2020 | 10 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Open | 4
F116412.105 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/2/2020 | 9 | 14/02/2020 | 0 | 12 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F110032.8 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/2/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.665 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/2/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.338355 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/2/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F84104.664 | JPC Sign Off / Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 12/2/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.22 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 12/2/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.663 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/2/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.676 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/2/2020 | 11 | 25/02/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.21 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 11/2/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.337999 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/2/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F116412.104 | Closed | RM.02.202>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.103 | Closed | RM.02.204>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.102 | Closed | RM.02.206>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.101 | Closed | RM.02.208>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.100 | Closed | RM.02.210>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.98 | Closed | RM.02.220>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.97 | Closed | RM.02.222>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.96 | Closed | RM.02.224>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.95 | Closed | RM.02.226>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.94 | Closed | RM.02.229>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.93 | Closed | RM.02.227>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.92 | Closed | RM.02.225>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.91 | Closed | RM.02.223>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.90 | Closed | RM.02.221>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.89 | Closed | RM.02.219>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.88 | Closed | RM.02.217>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.87 | Closed | RM.02.215>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.86 | Closed | RM.02.213>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.84 | Closed | RM.02.211>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.83 | Closed | RM.02.209>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.82 | Closed | RM.02.207>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.81 | Closed | RM.02.205>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.79 | Closed | RM.02.203>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.78 | Closed | RM.02.201>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.77 | Closed | RM.01.171>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.76 | Closed | RM.01.169>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.75 | Closed | R.01.241 - Office>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.74 | Closed | RM.01.163>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.73 | Closed | RM.01.161>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.72 | Closed | RM.01.159>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.69 | Closed | R.01.209 - Room>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.68 | Closed | R.01.230 - Laundry>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.67 | Closed | R.01.230 - Laundry>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.66 | Closed | RM.01.104>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.65 | Closed | RM.01.106>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.64 | Closed | RM.01.108>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.63 | Closed | RM.01.113>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.62 | Closed | RM.01.111>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.61 | Closed | RM.01.109>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.60 | Closed | RM.01.107>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.59 | Closed | RM.01.105>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.58 | Closed | RM.01.103>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.57 | Closed | RM.01.101>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.674 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/2/2020 | 9 | 14/02/2020 | 0 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F116412.55 | Closed | R.01.226 - Plant Room>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.54 | Closed | R.01.226 - Plant Room>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.662 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/2/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.337046 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/2/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F76201.671 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/2/2020 | 9 | 14/02/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.670 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 10/2/2020 | 6 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.667 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 10/2/2020 | 6 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.666 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 10/2/2020 | 6 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F116412.49 | Closed | 2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 10/2/2020 | 10 | 10/2/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.336527 | Closed | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 10/2/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.336475 | JPC Inspected | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 10/2/2020 | 10 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F110032.7 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/2/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.661 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/2/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.336232 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/2/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F107663.42 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/2/2020 | 9 | 14/02/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F107663.41 | Closed JPC Sign Off | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 7/2/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.47 | 3rd Party Sign Off - Closed | R.01.225 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 7/2/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.46 | Closed | 2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/2/2020 | 10 | 7/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F110032.6 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 7/2/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.659 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/2/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.664 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 6/2/2020 | 6 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F90896.131 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/2/2020 | 9 | 14/02/2020 | 0 | 8 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F118318.20 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 6/2/2020 | 9 | 14/02/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.658 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 6/2/2020 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F110032.4 | Closed JPC Sign Off | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 6/2/2020 | 11 | 20/02/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.18 | Closed | 1328 - Townsend St | EHS Inspection. | 6/2/2020 | 9 | 14/02/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.658 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/2/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.657 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 5/2/2020 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.656 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 5/2/2020 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F116412.157 | JPC Sign Off / Closed | RM.01.163>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 5/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F116412.156 | Closed | Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.155 | JPC Sign Off / Closed | RM.01.161>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.154 | Closed | 1328 - Townsend St | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.153 | JPC Sign Off / Closed | RM.01.159>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.152 | JPC Sign Off / Closed | RM.01.145>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.150 | Closed | RM.01.143>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.148 | JPC Sign Off / Closed | R.01.209 - Room>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | 1305-QM-CL-ARC-Structural Framing System (SFS) Inspection | 18/02/2020 | 8 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.147 | Closed | R.01.209 - Room>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.146 | Closed | R.01.230 - Laundry>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.160 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/02/2020 | 9 | 4/3/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F120172.7 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 18/02/2020 | 8 | 24/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.6 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 18/02/2020 | 8 | 24/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F120172.5 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 18/02/2020 | 8 | 21/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90896.130 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/2/2020 | 9 | 14/02/2020 | 0 | 24 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F116412.45 | Closed | 1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-004 QC Observation Report | 5/2/2020 | 10 | 9/9/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F77029.48 | Closed | JPC Project Management | JPC-HR-FRM-001 - Training Record | 5/2/2020 | 2 | 5/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F116412.44 | 3rd Party Sign Off - Closed | RM.01.118>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 5/2/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F118994.1 | Open / Ongoing Works | Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-SUB-100 Subcontractor Inspection Report | 5/2/2020 | 12 | 5/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F76201.655 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 5/2/2020 | 6 | 5/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F116412.43 | 3rd Party Sign Off - Closed | RM.02.205>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 5/2/2020 | 8 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F107663.40 | JPC Sign Off / Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 5/2/2020 | 11 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.657 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/2/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.333469 | Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 5/2/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.334263 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/2/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.333307 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/2/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F117841.6 | Open / Ongoing Works | 4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-900 Design Team Inspection (Non BC(A)R) | 31/01/2020 | 13 | 31/01/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 6
F76201.646 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 31/01/2020 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F82131.6 | Notification | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | BCAR Inspection Form | 31/01/2020 | 3 | 31/01/2020 | 1 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.642 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 31/01/2020 | 6 | 4/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F117841.4 | Rejected / Action Required | 4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 31/01/2020 | 13 | 26/06/2020 | 1 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 6
F76201.641 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 31/01/2020 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F1.330748 | 3rd Party Sign Off - Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 31/01/2020 | 13 | 18/08/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.330742 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 31/01/2020 | 13 | 18/08/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.330738 | 3rd Party Sign Off - Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 31/01/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.330736 | 3rd Party Sign Off - Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 31/01/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.330731 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 31/01/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.330723 | Open / Ongoing Works | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 31/01/2020 | 13 | 5/2/2020 | 1 | 6 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F76201.639 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.330486 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F76201.636 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 30/01/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.635 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 30/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.649 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 30/01/2020 | 9 | 6/2/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F116412.36 | Closed JPC Reviewed | 1328 - Townsend St | QM-FRM-QC-002 Off Site Inspection | 30/01/2020 | 10 | 30/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.35 | In Process / Manufactor | Items to be Deleted | QM-FRM-QC-002 Off Site Inspection | 30/01/2020 | 10 | 30/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.329458 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 29/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F117743.8 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/01/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F117743.7 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/01/2020 | 8 | 5/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F117743.6 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/01/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F117743.5 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/01/2020 | 8 | 3/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F117743.4 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/01/2020 | 8 | 3/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F117743.3 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/01/2020 | 8 | 3/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F117743.2 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/01/2020 | 8 | 3/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F117743.1 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 29/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.647 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 29/01/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F116412.33 | Open / Ongoing Works | RM.01.146>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.32 | Open / Ongoing Works | RM.01.146>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.31 | Open / Ongoing Works | RM.01.144>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.30 | Open / Ongoing Works | RM.01.142>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.29 | Open / Ongoing Works | RM.01.140>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90896.129 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 29/01/2020 | 9 | 6/2/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F116412.28 | Open / Ongoing Works | RM.01.138>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.27 | Open / Ongoing Works | RM.01.136>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.26 | Open / Ongoing Works | RM.01.134>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.25 | Open / Ongoing Works | RM.01.132>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.24 | Open / Ongoing Works | RM.01.130>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.23 | Open / Ongoing Works | RM.01.128>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.22 | Open / Ongoing Works | RM.01.126>Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 29/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.329018 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 29/01/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.634 | Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 29/01/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.21 | JPC Sign Off / Closed | R.01.224 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 29/01/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.20 | JPC Sign Off / Closed | 2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-004 QC Observation Report | 29/01/2020 | 10 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.633 | Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 29/01/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.646 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 29/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.333271 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/2/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.18 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.17 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.16 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.15 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.14 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F76201.650 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/2/2020 | 6 | 5/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.649 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/2/2020 | 6 | 5/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.648 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/2/2020 | 6 | 4/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F118318.13 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.12 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F76201.647 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 4/2/2020 | 6 | 5/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F118318.11 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.10 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.9 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.8 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.7 | Open / Ongoing Works | RM.01.158>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.6 | Open / Ongoing Works | RM.01.156>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.5 | Open / Ongoing Works | RM.01.154>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.4 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F110032.3 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 4/2/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.655 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/2/2020 | 9 | 4/3/2020 | 0 | 15 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F116412.42 | Open / Ongoing Works | JPC Project Management | QM-CL-ARC-221 Bathroom POD Inspection | 4/2/2020 | 8 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.654 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/2/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.653 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 3/2/2020 | 11 | 25/02/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.41 | 3rd Party Sign Off - Closed | R.01.225 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 3/2/2020 | 1 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F1.331585 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 3/2/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.651 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/2/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.331186 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F84104.650 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 31/01/2020 | 11 | 26/02/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F118318.3 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-221 Bathroom POD Inspection | 31/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F118318.2 | Open / Ongoing Works | RM.01.152>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 31/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F118318.1 | Open / Ongoing Works | RM.01.150>Area 3>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 31/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.14 | Closed | 1328 - Townsend St | EHS Inspection. | 31/01/2020 | 9 | 6/2/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.328601 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 28/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F1.328600 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | QS Site Review | 28/01/2020 | 6 | 28/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F116412.18 | JPC Sign Off / Closed | RM.01.103>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/01/2020 | 8 | 6/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.328567 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/01/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F116412.17 | Open / Ongoing Works | RM.01.105>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.16 | Open / Ongoing Works | RM.01.107>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.15 | Open / Ongoing Works | RM.01.109>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.14 | Open / Ongoing Works | RM.01.106>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.13 | Open / Ongoing Works | RM.01.104>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.12 | Open / Ongoing Works | RM.01.104>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 28/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F84104.642 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 28/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.641 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/01/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.639 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/01/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.629 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 28/01/2020 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.628 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 28/01/2020 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.627 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 28/01/2020 | 6 | 28/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.638 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/01/2020 | 9 | 6/2/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F108023.76 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 28/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F116412.9 | In Process / Manufactor | Items to be Deleted | QM-FRM-QC-002 Off Site Inspection | 28/01/2020 | 10 | 28/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.75 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 28/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.74 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 28/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.8 | Closed | R.01.240 - Corridor>Common Areas>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 28/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.635 | Closed JPC Sign Off | 4th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/01/2020 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.327644 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F116412.7 | Closed JPC Sign Off | RM.02.341 - Corridor>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 27/01/2020 | 11 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.6 | Closed JPC Sign Off | RM.02.334 - Corridor>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 27/01/2020 | 11 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.626 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 27/01/2020 | 6 | 28/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F1.327142 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-010 Free Issue Item Form | 27/01/2020 | 6 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F76201.625 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/01/2020 | 9 | 6/2/2020 | 0 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.634 | Completed and signed off | JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/01/2020 | 6 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.326555 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F1.326335 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-108 Underground Services Test | 24/01/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.13 | Closed | 1328 - Townsend St | EHS Inspection. | 24/01/2020 | 9 | 6/2/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.617 | Closed JPC Reviewed | Audits & Assessments>Quality Management>JPC Project Management | QS Site Review | 24/01/2020 | 6 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.616 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 24/01/2020 | 6 | 24/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.615 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 24/01/2020 | 6 | 24/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.633 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/01/2020 | 9 | 6/2/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.630 | JPC Sign Off / Closed | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 24/01/2020 | 11 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.614 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.629 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 23/01/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.325753 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F84104.628 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/01/2020 | 9 | 6/2/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.627 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.607 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 22/01/2020 | 6 | 22/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.324794 | JPC Inspected | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 22/01/2020 | 11 | 3/3/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F1.324787 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 22/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F84104.626 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 22/01/2020 | 11 | 30/03/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.606 | Closed | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | SM-FRM-006 Area Handover | 22/01/2020 | 6 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.605 | Closed | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | SM-FRM-006 Area Handover | 22/01/2020 | 6 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.604 | Closed | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | SM-FRM-006 Area Handover | 22/01/2020 | 6 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.603 | Closed | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | SM-FRM-006 Area Handover | 22/01/2020 | 6 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.602 | Closed | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | SM-FRM-006 Area Handover | 22/01/2020 | 6 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.324635 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 22/01/2020 | 9 | 6/2/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.324272 | Open / Ongoing Works | ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 22/01/2020 | 8 | 22/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.73 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F108023.72 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F108023.71 | In Manufactor | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/01/2020 | 8 | 22/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.70 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/01/2020 | 8 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.69 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/01/2020 | 8 | 30/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.68 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.67 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.65 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 22/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.323903 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F1.323837 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.625 | JPC Sign Off / Closed | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 21/01/2020 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.624 | JPC Sign Off / Closed | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 21/01/2020 | 11 | 21/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.3 | Closed JPC Sign Off | RM.02.344 - Corridor>Common Areas>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 21/01/2020 | 11 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.2 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 21/01/2020 | 11 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F116412.1 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 21/01/2020 | 11 | 6/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.623 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 21/01/2020 | 9 | 24/01/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F108023.64 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.62 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.60 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.59 | Ready to be delivered | Site Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.58 | Ready to be delivered | Site Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.57 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.56 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.54 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.52 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.51 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.50 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F108023.48 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F76201.601 | Closed | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 21/01/2020 | 10 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F108023.47 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 21/01/2020 | 8 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F76201.600 | Closed | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 21/01/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.327941 | JPC Sign Off / Closed | 1328 - Townsend St | QM-FRM-GEN-001 Non Conformance Record (NCR) | 28/01/2020 | 10 | 28/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F1.330872 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.330877 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/01/2020 | 11 | 4/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.330884 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/01/2020 | 11 | 4/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.331174 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/01/2020 | 11 | 26/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.331178 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/01/2020 | 11 | 26/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.331183 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/01/2020 | 11 | 26/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.331190 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/01/2020 | 11 | 26/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.333293 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 4/2/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.345834 | Works Complete | 1328 - Townsend St | BCAR Inspection Form | 21/02/2020 | 3 | 1/5/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.350479 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/02/2020 | 11 | 28/02/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F107663.49 | Closed JPC Sign Off | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/02/2020 | 11 | 25/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.50 | Closed JPC Sign Off | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/02/2020 | 11 | 25/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.179 | Closed | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 25/02/2020 | 10 | 4/3/2020 | 0 | 0 | child | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.609 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.610 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.611 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.612 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.613 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.630 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.631 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.632 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.653 | Closed JPC Sign Off | 4th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 4/2/2020 | 11 | 25/02/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.654 | Closed JPC Sign Off | 4th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 4/2/2020 | 11 | 25/02/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.704 | Closed | 4th Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 18/02/2020 | 10 | 3/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.636 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.637 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.640 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 19/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.643 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.644 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.645 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 19/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.656 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 4/2/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.666 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 12/2/2020 | 11 | 25/02/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.667 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 12/2/2020 | 11 | 25/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.668 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 12/2/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.669 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 12/2/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.670 | Closed JPC Sign Off | 1st Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 12/2/2020 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.181 | Closed | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 25/02/2020 | 10 | 8/7/2020 | 0 | 0 | child | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.693 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 18/02/2020 | 11 | 30/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.694 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 18/02/2020 | 11 | 30/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.697 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 19/02/2020 | 11 | 19/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.698 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 19/02/2020 | 11 | 19/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.699 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 19/02/2020 | 11 | 19/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.701 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 19/02/2020 | 11 | 19/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.705 | Closed JPC Sign Off | Foundations>Block 2>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 20/02/2020 | 11 | 20/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.15 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 5/2/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.16 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 5/2/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.17 | Closed JPC Sign Off | 6th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 5/2/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.159 | Open / Ongoing Works | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/02/2020 | 10 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.691 | JPC Sign Off / Closed | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 22/06/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.22 | Open / Ongoing Works | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.178 | Open / Ongoing Works | 2nd to 3rd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 25/02/2020 | 8 | 25/02/2020 | 1 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F90895.26 | Open / Ongoing Works | 3rd to 4th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.727 | Open / Ongoing Works | 4th to 5th Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.177 | Open / Ongoing Works | 1st to 2nd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 24/02/2020 | 8 | 24/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F84104.692 | Open / Ongoing Works | 2nd to 3rd Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 18/02/2020 | 10 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.27 | Open / Ongoing Works | 3rd to 4th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.728 | Open / Ongoing Works | 4th to 5th Floor>2. Courtyard (North Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F116412.166 | Open / Ongoing Works | 1st to 2nd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/02/2020 | 10 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.167 | JPC Sign Off / Closed | 1st to 2nd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 20/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.168 | Open / Ongoing Works | 1st to 2nd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/02/2020 | 10 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.23 | Open / Ongoing Works | 2nd to 3rd Floor>3. Courtyard (West Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.172 | Open / Ongoing Works | 1st to 2nd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/02/2020 | 10 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.169 | Open / Ongoing Works | 1st to 2nd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/02/2020 | 10 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.171 | JPC Sign Off / Closed | 1st to 2nd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 20/02/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.170 | Open / Ongoing Works | 1st to 2nd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 20/02/2020 | 10 | 20/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F90895.24 | Open / Ongoing Works | 2nd to 3rd Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90895.25 | Open / Ongoing Works | 3rd to 4th Floor>4. Courtyard (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F116412.145 | Closed | 1st to 2nd Floor>1. Bracken Lane (South Elevation)>Elevations>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 18/02/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.71 | Closed | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F116412.70 | Closed | Area 2>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 11/2/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.120 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 21/01/2020 | 9 | 24/01/2020 | 0 | 13 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F84104.622 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.323016 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/01/2020 | 6 | 5/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.599 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 20/01/2020 | 6 | 22/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.621 | Closed JPC Sign Off | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 20/01/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.598 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 20/01/2020 | 6 | 22/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.620 | Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 20/01/2020 | 10 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.596 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 20/01/2020 | 6 | 22/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.595 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 20/01/2020 | 6 | 21/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.619 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F107663.39 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 19/01/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.618 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 17/01/2020 | 9 | 21/01/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.321852 | Open / Ongoing Works | 1328 - Townsend St | SM-FRM-003 Daily Allocation Sheet | 17/01/2020 | 6 | 17/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F1.321848 | Open / Ongoing Works | 1328 - Townsend St | SM-FRM-003 Daily Allocation Sheet | 17/01/2020 | 6 | 17/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F1.321843 | Open / Ongoing Works | ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-SUB-100 Subcontractor Inspection Report | 17/01/2020 | 12 | 17/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 5
F1.321842 | Open / Ongoing Works | 1328 - Townsend St | SM-FRM-003 Daily Allocation Sheet | 17/01/2020 | 6 | 17/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F1.321837 | Open / Ongoing Works | 1328 - Townsend St | SM-FRM-003 Daily Allocation Sheet | 17/01/2020 | 6 | 17/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 3
F90895.12 | Closed | 1328 - Townsend St | EHS Inspection. | 17/01/2020 | 9 | 6/2/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.321757 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-010 Free Issue Item Form | 17/01/2020 | 6 | 17/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 3
F84104.617 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.616 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/01/2020 | 11 | 23/01/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.119 | Open / Ongoing Works | RM.02.207>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/01/2020 | 8 | 16/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90896.118 | Open / Ongoing Works | ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/01/2020 | 8 | 16/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F76201.594 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/01/2020 | 9 | 21/01/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.593 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/01/2020 | 9 | 20/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.615 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 16/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.320309 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 15/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F76201.592 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 15/01/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.117 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 15/01/2020 | 9 | 21/01/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.591 | Closed | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-009 Quality Control Record | 15/01/2020 | 10 | 15/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.590 | Closed JPC Sign Off | 5th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 15/01/2020 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.319647 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/01/2020 | 8 | 15/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.319633 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ARC-202 Partitions Inspection | 15/01/2020 | 8 | 15/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F84104.613 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 15/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.319392 | JPC Sign Off / Closed | 1328 - Townsend St | QM-FRM-QC-008 Non Conformance Record (NCR) | 15/01/2020 | 10 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.589 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 14/01/2020 | 9 | 16/01/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.319215 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.319209 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/01/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.612 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.588 | Open | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 13/01/2020 | 9 | 13/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F76201.587 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/01/2020 | 9 | 16/01/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.611 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/01/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F1.317269 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/1/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F90895.11 | Closed | 1328 - Townsend St | EHS Inspection. | 10/1/2020 | 9 | 21/01/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.610 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/1/2020 | 9 | 16/01/2020 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.609 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/1/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.608 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/1/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.316626 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 10/1/2020 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.586 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/1/2020 | 9 | 16/01/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.585 | Opened | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/1/2020 | 9 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F1.316395 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 9/1/2020 | 13 | 18/08/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.316168 | Closed JPC Reviewed | 1328 - Townsend St | QM-FRM-QC005 - Training Record | 9/1/2020 | 10 | 10/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.315719 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/1/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F84104.607 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 8/1/2020 | 9 | 16/01/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.606 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 8/1/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.605 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/1/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.314955 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/1/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.604 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/1/2020 | 9 | 10/1/2020 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.603 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 7/1/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.602 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 7/1/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.601 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/1/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.314318 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/1/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F84104.600 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/1/2020 | 9 | 16/01/2020 | 0 | 7 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.314154 | 3rd Party Sign Off - Closed | 1328 - Townsend St | QM-FRM-ARC-201 Benchmark / Sample Form | 6/1/2020 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F84104.599 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 6/1/2020 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.598 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/1/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.313802 | 3rd Party Sign Off - Closed | 1328 - Townsend St | QM-FRM-BCAR-100 Structural BCAR Inspection | 6/1/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.313694 | JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/1/2020 | 13 | 8/9/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.313693 | 3rd Party Sign Off - Closed | 2nd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/1/2020 | 13 | 18/08/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.313690 | 3rd Party Sign Off - Closed | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/1/2020 | 13 | 18/08/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.313689 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/1/2020 | 13 | 18/08/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.313687 | Open / Ongoing Works | Basement GA>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/1/2020 | 13 | 3/1/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.313685 | 3rd Party Sign Off - Closed | Basement GA>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/1/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.313684 | 3rd Party Sign Off - Closed | Basement GA>Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 3/1/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.309860 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 16/12/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F84104.584 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/12/2019 | 9 | 16/01/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.309627 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/12/2019 | 11 | 26/02/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.583 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/12/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.582 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 16/12/2019 | 6 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.581 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 16/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.580 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/12/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.579 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/12/2019 | 9 | 16/12/2019 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.308738 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/12/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.308623 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 13/12/2019 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.308162 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/12/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F90896.110 | JPC Sign Off / Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 12/12/2019 | 11 | 6/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F74906.85 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/12/2019 | 9 | 6/2/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.578 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/12/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90896.108 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 12/12/2019 | 9 | 16/12/2019 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.577 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/12/2019 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.307439 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/12/2019 | 6 | 5/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F84104.576 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 11/12/2019 | 9 | 16/12/2019 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.575 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 11/12/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.574 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F77029.27 | Closed | JPC Project Management | JPC-HR-FRM-001 - Training Record | 10/12/2019 | 2 | 10/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F90896.107 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/12/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.577 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 10/12/2019 | 9 | 16/12/2019 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.575 | Closed JPC Sign Off | JPC Project Management | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/12/2019 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.573 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.574 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/12/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.572 | JPC Sign Off / Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 9/12/2019 | 11 | 6/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.572 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 9/12/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F107663.35 | Closed | RM.02.204>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 9/12/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.34 | Closed | RM.02.202>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 9/12/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.571 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/12/2019 | 9 | 16/12/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90896.106 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F107663.33 | JPC Inspected | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/12/2019 | 11 | 17/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.570 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/12/2019 | 9 | 9/12/2019 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.569 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 6/12/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F90896.105 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 6/12/2019 | 9 | 16/12/2019 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.568 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.567 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F107663.32 | JPC Sign Off / Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 5/12/2019 | 11 | 26/02/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.566 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/12/2019 | 9 | 16/12/2019 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.303876 | 3rd Party Sign Off - Closed | 1328 - Townsend St | QM-FRM-ARC-201 Benchmark / Sample Form | 5/12/2019 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.303866 | 3rd Party Sign Off - Closed | 1328 - Townsend St | QM-FRM-BCAR-200 Architectural BCAR Inspection | 5/12/2019 | 13 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 6
F1.303856 | 3rd Party Sign Off - Closed | 1328 - Townsend St | QM-FRM-BCAR-200 Architectural BCAR Inspection | 5/12/2019 | 13 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 6
F90896.104 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 5/12/2019 | 11 | 26/02/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.570 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.303332 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 4/12/2019 | 9 | 5/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.565 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/12/2019 | 9 | 16/12/2019 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.569 | Opened | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 4/12/2019 | 9 | 4/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F1.303027 | JPC Sign Off / Closed | 1328 - Townsend St | QM-CL-ME-405 Lightning Protection & Earthing Inspection | 4/12/2019 | 1 | 4/12/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F84104.564 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F1.302243 | JPC Sign Off / Closed | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 3/12/2019 | 11 | 17/12/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.563 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.562 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.301695 | JPC Inspected | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/12/2019 | 10 | 24/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90896.102 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F107663.31 | JPC Sign Off / Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 2/12/2019 | 11 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.301638 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 2/12/2019 | 9 | 5/12/2019 | 0 | 8 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F90896.100 | JPC Inspected | Block 1>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 2/12/2019 | 10 | 8/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F1.301164 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 2/12/2019 | 8 | 9/12/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F84104.561 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.560 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 29/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.300669 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 29/11/2019 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F1.300642 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 29/11/2019 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F90896.98 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 29/11/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.559 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/11/2019 | 9 | 5/12/2019 | 0 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.558 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 29/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F107663.30 | JPC Inspected | Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 28/11/2019 | 10 | 24/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F76201.564 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/11/2019 | 9 | 5/12/2019 | 0 | 20 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.555 | Closed JPC Sign Off | JPC Project Management | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/11/2019 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.554 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 28/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F107663.29 | Closed | RM.02.203>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.28 | Closed | RM.02.201>Area 1>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 27/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.553 | JPC Sign Off / Closed | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 27/11/2019 | 11 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90896.97 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 27/11/2019 | 9 | 2/12/2019 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F74906.84 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 27/11/2019 | 9 | 4/3/2020 | 0 | 7 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F90896.95 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 27/11/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90896.94 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.563 | Closed JPC Sign Off | 2nd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 27/11/2019 | 11 | 26/02/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.298472 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 26/11/2019 | 11 | 16/12/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.552 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 26/11/2019 | 9 | 2/12/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.298327 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/11/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F107663.27 | Closed | RM.02.273>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.551 | Closed | RM.02.254>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.550 | Closed | RM.02.256>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.549 | Closed | RM.02.258>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.547 | Closed | RM.02.260>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.546 | Closed | RM.02.262>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.545 | Closed | RM.02.264>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.544 | Closed | RM.02.265>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.543 | Closed | RM.02.266>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.542 | Closed | RM.02.267>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.541 | Closed | RM.02.268>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.26 | Closed | RM.02.252>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.25 | Closed | RM.02.250>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.24 | Closed | RM.02.248>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.23 | Closed | RM.02.246>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.22 | Closed | RM.02.244>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.21 | Closed | RM.02.242>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.18 | Closed | RM.02.240>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.17 | Closed | RM.02.238>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.16 | Closed | RM.02.236>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.15 | Closed | RM.02.234>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.14 | Closed | RM.02.232>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.13 | Closed | RM.02.230>Area 2>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 26/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F108023.45 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 26/11/2019 | 8 | 17/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F108023.44 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 26/11/2019 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.540 | JPC Sign Off / Closed | 2nd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 26/11/2019 | 11 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.539 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.297607 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 25/11/2019 | 11 | 17/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.297606 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 25/11/2019 | 11 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.297604 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 25/11/2019 | 11 | 26/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.297592 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 25/11/2019 | 11 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.297587 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/11/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F84104.593 | Closed JPC Sign Off | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 2/1/2020 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.115 | Closed | 1328 - Townsend St | EHS Inspection. | 19/12/2019 | 9 | 21/01/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.311435 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/12/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F113721.1 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 18/12/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90896.114 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 18/12/2019 | 9 | 19/12/2019 | 0 | 18 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.592 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.310766 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/12/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F90896.113 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 17/12/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.584 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/12/2019 | 9 | 10/1/2020 | 0 | 16 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.581 | JPC Sign Off / Closed | 2nd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 17/12/2019 | 11 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.588 | JPC Inspected | Block 4>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 17/12/2019 | 10 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.587 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/12/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F90896.112 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-ME-405 Lightning Protection & Earthing Inspection | 16/12/2019 | 1 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F107663.12 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/11/2019 | 11 | 16/12/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90896.90 | Open / Ongoing Works | First Floor GA>02 Co-ordinated Service Drawings>ITP 04 M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/11/2019 | 8 | 20/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90896.89 | Open / Ongoing Works | First Floor GA>02 Co-ordinated Service Drawings>ITP 04 M&E Services>QC & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/11/2019 | 8 | 20/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F107663.4 | JPC Inspected | Walls Area A2>Precast Walls>2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 20/11/2019 | 10 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F84104.523 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/11/2019 | 9 | 26/11/2019 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.522 | Open / Ongoing Works | 02 Co-ordinated Service Drawings>ITP 04 M&E Services>QC & BC(A)R | QM-FRM-ME-401 M&E Benchmark Inspection | 20/11/2019 | 1 | 20/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F1.294746 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/11/2019 | 6 | 25/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F84104.520 | JPC Sign Off / Closed | Walls Area A2>Precast Walls>2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 20/11/2019 | 11 | 9/12/2019 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.562 | Closed | Area A1>Precast Slabs>3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 20/11/2019 | 10 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.294452 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/11/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F84104.519 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.294402 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/11/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F1.294200 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 19/11/2019 | 11 | 22/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F74906.83 | JPC Sign Off / Closed | JPC Project Management | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 19/11/2019 | 11 | 28/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F108023.42 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.41 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.40 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.39 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.38 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.37 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.36 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.35 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.34 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.33 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.32 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.31 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.30 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.29 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.28 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.27 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 26/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.26 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 26/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.25 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.24 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.23 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.22 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.21 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.20 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.19 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.18 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.17 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.16 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.15 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.14 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.13 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.12 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.11 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 21/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.10 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 21/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F108023.9 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 21/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F108023.8 | Ready to be delivered | QC Training Records>Quality Management>JPC Project Management | B-Pod - Bathroom Pod ITP Inspection. | 19/11/2019 | 8 | 21/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F76201.561 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 19/11/2019 | 9 | 20/11/2019 | 0 | 15 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90896.88 | Closed JPC Sign Off | Basement GA>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 19/11/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.518 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.532 | JPC Inspected | Area A2>Precast Slabs>2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 25/11/2019 | 10 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F90896.93 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/11/2019 | 9 | 26/11/2019 | 0 | 9 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F107663.11 | Closed | RM.02.270>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.10 | Closed | RM.02.272>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.530 | JPC Inspected | 2nd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 25/11/2019 | 10 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F107663.9 | Closed | RM.02.275>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.8 | Closed | RM.02.274>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.529 | Closed | RM.02.276>Area 3>2nd Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-221 Bathroom POD Inspection | 25/11/2019 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.528 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.296704 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 22/11/2019 | 11 | 9/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.296699 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 22/11/2019 | 11 | 22/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.296697 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 22/11/2019 | 11 | 22/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.296694 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 22/11/2019 | 11 | 22/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F107663.7 | JPC Inspected | Area A3>Precast Slabs>3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 22/11/2019 | 10 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 4
F84104.527 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/11/2019 | 9 | 26/11/2019 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F90896.92 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 22/11/2019 | 9 | 26/11/2019 | 0 | 10 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.526 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 22/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.525 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/11/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.524 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/11/2019 | 9 | 26/11/2019 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F90896.91 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.517 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 18/11/2019 | 11 | 22/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.293414 | 3rd Party Sign Off - Closed | 1328 - Townsend St | QM-FRM-ARC-201 Benchmark / Sample Form | 18/11/2019 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.516 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/11/2019 | 9 | 20/11/2019 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90896.86 | JPC Sign Off / Closed | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 18/11/2019 | 11 | 2/4/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.514 | Closed JPC Sign Off | Basement GA>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 18/11/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F1.292918 | JPC Sign Off | 1328 - Townsend St | QM-FRM-QC-001 Benchmark / Sample Form | 18/11/2019 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.292912 | JPC Sign Off | 1328 - Townsend St | QM-FRM-QC-001 Benchmark / Sample Form | 18/11/2019 | 10 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.292882 | JPC Sign Off | 1328 - Townsend St | QM-FRM-QC-001 Benchmark / Sample Form | 18/11/2019 | 10 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.292867 | JPC Sign Off | 1328 - Townsend St | QM-FRM-QC-001 Benchmark / Sample Form | 18/11/2019 | 10 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F1.292758 | Test Results Required | 02 Drainage>ITP 03 External Works>QC & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 18/11/2019 | 11 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 4
F84104.513 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/11/2019 | 6 | 30/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.292674 | Closed JPC Reviewed | 1328 - Townsend St | QM-FRM-QC-002 Off Site Inspection | 18/11/2019 | 10 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.511 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 15/11/2019 | 11 | 22/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.292440 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 15/11/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.510 | JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 15/11/2019 | 11 | 15/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90896.82 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 15/11/2019 | 9 | 20/11/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.498 | Closed JPC Sign Off | Basement GA>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 14/11/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90896.72 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.497 | JPC Sign Off / Closed | Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 13/11/2019 | 11 | 14/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.290524 | Closed | 1328 - Townsend St | JPC-HR-FRM-001 - Training Record | 13/11/2019 | 2 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F84104.493 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/11/2019 | 9 | 2/12/2019 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.492 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/11/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.290266 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/11/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.560 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 12/11/2019 | 9 | 13/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F90896.71 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 12/11/2019 | 9 | 20/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.491 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/11/2019 | 11 | 5/12/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.69 | Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 12/11/2019 | 11 | 14/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90896.68 | Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 12/11/2019 | 11 | 14/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.559 | Closed | RM.01.110>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection (Windows & Doors) | 12/11/2019 | 8 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.490 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/11/2019 | 6 | 30/03/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.488 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/11/2019 | 6 | 30/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F102497.5 | In Process / Manufactor | Items to be Deleted | QM-FRM-QC-002 Off Site Inspection | 11/11/2019 | 10 | 11/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F84104.487 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/11/2019 | 9 | 13/11/2019 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.288955 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 11/11/2019 | 8 | 13/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F102497.4 | In Process / Manufactor | ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 11/11/2019 | 10 | 11/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 4
F90896.67 | Closed JPC Sign Off | Basement GA>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 11/11/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F90896.66 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/11/2019 | 6 | 30/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F90896.65 | Closed JPC Sign Off | Basement GA>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 8/11/2019 | 11 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.486 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/11/2019 | 9 | 13/11/2019 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.485 | JPC Sign Off / Closed | Area A2>Precast Slabs>3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 8/11/2019 | 11 | 18/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.288084 | Closed | QC Training Records>Quality Management>JPC Project Management | JPC-HR-FRM-001 - Training Record | 8/11/2019 | 2 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F76201.558 | Closed | 1328 - Townsend St | EHS Inspection. | 8/11/2019 | 9 | 13/11/2019 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.483 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/11/2019 | 6 | 30/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.482 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/11/2019 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.481 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 8/11/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.287669 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/11/2019 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.480 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/11/2019 | 9 | 8/11/2019 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.479 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/11/2019 | 6 | 16/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.505 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/11/2019 | 9 | 20/11/2019 | 0 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90896.79 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 15/11/2019 | 11 | 5/12/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.78 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 15/11/2019 | 11 | 15/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.291975 | Closed JPC Reviewed | 1328 - Townsend St | QM-FRM-QC-002 Off Site Inspection | 15/11/2019 | 10 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.291965 | Closed JPC Reviewed | 1328 - Townsend St | QM-FRM-QC-002 Off Site Inspection | 15/11/2019 | 10 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.291949 | Closed JPC Reviewed | 1328 - Townsend St | QM-FRM-QC-002 Off Site Inspection | 15/11/2019 | 10 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.291931 | Closed JPC Reviewed | 1328 - Townsend St | QM-FRM-QC-002 Off Site Inspection | 15/11/2019 | 10 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.502 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 15/11/2019 | 6 | 30/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.557 | Completed and signed off | JPC Responsilbility Matrix>JPC Project Management | EHS Managment Inspection - Daily | 6/11/2019 | 9 | 2/12/2019 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.470 | JPC Sign Off / Closed | Walls Area A1>Precast Walls>2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 6/11/2019 | 11 | 19/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.286401 | Ready to be delivered | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 6/11/2019 | 8 | 8/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F84104.469 | JPC Inspected | Walls Area A3>Precast Walls>2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 6/11/2019 | 10 | 20/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.286350 | In Manufactor | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 6/11/2019 | 8 | 6/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F84104.468 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/11/2019 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.556 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 6/11/2019 | 11 | 5/12/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F1.286130 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/11/2019 | 6 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F76201.555 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/11/2019 | 9 | 8/11/2019 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.465 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/11/2019 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.285388 | Open / Ongoing Works | 1328 - Townsend St | QM-CL-ME-403 Mechanical Inspection | 4/11/2019 | 1 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F90896.64 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/11/2019 | 6 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 3
F76201.554 | Closed JPC Sign Off | Basement GA>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 4/11/2019 | 11 | 14/07/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.553 | Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 4/11/2019 | 11 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.552 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/11/2019 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.464 | Closed | 1328 - Townsend St | EHS Inspection. | 1/11/2019 | 9 | 8/11/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90896.62 | JPC Sign Off / Closed | Area A1>Precast Slabs>3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 1/11/2019 | 11 | 18/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.551 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 1/11/2019 | 6 | 20/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.284340 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 1/11/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.550 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 1/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.463 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 1/11/2019 | 9 | 8/11/2019 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.284267 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 1/11/2019 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 3
F76201.549 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 1/11/2019 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.548 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 1/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.462 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 1/11/2019 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.291762 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/11/2019 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.291667 | Closed | 1328 - Townsend St | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 14/11/2019 | 11 | 14/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F74906.82 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 14/11/2019 | 9 | 20/11/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.291636 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 14/11/2019 | 8 | 14/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.291601 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 14/11/2019 | 8 | 14/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.291585 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 14/11/2019 | 8 | 14/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.291571 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 14/11/2019 | 8 | 14/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.291526 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 14/11/2019 | 8 | 14/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.291506 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 14/11/2019 | 8 | 14/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F1.291497 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 14/11/2019 | 8 | 14/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F90896.76 | JPC Sign Off / Closed | RM.01.112>Area 1>1st Floor Plan>Block 3>ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-CL-ARC-209 Glazing Inspection (Windows & Doors) | 14/11/2019 | 8 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.499 | JPC Sign Off / Closed | Area A3>Precast Slabs>3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 14/11/2019 | 11 | 9/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.291440 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 14/11/2019 | 8 | 14/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.291392 | Delivered to site | 1328 - Townsend St | B-Pod - Bathroom Pod ITP Inspection. | 14/11/2019 | 8 | 14/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.451 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 30/10/2019 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.450 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 29/10/2019 | 11 | 15/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.60 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 29/10/2019 | 11 | 29/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.59 | JPC Sign Off / Closed | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 29/10/2019 | 11 | 5/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F1.282624 | Open / Ongoing Works | 1328 - Townsend St | Qm-CL-CS-112 Structural Steel Inspection | 29/10/2019 | 11 | 29/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F1.282623 | Closed | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 29/10/2019 | 11 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F84104.444 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 29/10/2019 | 9 | 8/11/2019 | 0 | 8 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.443 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 29/10/2019 | 6 | 15/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.281344 | 3rd Party Sign Off - Closed | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 28/10/2019 | 13 | 18/08/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.281230 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 26/10/2019 | 13 | 18/08/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 6
F1.281229 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 26/10/2019 | 13 | 18/08/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.281228 | 3rd Party Sign Off - Closed | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 26/10/2019 | 13 | 18/08/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F77029.25 | Closed | JPC Project Management | JPC-HR-FRM-001 - Training Record | 25/10/2019 | 2 | 25/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.545 | Closed | 1328 - Townsend St | EHS Inspection. | 25/10/2019 | 9 | 8/11/2019 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90896.54 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/10/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90896.53 | Opened | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/10/2019 | 9 | 25/10/2019 | 1 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F84104.442 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/10/2019 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.543 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 25/10/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.441 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 25/10/2019 | 6 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.440 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/10/2019 | 9 | 8/11/2019 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.438 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/10/2019 | 9 | 24/10/2019 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.437 | JPC Sign Off / Closed | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 23/10/2019 | 11 | 7/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.436 | JPC Sign Off / Closed | Precast Walls>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 23/10/2019 | 11 | 3/4/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.435 | JPC Sign Off / Closed | Area A2>Precast Slabs>2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 23/10/2019 | 11 | 19/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.434 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 23/10/2019 | 11 | 15/11/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90896.52 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/10/2019 | 6 | 15/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F90896.51 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 23/10/2019 | 11 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.283927 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/10/2019 | 6 | 15/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 3
F76201.547 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 31/10/2019 | 9 | 8/11/2019 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.458 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/10/2019 | 6 | 24/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F1.283327 | Completed and signed off | 1328 - Townsend St | 1328 CM-SM-FRM-001 Site Diary | 30/10/2019 | 6 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.80 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 30/10/2019 | 9 | 8/11/2019 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.454 | JPC Inspected | Area A2>Precast Slabs>2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 30/10/2019 | 10 | 28/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 4
F76201.546 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 30/10/2019 | 9 | 8/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.431 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/10/2019 | 9 | 24/10/2019 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.430 | JPC Sign Off / Closed | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 22/10/2019 | 11 | 7/4/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F82131.3 | 3rd Party Sign Off - Closed | Area A1>Precast Slabs>2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 22/10/2019 | 13 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 6
F90896.50 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 22/10/2019 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.539 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 21/10/2019 | 9 | 24/10/2019 | 0 | 17 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.428 | JPC Sign Off / Closed | Precast Walls>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 21/10/2019 | 11 | 6/4/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.426 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 21/10/2019 | 11 | 15/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.423 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/10/2019 | 6 | 25/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.421 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 18/10/2019 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.420 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 18/10/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.418 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/10/2019 | 9 | 24/10/2019 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90896.49 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/10/2019 | 6 | 15/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F74906.79 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 18/10/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 3
F90896.48 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 17/10/2019 | 11 | 22/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.47 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 17/10/2019 | 11 | 21/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.46 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 17/10/2019 | 11 | 17/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.538 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/10/2019 | 9 | 24/10/2019 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.416 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/10/2019 | 6 | 11/11/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.415 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 16/10/2019 | 11 | 16/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.413 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/10/2019 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.407 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 16/10/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.406 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 15/10/2019 | 9 | 15/10/2019 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F90896.45 | Closed | EHS Management>JPC Project Management | EHS Inspection. | 15/10/2019 | 9 | 24/10/2019 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.536 | Opened | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 15/10/2019 | 9 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F84104.405 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 15/10/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.273928 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 14/10/2019 | 9 | 24/10/2019 | 0 | 8 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F90896.44 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 14/10/2019 | 11 | 10/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.41 | Open | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 14/10/2019 | 9 | 14/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 2
F90896.40 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 14/10/2019 | 11 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.404 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 14/10/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.403 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 14/10/2019 | 11 | 15/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.401 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/10/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F74906.78 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F90896.39 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 11/10/2019 | 11 | 11/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.535 | Closed | 1328 - Townsend St | EHS Inspection. | 11/10/2019 | 9 | 24/10/2019 | 0 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.400 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/10/2019 | 9 | 24/10/2019 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.399 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F74906.77 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 11/10/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.537 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/10/2019 | 9 | 24/10/2019 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F90896.37 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 10/10/2019 | 11 | 10/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.36 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 10/10/2019 | 11 | 10/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.34 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/10/2019 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.534 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 10/10/2019 | 9 | 24/10/2019 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.533 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 10/10/2019 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.532 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 10/10/2019 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F76201.529 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 10/10/2019 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.528 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 10/10/2019 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.527 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.393 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 9/10/2019 | 9 | 24/10/2019 | 0 | 5 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F84104.388 | JPC Sign Off / Closed | Walls Area A1>Precast Walls>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 9/10/2019 | 11 | 3/4/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.526 | JPC Inspected | Quality Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 9/10/2019 | 10 | 28/01/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F74906.76 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 9/10/2019 | 6 | 20/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.387 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 9/10/2019 | 11 | 15/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.386 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/10/2019 | 6 | 10/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F90896.33 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/10/2019 | 11 | 8/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.32 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/10/2019 | 11 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F90896.24 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 7/10/2019 | 11 | 7/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F74906.75 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 7/10/2019 | 9 | 9/10/2019 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.376 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 7/10/2019 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.375 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/10/2019 | 6 | 10/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F90896.22 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 4/10/2019 | 11 | 2/4/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.374 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/10/2019 | 9 | 4/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.373 | Closed | 1328 - Townsend St | EHS Inspection. | 4/10/2019 | 9 | 9/10/2019 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.371 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/10/2019 | 6 | 10/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.370 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 3/10/2019 | 11 | 3/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.378 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/10/2019 | 9 | 9/10/2019 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.377 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/10/2019 | 6 | 10/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.366 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/10/2019 | 9 | 4/10/2019 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.364 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/10/2019 | 6 | 10/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.361 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 3/10/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.21 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 2/10/2019 | 11 | 3/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.20 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 2/10/2019 | 11 | 2/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.357 | Open | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 2/10/2019 | 9 | 2/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F84104.356 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/10/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.355 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 1/10/2019 | 9 | 4/10/2019 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.267280 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 1/10/2019 | 6 | 8/10/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.352 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 30/09/2019 | 9 | 4/10/2019 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.266399 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 30/09/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.266391 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 30/09/2019 | 6 | 8/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.266390 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 30/09/2019 | 11 | 2/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.266130 | 3rd Party Sign Off - Closed | 02 Drainage>ITP 03 External Works>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 29/09/2019 | 13 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 6
F1.266129 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 29/09/2019 | 13 | 19/08/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.266128 | Open / Ongoing Works | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 29/09/2019 | 13 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F1.266127 | Open / Ongoing Works | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 29/09/2019 | 13 | 29/09/2019 | 1 | 7 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F90896.14 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 27/09/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.350 | Closed | 1328 - Townsend St | EHS Inspection. | 27/09/2019 | 9 | 4/10/2019 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.524 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/10/2019 | 9 | 4/10/2019 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.360 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 2/10/2019 | 11 | 2/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.346 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 27/09/2019 | 11 | 2/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.345 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/09/2019 | 6 | 8/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F74906.74 | Closed | 1328 - Townsend St | SM-FRM-007 - Crane Co-ordination Meeting | 27/09/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 3
F74906.72 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/09/2019 | 9 | 4/10/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.342 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/09/2019 | 6 | 8/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.341 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/09/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.334 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/09/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.523 | Closed JPC Reviewed | ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-002B Off Site Inspection - Windows | 25/09/2019 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.333 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/09/2019 | 9 | 4/10/2019 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.328 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/09/2019 | 6 | 27/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.327 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 24/09/2019 | 11 | 25/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.319 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/09/2019 | 9 | 4/10/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.318 | Closed JPC Sign Off | Area A1>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 24/09/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.317 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/09/2019 | 6 | 27/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.316 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 24/09/2019 | 11 | 24/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.263412 | Open / Ongoing Works | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 24/09/2019 | 13 | 24/09/2019 | 1 | 9 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F76201.513 | Closed JPC Reviewed | 1328 - Townsend St | QM-FRM-QC-002a Off Site Inspection - Concrete Precast | 23/09/2019 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.263210 | Closed | 1328 - Townsend St | SM-FRM-007 - Crane Co-ordination Meeting | 23/09/2019 | 6 | 23/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.314 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 23/09/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.313 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/09/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F107663.5 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 20/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.7 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.9 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.10 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.12 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.13 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.14 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F113721.2 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F113721.3 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F113721.5 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.379 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.380 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.381 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.382 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.383 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.384 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.385 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.394 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.395 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.396 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.397 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.398 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.408 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/10/2019 | 11 | 10/12/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.409 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/10/2019 | 11 | 10/12/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.410 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/10/2019 | 11 | 10/12/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.411 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/10/2019 | 11 | 10/12/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.412 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/10/2019 | 11 | 10/12/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.417 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-008 Cause & Effect Record | 18/10/2019 | 6 | 18/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.419 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 18/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.422 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 18/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.427 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 21/10/2019 | 11 | 1/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.429 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/10/2019 | 11 | 7/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.432 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/10/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.433 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.452 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 30/10/2019 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.453 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 30/10/2019 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.455 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 30/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.456 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 30/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.457 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 30/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.459 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.460 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.461 | Closed JPC Sign Off | 1st Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 31/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.472 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 6/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.473 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 6/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.474 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 6/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.475 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 6/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.476 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 6/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.477 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 6/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.478 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 6/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.501 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 14/11/2019 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.503 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.504 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.506 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.507 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.508 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.509 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.533 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.534 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.535 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.536 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.537 | Closed JPC Sign Off | 3rd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.557 | Closed JPC Sign Off | Ground Floor Plan>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 28/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.585 | Closed JPC Sign Off | 2nd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/12/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.586 | Closed JPC Sign Off | 2nd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/12/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.589 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/12/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.590 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/12/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.591 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/12/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.594 | Closed JPC Sign Off | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.595 | Closed JPC Sign Off | 3rd Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.596 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.597 | Closed JPC Sign Off | 4th Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/1/2020 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.315 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/09/2019 | 11 | 15/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.320 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.321 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.322 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.323 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.324 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.325 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.326 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.338 | Closed JPC Sign Off | Area A1>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.339 | Closed JPC Sign Off | Area A1>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.340 | Closed JPC Sign Off | Area A1>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/09/2019 | 11 | 19/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.343 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 26/09/2019 | 11 | 25/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.347 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/09/2019 | 11 | 25/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.348 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/09/2019 | 11 | 25/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.349 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/09/2019 | 11 | 25/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.369 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 3/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.42 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 14/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.43 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 14/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.15 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.16 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.73 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-008 Cause & Effect Record | 14/11/2019 | 6 | 14/11/2019 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F90896.18 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.80 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.81 | Closed JPC Sign Off | 2nd Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.87 | Closed JPC Sign Off | Foundations>Block 1>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 18/11/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F90896.19 | Closed JPC Sign Off | Area A3>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/10/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.28 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/10/2019 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.29 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/10/2019 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.30 | Closed JPC Sign Off | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 7/10/2019 | 11 | 17/02/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.298 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/09/2019 | 6 | 24/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.296 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 18/09/2019 | 9 | 20/09/2019 | 0 | 15 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.294 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 18/09/2019 | 11 | 23/09/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.293 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 18/09/2019 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.292 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 18/09/2019 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.290 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 18/09/2019 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.287 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 18/09/2019 | 11 | 18/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.286 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/09/2019 | 6 | 23/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.260999 | Open / Ongoing Works | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 17/09/2019 | 13 | 17/09/2019 | 1 | 5 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Open | 6
F84104.285 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/09/2019 | 9 | 20/09/2019 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.260792 | Closed | 1328 - Townsend St | SM-FRM-007 - Crane Co-ordination Meeting | 17/09/2019 | 6 | 23/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.284 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/09/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.283 | Closed JPC Reviewed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-CS-104 Material Movement Record | 17/09/2019 | 11 | 17/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.282 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/09/2019 | 11 | 8/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.281 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/09/2019 | 11 | 8/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.512 | Closed | 1328 - Townsend St | EHS Inspection. | 20/09/2019 | 9 | 4/10/2019 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.307 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 20/09/2019 | 11 | 24/09/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.305 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 20/09/2019 | 11 | 23/09/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.304 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/09/2019 | 6 | 23/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.303 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/09/2019 | 9 | 24/09/2019 | 0 | 11 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.302 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 19/09/2019 | 11 | 23/09/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.301 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 19/09/2019 | 11 | 19/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.279 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/09/2019 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.511 | Open | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 16/09/2019 | 9 | 16/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F1.260039 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 16/09/2019 | 9 | 28/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F1.259784 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 14/09/2019 | 9 | 20/09/2019 | 0 | 9 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F84104.277 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-108 Underground Services Test | 13/09/2019 | 11 | 23/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.276 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 13/09/2019 | 11 | 20/02/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.510 | Closed | 1328 - Townsend St | EHS Inspection. | 13/09/2019 | 9 | 20/09/2019 | 0 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.275 | JPC Sign Off / Closed | Area A1>Precast - Slabs>1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 13/09/2019 | 11 | 3/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.312 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/09/2019 | 6 | 24/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.311 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/09/2019 | 9 | 4/10/2019 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.310 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 23/09/2019 | 11 | 14/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.309 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 20/09/2019 | 6 | 20/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.69 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/09/2019 | 9 | 4/10/2019 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.272 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/09/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.509 | Closed | JPC Project Management | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 12/9/2019 | 11 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.259227 | JPC Sign Off / Closed | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-ME-405 Lightning Protection & Earthing Inspection | 12/9/2019 | 1 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F84104.270 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 12/9/2019 | 11 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.259016 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 12/9/2019 | 13 | 18/08/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.259014 | Open / Ongoing Works | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 12/9/2019 | 13 | 14/08/2020 | 1 | 5 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Open | 6
F84104.266 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/9/2019 | 11 | 12/10/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.502 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 12/9/2019 | 9 | 20/09/2019 | 0 | 13 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.265 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 12/9/2019 | 11 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.264 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/9/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.255 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/9/2019 | 11 | 22/10/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F92999.6 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 10/9/2019 | 13 | 21/08/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 6
F92999.5 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 10/9/2019 | 13 | 21/08/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 6
F92999.4 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 10/9/2019 | 13 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 6
F74906.68 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/9/2019 | 9 | 12/9/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.254 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/9/2019 | 6 | 11/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.257207 | Open / Ongoing Works | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 10/9/2019 | 13 | 14/08/2020 | 1 | 7 | parent | FALSE | FALSE | TRUE | TRUE | 1328 | Open | 6
F1.257197 | 3rd Party Sign Off - Closed | 1st Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 10/9/2019 | 13 | 18/08/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 6
F84104.253 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 9/9/2019 | 11 | 10/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.252 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 9/9/2019 | 11 | 23/09/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.251 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 9/9/2019 | 11 | 9/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.500 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/9/2019 | 9 | 12/9/2019 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.250 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 9/9/2019 | 11 | 9/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.499 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/9/2019 | 6 | 10/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.498 | Closed JPC Sign Off | JPC Project Management | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 7/9/2019 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F74906.67 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/9/2019 | 6 | 11/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F74906.66 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 6/9/2019 | 6 | 6/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.247 | Closed | 1328 - Townsend St | EHS Inspection. | 6/9/2019 | 9 | 12/9/2019 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.246 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/9/2019 | 9 | 12/9/2019 | 0 | 12 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.244 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/9/2019 | 6 | 11/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.243 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 5/9/2019 | 11 | 23/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.255211 | Open / Ongoing Works | Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 5/9/2019 | 13 | 14/08/2020 | 3 | 8 | parent | FALSE | TRUE | FALSE | TRUE | 1328 | Open | 6
F1.255207 | 3rd Party Sign Off - Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 5/9/2019 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 6
F1.255203 | 3rd Party Sign Off - Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 5/9/2019 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 6
F1.255199 | 3rd Party Sign Off - Closed | Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 5/9/2019 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 6
F1.255182 | Open / Ongoing Works | Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 5/9/2019 | 13 | 14/08/2020 | 1 | 3 | parent | FALSE | FALSE | TRUE | TRUE | 1328 | Open | 6
F76201.497 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/9/2019 | 9 | 12/9/2019 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.242 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/9/2019 | 6 | 11/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.241 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 4/9/2019 | 11 | 15/11/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.239 | JPC Sign Off / Closed | ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 4/9/2019 | 11 | 18/11/2019 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90896.13 | JPC Sign Off / Closed | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 4/9/2019 | 11 | 4/9/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90896.12 | JPC Sign Off / Closed | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 4/9/2019 | 11 | 2/4/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.238 | JPC Sign Off / Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 4/9/2019 | 11 | 21/02/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.496 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/9/2019 | 9 | 12/9/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.237 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 4/9/2019 | 11 | 7/10/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.254568 | Closed | 1328 - Townsend St | SM-FRM-007 - Crane Co-ordination Meeting | 4/9/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.501 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/9/2019 | 9 | 12/9/2019 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.261 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 11/9/2019 | 11 | 26/09/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.260 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/9/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.259 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 10/9/2019 | 11 | 10/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.257 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 10/9/2019 | 11 | 23/09/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.235 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/9/2019 | 6 | 6/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.495 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/9/2019 | 9 | 12/9/2019 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.233 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 3/9/2019 | 11 | 23/09/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.227 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/9/2019 | 6 | 6/9/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F90896.11 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/9/2019 | 9 | 12/9/2019 | 0 | 5 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F84104.226 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 2/9/2019 | 11 | 30/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.225 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/9/2019 | 6 | 24/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.494 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/08/2019 | 6 | 24/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.493 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/08/2019 | 6 | 24/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.492 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 30/08/2019 | 9 | 12/9/2019 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.223 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 30/08/2019 | 11 | 23/09/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.221 | JPC Sign Off / Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 30/08/2019 | 11 | 2/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.491 | Closed | 1328 - Townsend St | EHS Inspection. | 30/08/2019 | 9 | 12/9/2019 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.220 | JPC Sign Off / Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 30/08/2019 | 11 | 23/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.218 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 30/08/2019 | 6 | 17/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.217 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-108 Underground Services Test | 29/08/2019 | 11 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.213 | JPC Sign Off / Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 29/08/2019 | 11 | 29/08/2019 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F74906.65 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/08/2019 | 9 | 12/9/2019 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.212 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 28/08/2019 | 9 | 28/08/2019 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F74906.63 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 28/08/2019 | 6 | 30/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.210 | JPC Sign Off / Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 28/08/2019 | 11 | 28/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.209 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/08/2019 | 11 | 12/10/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.208 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 28/08/2019 | 6 | 29/08/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.207 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/08/2019 | 9 | 12/9/2019 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.203 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/08/2019 | 6 | 28/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.250448 | Open | 1328 - Townsend St | CM-SM-FRM-003 Allocation Sheet | 27/08/2019 | 6 | 27/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F84104.201 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/08/2019 | 11 | 28/08/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.192 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/08/2019 | 6 | 26/08/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.191 | JPC Sign Off / Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 23/08/2019 | 11 | 23/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.190 | JPC Sign Off / Closed | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 22/08/2019 | 11 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.484 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 22/08/2019 | 9 | 28/08/2019 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.189 | Closed | 1328 - Townsend St | EHS Inspection. | 22/08/2019 | 9 | 28/08/2019 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.188 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 22/08/2019 | 6 | 26/08/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.187 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 22/08/2019 | 11 | 26/08/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.186 | JPC Sign Off / Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 22/08/2019 | 11 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.10 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 26/08/2019 | 9 | 12/9/2019 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.489 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/08/2019 | 6 | 27/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.488 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 23/08/2019 | 11 | 28/08/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.487 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/08/2019 | 9 | 28/08/2019 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.486 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 23/08/2019 | 11 | 28/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.195 | Opened | 1328 - Townsend St | EHS Inspection. | 23/08/2019 | 9 | 23/08/2019 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Open | 2
F84104.183 | Closed | 1328 - Townsend St | EHS Inspection. | 21/08/2019 | 9 | 28/08/2019 | 0 | 10 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.182 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/08/2019 | 9 | 28/08/2019 | 0 | 16 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.181 | JPC Sign Off / Closed | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 21/08/2019 | 11 | 21/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.180 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/08/2019 | 6 | 26/08/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F84104.179 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 21/08/2019 | 11 | 28/08/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.176 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/08/2019 | 9 | 28/08/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.175 | JPC Sign Off / Closed | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 20/08/2019 | 11 | 20/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.173 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 20/08/2019 | 11 | 20/08/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.482 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 20/08/2019 | 11 | 26/08/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.172 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/08/2019 | 6 | 21/08/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F90895.10 | Completed and signed off | ITP 01 Structural>QC & BC(A)R | EHS Managment Inspection - Daily | 19/08/2019 | 9 | 28/08/2019 | 0 | 9 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F82129.4 | 3rd Party Sign Off - Closed | 1328 - Townsend St | QM-FRM-ARC-201 Benchmark / Sample Form | 19/08/2019 | 8 | 26/06/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.166 | Closed | Site Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 19/08/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.163 | Completed and signed off | JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/08/2019 | 6 | 19/08/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.162 | Closed | 1328 - Townsend St | EHS Inspection. | 16/08/2019 | 9 | 28/08/2019 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.481 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/08/2019 | 11 | 20/08/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.161 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 15/08/2019 | 9 | 20/08/2019 | 0 | 14 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.160 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 15/08/2019 | 11 | 20/08/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.159 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 15/08/2019 | 6 | 20/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.157 | JPC Sign Off / Closed | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-ME-405 Lightning Protection & Earthing Inspection | 14/08/2019 | 1 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F84104.155 | JPC Sign Off / Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 14/08/2019 | 11 | 15/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90895.9 | Completed and signed off | 03 Safety Notices>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/08/2019 | 9 | 20/08/2019 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.154 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 14/08/2019 | 11 | 20/08/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.150 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 14/08/2019 | 6 | 20/08/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.479 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/08/2019 | 9 | 20/08/2019 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F92999.3 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-600 Assigned Certifier BCAR Inspection | 13/08/2019 | 13 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 6
F84104.149 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 13/08/2019 | 11 | 20/08/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.148 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 13/08/2019 | 6 | 14/08/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.243622 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 13/08/2019 | 9 | 19/08/2019 | 0 | 8 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.478 | Closed JPC Sign Off | ITP 01 Structural>QC & BC(A)R | QM-CL-ME-401 Services Test | 13/08/2019 | 1 | 29/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.243375 | JPC Sign Off | ITP 04 M&E Services>QC & BC(A)R | QM-FRM-BCAR-300 Electrical BCAR Inspection | 12/8/2019 | 13 | 27/08/2019 | 1 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 6
F84104.147 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 12/8/2019 | 11 | 27/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.477 | Closed JPC Sign Off | ITP 01 Structural>QC & BC(A)R | QM-CL-ME-401 Services Test | 12/8/2019 | 1 | 29/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F84104.142 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/8/2019 | 6 | 13/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.476 | JPC Sign Off / Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 9/8/2019 | 11 | 14/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.473 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 9/8/2019 | 11 | 12/8/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.141 | Closed | 1328 - Townsend St | EHS Inspection. | 9/8/2019 | 9 | 20/08/2019 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.140 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/8/2019 | 9 | 20/08/2019 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.139 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/8/2019 | 6 | 12/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.138 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 9/8/2019 | 9 | 9/8/2019 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.136 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 8/8/2019 | 11 | 15/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.129 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/8/2019 | 6 | 12/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.128 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 7/8/2019 | 9 | 8/8/2019 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.470 | Closed JPC Sign Off | Site Management>JPC Project Management | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 7/8/2019 | 11 | 12/8/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.468 | Completed and signed off | JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 7/8/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F90895.8 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/8/2019 | 9 | 19/08/2019 | 0 | 9 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F84104.127 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 6/8/2019 | 6 | 6/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.467 | Closed | EHS Management>JPC Project Management | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 2/8/2019 | 11 | 2/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.466 | Closed JPC Sign Off | EHS Management>JPC Project Management | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 2/8/2019 | 11 | 8/8/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F1.238872 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 2/8/2019 | 6 | 2/8/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.465 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/8/2019 | 9 | 2/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.126 | Closed | 1328 - Townsend St | 1328 - EHS Inspection | 2/8/2019 | 9 | 20/08/2019 | 0 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F74906.62 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 1/8/2019 | 9 | 20/08/2019 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.123 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 1/8/2019 | 11 | 8/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.122 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 1/8/2019 | 11 | 1/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.121 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 1/8/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.237973 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 31/07/2019 | 9 | 6/8/2019 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.118 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 31/07/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.117 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 31/07/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F84104.116 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 31/07/2019 | 9 | 6/8/2019 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.115 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 30/07/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F90895.7 | Completed and signed off | Block 3>ITP 01 Structural>QC & BC(A)R | EHS Managment Inspection - Daily | 30/07/2019 | 9 | 12/8/2019 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.103 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/07/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.102 | Closed | Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 26/07/2019 | 11 | 12/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.101 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 26/07/2019 | 11 | 1/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.100 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/07/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F1.235575 | Open / Ongoing Works | Quality Management>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 26/07/2019 | 10 | 26/07/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Open | 4
F74906.59 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 26/07/2019 | 6 | 26/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.99 | Closed | 1328 - Townsend St | 1328 - EHS Inspection | 26/07/2019 | 9 | 6/8/2019 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.235559 | Open / Ongoing Works | Quality Management>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 26/07/2019 | 10 | 26/07/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Open | 4
F76201.458 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/07/2019 | 9 | 6/8/2019 | 0 | 23 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.98 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/07/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.97 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 25/07/2019 | 11 | 29/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F74907.17 | Closed | 1328 - Townsend St | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 25/07/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F74907.14 | Closed | 01 Inspections>EHS Management>JPC Project Management | 1328 - EHS Inspection | 25/07/2019 | 9 | 12/8/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F74907.13 | Closed | 01 Inspections>EHS Management>JPC Project Management | 1328 - EHS Inspection | 25/07/2019 | 9 | 12/8/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.96 | JPC Sign Off / Closed | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-ME-405 Lightning Protection & Earthing Inspection | 25/07/2019 | 1 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.456 | Completed and signed off | JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/07/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.461 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 30/07/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.111 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 29/07/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.110 | Completed and signed off | Block 3>ITP 01 Structural>QC & BC(A)R | EHS Managment Inspection - Daily | 29/07/2019 | 9 | 12/8/2019 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.236229 | 3rd Party Sign Off - Closed | ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 29/07/2019 | 13 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F84104.105 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 29/07/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.89 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 24/07/2019 | 11 | 8/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.88 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 24/07/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F84104.87 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/07/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F90895.4 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/07/2019 | 9 | 31/07/2019 | 0 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.86 | Closed JPC Reviewed | QC Training Records>Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 24/07/2019 | 10 | 5/9/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F1.234024 | 3rd Party Sign Off - Closed | ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-200 Architectural BCAR Inspection | 24/07/2019 | 13 | 5/9/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 6
F90895.3 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/07/2019 | 9 | 24/07/2019 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.84 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 23/07/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F1.233358 | 3rd Party Sign Off - Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 23/07/2019 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.233352 | 3rd Party Sign Off - Closed | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 23/07/2019 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 6
F76201.454 | Closed | 1328 - Townsend St | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 22/07/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.232929 | 3rd Party Sign Off - Closed | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 22/07/2019 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F84104.79 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/07/2019 | 9 | 24/07/2019 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.232926 | 3rd Party Sign Off - Closed | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 22/07/2019 | 13 | 18/08/2020 | 0 | 1 | parent | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 6
F1.232922 | 3rd Party Sign Off - Closed | ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 22/07/2019 | 13 | 18/08/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.232912 | 3rd Party Sign Off - Closed | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 22/07/2019 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.232902 | 3rd Party Sign Off - Closed | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 22/07/2019 | 13 | 18/08/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F1.232893 | 3rd Party Sign Off - Closed | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 22/07/2019 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 6
F84104.78 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 22/07/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.77 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 19/07/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.76 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/07/2019 | 9 | 24/07/2019 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.453 | Closed | 1328 - Townsend St | 1328 - EHS Inspection | 19/07/2019 | 9 | 24/07/2019 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.75 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 19/07/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.74 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/07/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.93 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 25/07/2019 | 9 | 30/07/2019 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F84104.92 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 24/07/2019 | 11 | 25/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F74906.58 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 19/07/2019 | 6 | 26/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.72 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 18/07/2019 | 9 | 19/07/2019 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.71 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/07/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.70 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 18/07/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.63 | Open / Ongoing Works | Audits & Assessments>Quality Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 16/07/2019 | 10 | 16/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Open | 4
F84104.62 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 16/07/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.445 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/07/2019 | 9 | 19/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F1.230071 | JPC Sign Off / Closed | Quality Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/07/2019 | 10 | 5/9/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.61 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 16/07/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.60 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 16/07/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.59 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/07/2019 | 9 | 19/07/2019 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.58 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 15/07/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.56 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 15/07/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.68 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 17/07/2019 | 11 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F90896.2 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/07/2019 | 9 | 19/07/2019 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.67 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 17/07/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.65 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 17/07/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F84104.47 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.55 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 12/7/2019 | 6 | 26/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.54 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/7/2019 | 9 | 19/07/2019 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.442 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 11/7/2019 | 11 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.441 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 11/7/2019 | 11 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.440 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 11/7/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.439 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.438 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 11/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.437 | Closed JPC Reviewed | Site Management>JPC Project Management | QM-FRM-QC005 - Training Record | 11/7/2019 | 10 | 16/07/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F76201.428 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 10/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.427 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/7/2019 | 9 | 19/07/2019 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.46 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 9/7/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.45 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 9/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.44 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 9/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.43 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 9/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F84104.42 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 8/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.40 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 8/7/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.426 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2019 | 9 | 19/07/2019 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F84104.39 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2019 | 9 | 12/7/2019 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.38 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 8/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.36 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 8/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.35 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 5/7/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.425 | Closed | 1328 - Townsend St | 1328 - EHS Inspection | 5/7/2019 | 9 | 19/07/2019 | 0 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.34 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 5/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.33 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 5/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.53 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 15/07/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.52 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/7/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F90895.2 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/7/2019 | 9 | 22/07/2019 | 0 | 8 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F84104.51 | Closed | 1328 - Townsend St | 1328 - EHS Inspection | 12/7/2019 | 9 | 19/07/2019 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.50 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 12/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.49 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 12/7/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.435 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/7/2019 | 9 | 12/9/2019 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.434 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 10/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.424 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 4/7/2019 | 9 | 12/7/2019 | 0 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F84104.26 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 4/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.25 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 4/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.24 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 4/7/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.423 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/7/2019 | 9 | 12/7/2019 | 0 | 13 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F76201.422 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 4/7/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 3
F76201.421 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 3/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.420 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 3/7/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.419 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 3/7/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.418 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 3/7/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.22 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 3/7/2019 | 11 | 4/8/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.417 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.415 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 3/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.414 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 2/7/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.413 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/7/2019 | 9 | 12/7/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.409 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 2/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.408 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 2/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.407 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 2/7/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.406 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 2/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.53 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 1/7/2019 | 9 | 3/7/2019 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.404 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 1/7/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.401 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 28/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.18 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/06/2019 | 9 | 3/7/2019 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.400 | Closed | Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 28/06/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.398 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/06/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.397 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 28/06/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.396 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 28/06/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.395 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 27/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.394 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 27/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.393 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 27/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.392 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 27/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.369 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/06/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.17 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 25/06/2019 | 9 | 3/7/2019 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F74906.52 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 25/06/2019 | 6 | 25/06/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F74906.51 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 25/06/2019 | 6 | 26/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.367 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 25/06/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.366 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 24/06/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.365 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 24/06/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.49 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 24/06/2019 | 9 | 3/7/2019 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.359 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 24/06/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.358 | Closed | 01 Inspections>EHS Management>JPC Project Management | 1328 - EHS Inspection | 21/06/2019 | 9 | 3/7/2019 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.357 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/06/2019 | 9 | 3/7/2019 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.356 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 21/06/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.355 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 21/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.354 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 21/06/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.353 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 20/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.352 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 20/06/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.351 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 20/06/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.348 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/06/2019 | 9 | 3/7/2019 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.346 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 19/06/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.345 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 19/06/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.344 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 19/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.343 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 19/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.342 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 19/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.341 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/06/2019 | 9 | 3/7/2019 | 0 | 7 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.338 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/06/2019 | 6 | 25/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.337 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 18/06/2019 | 6 | 18/06/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.336 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 18/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.335 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 18/06/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.334 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/06/2019 | 9 | 20/06/2019 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.388 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/06/2019 | 9 | 31/07/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.386 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 27/06/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.385 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/06/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F1.221075 | Closed | 1328 - Townsend St | 1328 - EHS Inspection | 26/06/2019 | 9 | 3/7/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.381 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/06/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.380 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/06/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.379 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 26/06/2019 | 11 | 27/08/2019 | 0 | 0 | parent | FALSE | FALSE | TRUE | TRUE | 1328 | Closed | 4
F76201.378 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/06/2019 | 9 | 3/7/2019 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.377 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 26/06/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.372 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 25/06/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.326 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/06/2019 | 9 | 20/06/2019 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.323 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/06/2019 | 9 | 20/06/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.322 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-110 Concreting Inspection (In Situ) | 14/06/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F84104.16 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/06/2019 | 9 | 20/06/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.321 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 12/6/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.320 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 12/6/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.319 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 12/6/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.318 | Closed | Site Management>JPC Project Management | 1328 - EHS Inspection | 12/6/2019 | 9 | 20/06/2019 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.316 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 12/6/2019 | 6 | 25/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.12 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | 1328 CM-SM-FRM-001 Site Diary | 11/6/2019 | 6 | 25/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.48 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2019 | 9 | 3/7/2019 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F74906.46 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2019 | 9 | 20/06/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.300 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2019 | 9 | 20/06/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.299 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 11/6/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F76201.296 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 11/6/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.294 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 10/6/2019 | 6 | 13/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.292 | Closed JPC Sign Off | Foundations>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 10/6/2019 | 11 | 4/8/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.291 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 10/6/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.290 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 7/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.289 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 7/6/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.288 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 7/6/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.287 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/6/2019 | 9 | 10/6/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.286 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 6/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.284 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/6/2019 | 9 | 10/6/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.282 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 6/6/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.280 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 6/6/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.279 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 6/6/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.276 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 5/6/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F74906.45 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 5/6/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.275 | JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 5/6/2019 | 10 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F74906.44 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F74906.43 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.42 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.41 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.39 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.38 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.37 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.36 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.273 | Completed and signed off | 03 Safety Notices>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/6/2019 | 9 | 10/6/2019 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F74906.35 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.34 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.33 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.32 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.31 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.30 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.29 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.28 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.27 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.26 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.25 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.24 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.23 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.22 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.21 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.272 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.271 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.270 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.269 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.268 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.267 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.266 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.265 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.264 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.263 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.262 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.260 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.259 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.258 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.256 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.253 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.252 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.250 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 4/6/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.248 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 4/6/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.247 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/6/2019 | 9 | 6/6/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.245 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 31/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.244 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 31/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.243 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 31/05/2019 | 9 | 6/6/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.242 | Closed JPC Reviewed | QC Training Records>Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 31/05/2019 | 10 | 5/9/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.237 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 30/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.235 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 30/05/2019 | 9 | 6/6/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.234 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.233 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.232 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.231 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.230 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.229 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.228 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.227 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.226 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.225 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.224 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 4
F76201.223 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.222 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.221 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.220 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.219 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.218 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.217 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.216 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.215 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.214 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.213 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/05/2019 | 11 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.11 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 29/05/2019 | 9 | 6/6/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.212 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/05/2019 | 9 | 6/6/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.211 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/05/2019 | 9 | 6/6/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.210 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 28/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F74906.20 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 28/05/2019 | 9 | 6/6/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.209 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 27/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.208 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/05/2019 | 9 | 30/05/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.207 | Closed JPC Sign Off | Site Management>JPC Project Management | QM-CL-CS-116 Concrete Cube Record | 24/05/2019 | 11 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.206 | Closed JPC Sign Off | Site Management>JPC Project Management | QM-CL-CS-116 Concrete Cube Record | 24/05/2019 | 11 | 6/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.205 | Closed JPC Sign Off | Site Management>JPC Project Management | QM-CL-CS-116 Concrete Cube Record | 24/05/2019 | 11 | 6/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.204 | Closed | 1328 - Townsend St | EHS Inspection. | 24/05/2019 | 9 | 31/05/2019 | 0 | 7 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F76201.201 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 23/05/2019 | 11 | 30/07/2019 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.197 | Closed JPC Sign Off | 03 Material Deliveries>Site Management>JPC Project Management | QM-CL-CS-116 Concrete Cube Record | 23/05/2019 | 11 | 8/8/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.196 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 23/05/2019 | 9 | 30/05/2019 | 0 | 13 | parent | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 2
F76201.195 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 23/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.193 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 23/05/2019 | 9 | 30/05/2019 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.192 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 22/05/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.190 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 22/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F74906.18 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 21/05/2019 | 9 | 30/05/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.189 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 21/05/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.180 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/05/2019 | 9 | 30/05/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.179 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 21/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.177 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 20/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.176 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 17/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.175 | Closed | 1328 - Townsend St | EHS Inspection. | 17/05/2019 | 9 | 30/05/2019 | 0 | 7 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.174 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/05/2019 | 9 | 22/05/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.173 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 17/05/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.172 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 17/05/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.171 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 17/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.170 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/05/2019 | 9 | 22/05/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.166 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 16/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.164 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 16/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.163 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 15/05/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.162 | Closed JPC Reviewed | JPC Project Management | QM-FRM-CS-104 Material Movement Record | 15/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.161 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/05/2019 | 9 | 16/05/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.160 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 14/05/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.158 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 14/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.157 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 13/05/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.150 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 13/05/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.149 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 13/05/2019 | 9 | 16/05/2019 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.148 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 13/05/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.135 | Closed | 1328 - Townsend St | EHS Inspection. | 10/5/2019 | 9 | 22/05/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.134 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 10/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.133 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 10/5/2019 | 9 | 16/05/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.132 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/5/2019 | 9 | 16/05/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.131 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 9/5/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.130 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 9/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.129 | Closed JPC Sign Off | Piling>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 8/5/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F1.200429 | Opened | Site Management>JPC Project Management | SM-FRM-005 Permit to Enter | 8/5/2019 | 6 | 8/5/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Open | 3
F76201.128 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/5/2019 | 9 | 16/05/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.126 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.125 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F74906.56 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/07/2019 | 11 | 15/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F74906.57 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 16/07/2019 | 11 | 15/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.130 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/8/2019 | 11 | 24/09/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.328 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 18/06/2019 | 11 | 30/07/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.329 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 18/06/2019 | 11 | 30/07/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.330 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 18/06/2019 | 11 | 30/07/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.331 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 18/06/2019 | 11 | 30/07/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.332 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 18/06/2019 | 11 | 30/07/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.333 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 18/06/2019 | 11 | 30/07/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.370 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 25/06/2019 | 11 | 20/08/2019 | 0 | 0 | child | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F76201.371 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 25/06/2019 | 11 | 20/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.373 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 25/06/2019 | 11 | 20/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.374 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 25/06/2019 | 11 | 20/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.375 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 25/06/2019 | 11 | 20/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.376 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 25/06/2019 | 11 | 27/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.389 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 27/06/2019 | 11 | 23/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.399 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 28/06/2019 | 11 | 23/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.405 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 1/7/2019 | 11 | 27/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.411 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 2/7/2019 | 11 | 7/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.412 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 2/7/2019 | 11 | 27/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.416 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 3/7/2019 | 11 | 15/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.429 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.430 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.431 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.432 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.433 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.436 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/7/2019 | 11 | 12/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.462 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 30/07/2019 | 11 | 30/07/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.463 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 30/07/2019 | 11 | 30/07/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.464 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 30/07/2019 | 11 | 30/07/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.472 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 9/8/2019 | 11 | 8/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F84104.66 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/07/2019 | 11 | 15/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.69 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 18/07/2019 | 11 | 15/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.73 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 19/07/2019 | 11 | 20/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.80 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/07/2019 | 11 | 20/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.23 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 4/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.81 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/07/2019 | 11 | 20/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.91 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 24/07/2019 | 11 | 23/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.94 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 25/07/2019 | 11 | 23/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.104 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 29/07/2019 | 11 | 27/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.106 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 29/07/2019 | 11 | 27/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.107 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 29/07/2019 | 11 | 27/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.108 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 29/07/2019 | 11 | 27/09/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.109 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 29/07/2019 | 11 | 27/09/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.27 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 5/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.113 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 30/07/2019 | 11 | 27/09/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.114 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 30/07/2019 | 11 | 27/09/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.119 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/8/2019 | 11 | 27/09/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.120 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 1/8/2019 | 11 | 27/09/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.28 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 5/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.131 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/8/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.132 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/8/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.133 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/8/2019 | 11 | 31/03/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.135 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 8/8/2019 | 11 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.29 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 5/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.146 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 12/8/2019 | 11 | 8/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.145 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 12/8/2019 | 11 | 8/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.30 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 5/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.152 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 14/08/2019 | 11 | 8/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.151 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 14/08/2019 | 11 | 8/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.153 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 14/08/2019 | 11 | 8/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.31 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 5/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.158 | Closed JPC Sign Off | Basement Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/08/2019 | 11 | 11/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.32 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 5/7/2019 | 11 | 8/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.164 | Closed | JPC Project Management | SM-FRM-008 Cause & Effect Record | 19/08/2019 | 6 | 19/08/2019 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F84104.167 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 20/08/2019 | 11 | 11/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.168 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 20/08/2019 | 11 | 24/09/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.169 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 20/08/2019 | 11 | 16/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.170 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 20/08/2019 | 11 | 16/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.171 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 20/08/2019 | 11 | 16/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.174 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 20/08/2019 | 11 | 16/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.177 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 21/08/2019 | 11 | 16/10/2019 | 0 | 0 | child | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.178 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 21/08/2019 | 11 | 16/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.184 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/08/2019 | 11 | 15/11/2019 | 0 | 0 | child | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 4
F84104.185 | Closed JPC Sign Off | Foundations>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 22/08/2019 | 11 | 2/4/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.193 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 23/08/2019 | 11 | 21/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.196 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 26/08/2019 | 11 | 23/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.197 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 26/08/2019 | 11 | 23/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.198 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 26/08/2019 | 11 | 23/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.199 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 26/08/2019 | 11 | 23/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.200 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 26/08/2019 | 11 | 23/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.202 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/08/2019 | 11 | 23/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.205 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/08/2019 | 11 | 8/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.206 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 27/08/2019 | 11 | 23/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.214 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 29/08/2019 | 11 | 23/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.228 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 3/9/2019 | 11 | 30/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.229 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 3/9/2019 | 11 | 30/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.230 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 3/9/2019 | 11 | 30/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.231 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 3/9/2019 | 11 | 30/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.232 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 3/9/2019 | 11 | 30/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.236 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 4/9/2019 | 11 | 30/10/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.245 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 6/9/2019 | 11 | 7/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.256 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 10/9/2019 | 11 | 7/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.262 | Closed JPC Sign Off | Ground Floor Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 11/9/2019 | 11 | 7/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.263 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 11/9/2019 | 11 | 7/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.271 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 12/9/2019 | 11 | 7/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.273 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 13/09/2019 | 11 | 7/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.274 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 13/09/2019 | 11 | 7/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.280 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 17/09/2019 | 11 | 8/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.48 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 12/7/2019 | 11 | 12/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.299 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 19/09/2019 | 11 | 15/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.300 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 19/09/2019 | 11 | 15/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.308 | Closed JPC Sign Off | Ground Floor Plan>Block 3>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 20/09/2019 | 11 | 15/11/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.54 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/07/2019 | 11 | 12/8/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F84104.55 | Closed JPC Sign Off | Basement Plan>Block 4>ITP 01 Structural>QC & BC(A)R | 1328 QM-CL-CS-116 Concrete Cube Record | 15/07/2019 | 11 | 15/08/2019 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.124 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.123 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.120 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.119 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.116 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.111 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.110 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/5/2019 | 9 | 10/5/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.109 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 8/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F1.199599 | In Process / Manufactor | ITP 02 Architectural & M&E Services>QC & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 7/5/2019 | 10 | 7/5/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Open | 4
F76201.104 | Closed | 1328 - Townsend St | EHS Inspection. | 3/5/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.103 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/5/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F74906.17 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 3/5/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.101 | Closed JPC Sign Off | Piling>Block 1>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 2/5/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.100 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | QM-FRM-CS-104 Material Movement Record | 2/5/2019 | 11 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 4
F76201.99 | Closed JPC Sign Off | Piling>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 1/5/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F74906.16 | Closed JPC Reviewed | 1328 - Townsend St | SM-FRM-001 Site Diary | 1/5/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.98 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 30/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.97 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 30/04/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.96 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 30/04/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F1.196549 | Permit to Unload / Dismantle (Closed) | 1328 - Townsend St | CM-EHS-FRM-003 Temporary Works / Permit to Load | 29/04/2019 | 9 | 29/04/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.95 | Closed JPC Sign Off | Piling>Block 2>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 29/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.94 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 26/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.93 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 25/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.92 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/04/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.89 | Closed | 1328 - Townsend St | EHS Inspection. | 25/04/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.88 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 25/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.87 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/04/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.86 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 23/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 4
F76201.85 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 23/04/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.84 | Closed | 1328 - Townsend St | EHS Inspection. | 19/04/2019 | 9 | 8/5/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.83 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 18/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.79 | Closed JPC Sign Off | Piling>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 18/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.78 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 18/04/2019 | 9 | 16/05/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.76 | Closed JPC Sign Off | Piling>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 16/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.75 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/04/2019 | 9 | 16/05/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.70 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/04/2019 | 9 | 16/05/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.69 | Closed JPC Sign Off | Piling>Block 4>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 15/04/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.68 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/04/2019 | 9 | 16/05/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.67 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/04/2019 | 9 | 16/05/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.66 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/04/2019 | 9 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.65 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 12/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.63 | Closed | 1328 - Townsend St | EHS Inspection. | 12/4/2019 | 9 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.62 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 12/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.61 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 10/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.58 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 10/4/2019 | 9 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.56 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 9/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.55 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 9/4/2019 | 9 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.53 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 8/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.52 | Completed and signed off | 1328 - Townsend St | EHS Managment Inspection - Daily | 8/4/2019 | 9 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F74906.15 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 5/4/2019 | 6 | 31/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.13 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 5/4/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.12 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 5/4/2019 | 6 | 31/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.48 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 5/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.46 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 5/4/2019 | 9 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.45 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 4/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F74906.11 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/4/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.10 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/4/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.44 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 3/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.43 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/4/2019 | 9 | 22/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.42 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 2/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F76201.41 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 2/4/2019 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1328 | Closed | 4
F74906.9 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/4/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.33 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/4/2019 | 9 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F74906.8 | Closed JPC Reviewed | 1328 - Townsend St | SM-FRM-001 Site Diary | 1/4/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.3 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/4/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74906.2 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/4/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 3
F76201.27 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/03/2019 | 9 | 28/03/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 2
F76201.26 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/03/2019 | 9 | 19/07/2019 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1328 | Closed | 2
F76201.25 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/03/2019 | 9 | 19/07/2019 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1328 | Closed | 2
F76201.23 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/03/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74905.4 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 8/3/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F74905.3 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 8/3/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1328 | Closed | 3
F76201.7 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 6/3/2019 | 11 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F76201.6 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/3/2019 | 6 | 24/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1328 | Closed | 3
F76201.3 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 26/02/2019 | 11 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1328 | Closed | 4
F76201.2 | Closed JPC Sign Off | Piling>Block 3>ITP 01 Structural>QC & BC(A)R | QM-CL-CS-105 Piling Inspection | 26/02/2019 | 11 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1328 | Closed | 4
F102314.114 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/09/2020 | 9 | 14/09/2020 | 4 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.457 | Open / Ongoing Works | 04 Staturatury Forms>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/9/2020 | 9 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F134609.76 | Open | Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 11/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F133598.105 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F102314.113 | Opened | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 11/9/2020 | 9 | 11/9/2020 | 9 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F92677.453 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 11/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.104 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F102314.112 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/9/2020 | 9 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F92677.452 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F102314.110 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/9/2020 | 9 | 10/9/2020 | 1 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F92677.451 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.450 | Open / Ongoing Works | Lvl 01 Floor Plan>Block 21>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.103 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F102314.108 | Closed | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 9/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.102 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 9/9/2020 | 9 | 9/9/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F92677.449 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/9/2020 | 11 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.448 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.447 | Closed | 04 Staturatury Forms>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 8/9/2020 | 1 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F133598.101 | Open / Ongoing Works | 04 Staturatury Forms>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F133598.100 | Open / Ongoing Works | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 8/9/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F133598.99 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.446 | Open / Ongoing Works | Lvl 03 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | 1329 - Interspan QM-CL-CS-110 Concreting Inspection (In Situ) - V1 | 8/9/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.445 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.444 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/9/2020 | 9 | 7/9/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F133598.98 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.443 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.442 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.441 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F102314.107 | Opened | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 4/9/2020 | 9 | 4/9/2020 | 1 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F102314.106 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 4/9/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F133598.97 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.440 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 4/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.439 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 4/9/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F129164.21 | Open | 1329 - 19-22 Kildare Street | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 4/9/2020 | 9 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F92677.438 | Open / Ongoing Works | Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 4/9/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.437 | Open / Ongoing Works | Block 20 - Rear Office - 20.3.03>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 4/9/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.436 | Open / Ongoing Works | Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 4/9/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.435 | JPC Sign Off / Closed | Block 19 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 4/9/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.434 | Open / Ongoing Works | Lvl 02 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 4/9/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.433 | Open / Ongoing Works | Lvl 01 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 4/9/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.432 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.456 | Open / Ongoing Works | 04 Staturatury Forms>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 3/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F133598.96 | Open / Ongoing Works | 04 Staturatury Forms>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 3/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F92677.431 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.430 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.429 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/9/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.455 | Open / Ongoing Works | Block 21 - Rear Office - 21.2.03>Lvl 02 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225 Firestopping Inspection Checklist | 3/9/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.428 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/9/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.454 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.427 | Open / Ongoing Works | Lvl 02 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 3/9/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.426 | JPC Inspected | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 3/9/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.425 | JPC Inspected | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 3/9/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F102314.105 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F102314.104 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 2/9/2020 | 9 | 3/9/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.453 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.424 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/9/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.423 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/9/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.422 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.421 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.420 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.419 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/9/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.418 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/9/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.417 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.452 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 1/9/2020 | 9 | 2/9/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.450 | Opened | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 1/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F1.483075 | Open / Ongoing Works | Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.449 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.448 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.416 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 1/9/2020 | 11 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F129164.20 | Opened | 1329 - 19-22 Kildare Street | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 1/9/2020 | 9 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F133598.95 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 31/08/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F133598.94 | Open / Ongoing Works | 04 Staturatury Forms>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.447 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.415 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 31/08/2020 | 11 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F102314.103 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F92677.414 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.413 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/08/2020 | 9 | 3/9/2020 | 1 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.446 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.412 | JPC Sign Off / Closed | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 28/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.411 | Open / Ongoing Works | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 28/08/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.410 | Open / Ongoing Works | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 28/08/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.409 | Open / Ongoing Works | Lvl 04 Roof Plan>Block 19>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 28/08/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.408 | JPC Inspected | Lvl 02 Floor Plan>Block 20>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 28/08/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.407 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 28/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.102 | Opened | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 27/08/2020 | 9 | 3/9/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.441 | Open / Ongoing Works | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 27/08/2020 | 9 | 8/9/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.440 | Opened | EHS Management>JPC Project Management | EHS Inspection. | 27/08/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.436 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.406 | Open / Ongoing Works | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/08/2020 | 11 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.405 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 27/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.101 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/08/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.435 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.434 | Closed | 04 Staturatury Forms>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 26/08/2020 | 9 | 26/08/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.404 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 26/08/2020 | 11 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.403 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.100 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 25/08/2020 | 9 | 25/08/2020 | 4 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F92677.402 | Open / Ongoing Works | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | 1329 - Interspan QM-CL-CS-110 Concreting Inspection (In Situ) - V1 | 25/08/2020 | 11 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Open | 4
F92677.401 | Rejected / Action Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 25/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.432 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.400 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.399 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 25/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F102314.99 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 24/08/2020 | 9 | 24/08/2020 | 4 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.431 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.97 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 24/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F92677.398 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 24/08/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.397 | Test Results Required | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 24/08/2020 | 11 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F102314.96 | Opened | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 21/08/2020 | 9 | 21/08/2020 | 4 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F133598.91 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 21/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.396 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 21/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.395 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 21/08/2020 | 9 | 21/08/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.394 | Open / Ongoing Works | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 21/08/2020 | 9 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.430 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.95 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/08/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F133598.89 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/08/2020 | 9 | 26/08/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F134609.75 | Open | Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F91214.427 | Opened | EHS Management>JPC Project Management | EHS Inspection. | 20/08/2020 | 9 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.425 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.424 | Open / Ongoing Works | Lvl 04 Roof Plan>Block 20>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.423 | Open / Ongoing Works | Lvl 04 Roof Plan>Block 22>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.422 | Open / Ongoing Works | Lvl 04 Roof Plan>Block 21>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.391 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.94 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/08/2020 | 9 | 26/08/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.421 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.471886 | JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F1.471841 | JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F1.471814 | JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F1.471798 | JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F92677.390 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/08/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.389 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 19/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.420 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.388 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 18/08/2020 | 9 | 18/08/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.387 | Closed | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 18/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.386 | Permit to Load Signed Off | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | CM-EHS-FRM-003 Temporary Works / Permit to Load | 18/08/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 |  | 2
F92677.385 | Test Results Required | Lvl 02 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | 1329 - Interspan QM-CL-CS-110 Concreting Inspection (In Situ) - V1 | 18/08/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Open | 4
F92677.384 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 18/08/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.469246 | In Process / Manufactor | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F1.469228 | In Process / Manufactor | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F1.469215 | In Process / Manufactor | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.383 | Test Results Required | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 17/08/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F1.469162 | Open / Ongoing Works | Lvl 02 Floor Plan>Block 21>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F1.469141 | Works Complete / Resolved | Lvl 04 Roof Plan>Block 19>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/08/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Open | 4
F102314.93 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/08/2020 | 9 | 26/08/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.469111 | JPC Sign Off | Block 19 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/08/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F1.469076 | JPC Sign Off | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/08/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F102314.92 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 17/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F92677.382 | Test Results Required | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 17/08/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.381 | Test Results Required | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 17/08/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.380 | Test Results Required | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 17/08/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.419 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F129164.19 | Open | 1329 - 19-22 Kildare Street | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 17/08/2020 | 9 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F129164.18 | Open | 1329 - 19-22 Kildare Street | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 17/08/2020 | 9 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F92677.379 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 17/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.91 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 14/08/2020 | 9 | 26/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.418 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/08/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F133598.88 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/08/2020 | 9 | 14/08/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.467643 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.417 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.90 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/08/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.416 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.378 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 13/08/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.377 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 13/08/2020 | 6 | 13/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.89 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/8/2020 | 9 | 26/08/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F133598.87 | Open / Ongoing Works | Lvl 02 Floor Plan>Block 19>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 12/8/2020 | 11 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.86 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.376 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.375 | Works Complete / Resolved | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/8/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.374 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F133598.84 | Open / Ongoing Works | Block 19 - Toilets - 19.3.02>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225 Firestopping Inspection Checklist | 11/8/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.83 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | QM-CL-ARC-225 Firestopping Inspection Checklist | 11/8/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.373 | Works Complete / Resolved | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 11/8/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.415 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F92677.372 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/8/2020 | 9 | 11/8/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.371 | Test Results Required | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 11/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.370 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 11/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.369 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 11/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F133598.82 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/8/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.368 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 11/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.367 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.366 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.365 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.364 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.414 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.413 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/8/2020 | 9 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.88 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 10/8/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F133598.79 | Open / Ongoing Works | Block 21 - Front Office - 21.3.01>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225 Firestopping Inspection Checklist | 10/8/2020 | 8 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F133598.78 | Open / Ongoing Works | Block 19 - Front Office - 19.3.01>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225 Firestopping Inspection Checklist | 10/8/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.77 | Works Complete / Resolved | Lvl 03 Floor Plan>Block 19>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 10/8/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.76 | Works Complete / Resolved | Lvl 03 Floor Plan>Block 19>Existing Buildings>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 10/8/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.75 | Open | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 10/8/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F133598.73 | Open / Ongoing Works | Block 21 - Front Office - 21.2.01>Lvl 02 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 10/8/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.72 | JPC Sign Off / Closed | Block 21 - Front Office - 21.3.01>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 10/8/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F133598.71 | JPC Inspected | Block 19 - Front Office - 19.3.01>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 10/8/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.363 | Test Results Required | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.69 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/8/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.362 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.361 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 10/8/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.68 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.67 | JPC Inspected | Block 19 - Front Office - 19.3.01>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 7/8/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.65 | Open / Ongoing Works | Block 19 - Front Office - 19.3.01>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-214 Timber Sprung Floor Inspection | 7/8/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F133598.63 | Open / Ongoing Works | Block 19 - Front Office - 19.3.01>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-214 Timber Sprung Floor Inspection | 7/8/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F133598.62 | Open / Ongoing Works | Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-214 Timber Sprung Floor Inspection | 7/8/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F133598.61 | Open / Ongoing Works | Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-214 Timber Sprung Floor Inspection | 7/8/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F133598.60 | Open / Ongoing Works | Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-214 Timber Sprung Floor Inspection | 7/8/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.412 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.360 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 7/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.359 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 7/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.358 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.87 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 6/8/2020 | 9 | 26/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F133598.59 | Opened | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F133598.58 | Open / Ongoing Works | 04 Staturatury Forms>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 6/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.411 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.57 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F133598.55 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/8/2020 | 9 | 5/8/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.357 | Permit to Load Signed Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | CM-EHS-FRM-003 Temporary Works / Permit to Load | 5/8/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 |  | 2
F102314.86 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.458435 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | QM-FRM-QC-001 Benchmark / Sample Form | 5/8/2020 | 10 | 5/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F133598.54 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.356 | Closed JPC Sign Off | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 5/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.355 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.409 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.354 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/8/2020 | 9 | 4/8/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F129164.16 | Open / Ongoing Works | JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 4/8/2020 | 10 | 4/8/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F129164.15 | Open / Ongoing Works | JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 4/8/2020 | 10 | 4/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F129164.14 | Opened | 1329 - 19-22 Kildare Street | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 4/8/2020 | 9 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F133598.53 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.85 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 31/07/2020 | 9 | 26/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F129164.13 | Opened | 1329 - 19-22 Kildare Street | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 31/07/2020 | 9 | 31/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.408 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/07/2020 | 6 | 31/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.407 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 31/07/2020 | 9 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F102314.84 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 31/07/2020 | 6 | 31/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F92677.353 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 31/07/2020 | 6 | 31/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.83 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 30/07/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F102314.82 | Open / Ongoing Works | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-008 Daily Site Access Register | 30/07/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F133598.52 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F102314.81 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 30/07/2020 | 9 | 26/08/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F133598.51 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F134609.74 | Open | Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 30/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.352 | Test Results Required | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | 1329 - Interspan QM-CL-CS-110 Concreting Inspection (In Situ) - V1 | 30/07/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Open | 4
F92677.351 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 30/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.50 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 29/07/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.406 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.49 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.350 | Open / Ongoing Works | JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F92677.349 | Test Results Required | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 29/07/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.348 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.347 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F133598.48 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/07/2020 | 6 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F129164.12 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 28/07/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.346 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 28/07/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.345 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 28/07/2020 | 6 | 28/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.80 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/07/2020 | 9 | 26/08/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F133598.47 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/07/2020 | 6 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F102314.79 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 24/07/2020 | 9 | 26/08/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F129164.17 | Open / Ongoing Works | JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 4/8/2020 | 10 | 4/8/2020 | 0 | 0 | child | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F102314.78 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/07/2020 | 9 | 26/08/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.405 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.46 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F102314.77 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F92677.344 | JPC Inspected | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 24/07/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.343 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.45 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F134609.73 | Closed JPC Reviewed | New Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.72 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.71 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.70 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.69 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.68 | Closed JPC Reviewed | Roof Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.67 | Closed JPC Reviewed | Roof Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.76 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/07/2020 | 9 | 26/08/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.342 | Test Results Required | Lvl 01 Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | 1329 - Interspan QM-CL-CS-110 Concreting Inspection (In Situ) - V1 | 23/07/2020 | 11 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Open | 4
F92677.341 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 23/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.340 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.404 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/07/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 2
F133598.44 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F91214.403 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.339 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 22/07/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.338 | Permit to Unload / Dismantle (Closed) | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | CM-EHS-FRM-003 Temporary Works / Permit to Load | 22/07/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 2
F92677.337 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.43 | Opened | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/07/2020 | 9 | 21/07/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F134609.66 | Closed JPC Reviewed | Basement>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.65 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.64 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.63 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.62 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.443130 | Closed JPC Reviewed | New Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.75 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/07/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.336 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.335 | Test Results Required | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/07/2020 | 11 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.402 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.61 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.60 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.59 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.58 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.57 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.56 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.55 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.54 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.334 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.333 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 21/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.401 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/07/2020 | 9 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.400 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.442136 | Closed JPC Reviewed | Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.42 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F133598.41 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F1.441566 | In Process / Manufactor | 1329 - 19-22 Kildare Street | QM-FRM-QC-002 Off Site Inspection | 20/07/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1329 | Open | 4
F92677.332 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 20/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.399 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.398 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/07/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F133598.40 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.331 | JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.330 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 17/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.329 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.328 | Open | ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 3
F102314.74 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 16/07/2020 | 9 | 26/08/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.327 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/07/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F134609.53 | Closed JPC Reviewed | Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F133598.39 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F102314.73 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 16/07/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.326 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F102314.72 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/07/2020 | 9 | 26/08/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.325 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/07/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.324 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.323 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/07/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.322 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F129164.9 | In Process / Manufactor | Quality Control & BC(A)R | QM-FRM-QC-002B Off Site Inspection - Windows | 15/07/2020 | 10 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.397 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/07/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F133598.37 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.396 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.71 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/07/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F133598.36 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.394 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.393 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.321 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 14/07/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.392 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/07/2020 | 9 | 26/08/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.319 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 14/07/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.318 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 14/07/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.317 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 14/07/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.316 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 14/07/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.315 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 14/07/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.314 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/07/2020 | 9 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F133598.33 | Opened | JPC Project Management | EHS Inspection. | 13/07/2020 | 9 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F133598.32 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.313 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 13/07/2020 | 9 | 13/07/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F129164.5 | Open | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 13/07/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F129164.4 | Open | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 13/07/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F92677.312 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 13/07/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.311 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 13/07/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.310 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 13/07/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F133598.31 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F1.434451 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | JPC-QA-RP-003 - Site Audit Report | 10/7/2020 | 2 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1329 | Open | 3
F92677.309 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/7/2020 | 11 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.308 | Closed JPC Reviewed | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.70 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 9/7/2020 | 9 | 26/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.307 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/7/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.306 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/7/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F133598.30 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.305 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/7/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F134609.52 | Closed JPC Reviewed | Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 9/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.304 | Closed | JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.303 | Closed | JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.302 | Closed | JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.301 | Closed | JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.300 | Test Results Required | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/7/2020 | 11 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.299 | Closed JPC Reviewed | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.28 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.69 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2020 | 9 | 13/07/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.391 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F134609.51 | Open / Ongoing Works | Block 19 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 8/7/2020 | 11 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.50 | Open / Ongoing Works | Block 21 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 8/7/2020 | 11 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.49 | Open / Ongoing Works | Block 22 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 8/7/2020 | 11 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.27 | Open / Ongoing Works | Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 8/7/2020 | 11 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.298 | Closed JPC Reviewed | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 8/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.68 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 7/7/2020 | 9 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.297 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 7/7/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F133598.23 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.390 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.389 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/7/2020 | 9 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F134609.48 | Closed JPC Reviewed | Basement>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.47 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.46 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.45 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.44 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.43 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.42 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.41 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.40 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.39 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.38 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.37 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.36 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.35 | Closed JPC Reviewed | Basement>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.34 | Closed JPC Reviewed | Basement>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.33 | Closed JPC Reviewed | Basement>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.32 | Closed JPC Reviewed | Basement>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.31 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.30 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.29 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.28 | Closed JPC Reviewed | Ground Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.27 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.26 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.25 | Closed JPC Reviewed | First Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.296 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 7/7/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.295 | Completed and signed off | New Building>ITP 01 Structural>Quality Control & BC(A)R | EHS Managment Inspection - Daily | 7/7/2020 | 9 | 7/7/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.294 | Closed JPC Reviewed | New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 7/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.67 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 6/7/2020 | 9 | 7/7/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.387 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.386 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/7/2020 | 9 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F133598.22 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F134609.24 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 6/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.23 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 6/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.22 | Closed JPC Reviewed | Second Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 6/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.20 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 6/7/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.19 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 6/7/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F134609.18 | Closed JPC Reviewed | Third Floor>Existing Building>Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 6/7/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.293 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 6/7/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.385 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.384 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/7/2020 | 9 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F133598.21 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F133598.20 | JPC Sign Off / Closed | Block 21 - Front Office - 21.3.01>Lvl 03 Floor Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-214 Timber Sprung Floor Inspection | 3/7/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.292 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/7/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.291 | Closed JPC Reviewed | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 3/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.18 | Open / Ongoing Works | JPC Project Management | SM-FRM-001 Daily Site Diary | 2/7/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F92677.290 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F133556.2 | Closed JPC Reviewed | Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 2/7/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.289 | Permit to Unload / Dismantle (Closed) | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | CM-EHS-FRM-003 Temporary Works / Permit to Load | 2/7/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.383 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.382 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 1/7/2020 | 9 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.288 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | 1329 - Interspan QM-CL-CS-110 Concreting Inspection (In Situ) - V1 | 1/7/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F134609.16 | Open / Ongoing Works | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.15 | JPC Sign Off / Closed | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F134609.13 | Open / Ongoing Works | Block 20 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.11 | Open / Ongoing Works | Block 19 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.10 | JPC Sign Off / Closed | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F134609.9 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.7 | Works Complete / Resolved | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.6 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.5 | JPC Sign Off / Closed | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F134609.4 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.3 | JPC Sign Off / Closed | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F134609.2 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F134609.1 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 1/7/2020 | 11 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.287 | Closed JPC Reviewed | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F129164.3 | Closed | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 30/06/2020 | 9 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.381 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 30/06/2020 | 9 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.380 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.15 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.286 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 30/06/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.285 | Closed JPC Reviewed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.284 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 29/06/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.379 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.378 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/06/2020 | 9 | 30/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F133598.12 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.283 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 26/06/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.282 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 26/06/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.377 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/06/2020 | 9 | 29/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.376 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/06/2020 | 6 | 29/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F133598.11 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F133556.1 | Closed JPC Reviewed | Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 25/06/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.281 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 25/06/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.375 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.421048 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-002 Progress Record | 25/06/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1329 | Closed | 3
F133598.9 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 25/06/2020 | 9 | 13/07/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F133598.8 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/06/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 3
F91214.374 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/06/2020 | 9 | 25/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.280 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.373 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/06/2020 | 9 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.372 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F133598.7 | Open / Ongoing Works | Block 19 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 24/06/2020 | 11 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F133598.6 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | QM-CL-CS-115 Timber Structural Inspection | 24/06/2020 | 11 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F133598.5 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | QM-CL-CS-115 Timber Structural Inspection | 24/06/2020 | 11 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F133598.4 | Open | Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 24/06/2020 | 10 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.279 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 24/06/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.278 | Closed JPC Reviewed | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 24/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.277 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 23/06/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F133598.2 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 23/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.371 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.370 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/06/2020 | 9 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.276 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 23/06/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.275 | Closed JPC Reviewed | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 23/06/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.66 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/06/2020 | 9 | 13/07/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.274 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 22/06/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.273 | Permit to Unload / Dismantle (Closed) | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | CM-EHS-FRM-003 Temporary Works / Permit to Load | 22/06/2020 | 9 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.272 | Closed JPC Sign Off | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | 1329 - Interspan QM-CL-CS-110 Concreting Inspection (In Situ) - V1 | 22/06/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F102314.65 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 19/06/2020 | 9 | 7/7/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F129164.2 | Open | 1329 - 19-22 Kildare Street | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 19/06/2020 | 9 | 19/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F92677.271 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/06/2020 | 11 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.369 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/06/2020 | 9 | 23/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.368 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.270 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 19/06/2020 | 6 | 19/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.268 | Open / Ongoing Works | Block 20 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 18/06/2020 | 11 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.267 | Open / Ongoing Works | Block 20 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 18/06/2020 | 11 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.266 | Open / Ongoing Works | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 18/06/2020 | 11 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.265 | Works Complete / Resolved | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 18/06/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.264 | Open / Ongoing Works | Block 19 - Roof>Lvl 04 Roof Plans>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-115 Timber Structural Inspection | 18/06/2020 | 11 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.263 | Closed | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 18/06/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F91214.367 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.262 | Closed JPC Reviewed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 18/06/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.366 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.365 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/06/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.261 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 17/06/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.364 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.363 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/06/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.260 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/06/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.259 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/06/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.258 | Open / Ongoing Works | Site Management>JPC Project Management | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/06/2020 | 11 | 16/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.362 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/06/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.257 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 15/06/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.361 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/06/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.255 | Closed JPC Reviewed | Lvl 00 Ground Floor Plan>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 15/06/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.360 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.64 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 12/6/2020 | 9 | 7/7/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.254 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/6/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F102314.63 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.359 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.358 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.253 | Closed JPC Reviewed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 12/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.357 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.62 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.252 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 11/6/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.251 | Test Results Required | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 11/6/2020 | 11 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.356 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.355 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.61 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 10/6/2020 | 9 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.250 | Closed JPC Reviewed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 10/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.60 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 9/6/2020 | 9 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.249 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/6/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.248 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/6/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.354 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.247 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/6/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.353 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.352 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.246 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 9/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.407069 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 8/6/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.59 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 8/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.245 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 8/6/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.244 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 8/6/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F102314.58 | Closed | 1329 - 19-22 Kildare Street | EHS Inspection. | 5/6/2020 | 9 | 13/07/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.57 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 5/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.243 | JPC Sign Off / Closed | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 5/6/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.242 | JPC Sign Off / Closed | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 5/6/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.241 | JPC Sign Off / Closed | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 5/6/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.240 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/6/2020 | 9 | 5/6/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.239 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/6/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.56 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 4/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.351 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/6/2020 | 9 | 4/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.238 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/6/2020 | 6 | 4/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.350 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/6/2020 | 6 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.237 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 4/6/2020 | 11 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.236 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 4/6/2020 | 11 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.235 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 4/6/2020 | 11 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Open | 4
F91214.349 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/6/2020 | 9 | 3/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.348 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 3/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.55 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 3/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.234 | Closed JPC Reviewed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 3/6/2020 | 6 | 3/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.346 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/6/2020 | 6 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.345 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/6/2020 | 9 | 3/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.54 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 2/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.233 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/6/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.232 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/6/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.231 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 2/6/2020 | 11 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.230 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 2/6/2020 | 11 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.229 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/6/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.344 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/05/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.343 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/05/2020 | 9 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.53 | Closed | 1329 - 19-22 Kildare Street | EHS Inspection. | 29/05/2020 | 9 | 5/6/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.52 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 29/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.228 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 29/05/2020 | 6 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.342 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/05/2020 | 9 | 28/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.341 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/05/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.400137 | JPC Sign Off | 1329 - 19-22 Kildare Street | QM-FRM-QC-001 Benchmark / Sample Form | 28/05/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F102314.51 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 28/05/2020 | 9 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F92677.227 | Closed JPC Reviewed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 28/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.339 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 28/05/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.226 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/05/2020 | 9 | 28/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.50 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.338 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.337 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/05/2020 | 9 | 28/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.225 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/05/2020 | 11 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F129164.1 | Opened | 1329 - 19-22 Kildare Street | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 27/05/2020 | 9 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F92677.224 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/05/2020 | 11 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.223 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/05/2020 | 11 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.222 | Closed JPC Reviewed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.49 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 26/05/2020 | 9 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.336 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/05/2020 | 9 | 28/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.335 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.221 | Test Results Required | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 26/05/2020 | 11 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.220 | Open / Ongoing Works | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 26/05/2020 | 11 | 26/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.219 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 26/05/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.218 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 26/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.334 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/05/2020 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.216 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/05/2020 | 6 | 25/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.333 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.215 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 25/05/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.214 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 25/05/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.213 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 25/05/2020 | 11 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.212 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/05/2020 | 6 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.48 | Closed | 1329 - 19-22 Kildare Street | EHS Inspection. | 22/05/2020 | 9 | 22/05/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.331 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.330 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 22/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.396930 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.211 | Open / Ongoing Works | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 22/05/2020 | 12 | 22/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 5
F102314.47 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 22/05/2020 | 9 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.210 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.328 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/05/2020 | 9 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.327 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.46 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 21/05/2020 | 9 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.209 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/05/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.208 | Closed JPC Sign Off | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/05/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.207 | Closed JPC Reviewed | New Building>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-001 Site Diary | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.395521 | Completed and signed off | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 20/05/2020 | 9 | 20/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.395505 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.395469 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.326 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.325 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/05/2020 | 9 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.206 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 20/05/2020 | 11 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.205 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.45 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-007 COVID-19 Inspection | 20/05/2020 | 9 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.324 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.323 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/05/2020 | 9 | 19/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.204 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/05/2020 | 11 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.203 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 19/05/2020 | 6 | 19/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.202 | JPC Inspected | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/05/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.322 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.321 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/05/2020 | 9 | 19/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.393585 | Closed | 1329 - 19-22 Kildare Street | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 18/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.44 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 18/05/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.201 | Open / Ongoing Works | JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/05/2020 | 9 | 14/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F1.389745 | JPC Sign Off | 1329 - 19-22 Kildare Street | QM-FRM-QC-001 Benchmark / Sample Form | 12/5/2020 | 10 | 12/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.389281 | JPC Sign Off | 1329 - 19-22 Kildare Street | QM-FRM-QC-001 Benchmark / Sample Form | 12/5/2020 | 10 | 12/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F92677.198 | Open / Ongoing Works | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 3/4/2020 | 10 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.197 | Notification | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | BCAR Inspection Form | 3/4/2020 | 3 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F1.370675 | JPC Sign Off | 1329 - 19-22 Kildare Street | QM-FRM-QC-001 Benchmark / Sample Form | 2/4/2020 | 10 | 12/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.196 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 1/4/2020 | 11 | 17/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F1.369384 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 31/03/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.369369 | Completed and signed off | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 31/03/2020 | 9 | 31/03/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.42 | Opened | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 30/03/2020 | 9 | 30/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F102314.41 | Opened | 1329 - 19-22 Kildare Street | EHS Inspection. | 30/03/2020 | 9 | 30/03/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F102314.40 | Opened | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 30/03/2020 | 9 | 30/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.320 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/03/2020 | 9 | 27/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.319 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/03/2020 | 6 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.194 | Closed JPC Sign Off | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/03/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F102314.39 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | CM-EHS-FRM-006 Site Welfare Inspection | 27/03/2020 | 9 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F102314.38 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | CM-EHS-FRM-006 Site Welfare Inspection | 26/03/2020 | 9 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.318 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/03/2020 | 6 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.367145 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 26/03/2020 | 6 | 26/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.367141 | Completed and signed off | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 26/03/2020 | 9 | 26/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.37 | Opened | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 25/03/2020 | 9 | 25/03/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F92677.193 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/03/2020 | 9 | 25/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.317 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/03/2020 | 9 | 25/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.316 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/03/2020 | 6 | 25/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.192 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 25/03/2020 | 11 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.191 | Closed JPC Sign Off | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 25/03/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F102314.36 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-006 Site Welfare Inspection | 25/03/2020 | 9 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.315 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/03/2020 | 6 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.35 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-006 Site Welfare Inspection | 24/03/2020 | 9 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.314 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/03/2020 | 6 | 25/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.313 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/03/2020 | 9 | 23/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.34 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-006 Site Welfare Inspection | 23/03/2020 | 9 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.365140 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 23/03/2020 | 6 | 23/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.312 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/03/2020 | 9 | 23/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.311 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/03/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.32 | Closed | 1329 - 19-22 Kildare Street | EHS Inspection. | 20/03/2020 | 9 | 31/03/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.190 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 20/03/2020 | 11 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F92677.189 | Open / Ongoing Works | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 20/03/2020 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F102314.30 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-006 Site Welfare Inspection | 20/03/2020 | 9 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.364177 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 20/03/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.310 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/03/2020 | 9 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.188 | Closed | EHS Management>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 19/03/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.187 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/03/2020 | 9 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.308 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/03/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.29 | Completed and signed off | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 19/03/2020 | 9 | 19/03/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.186 | JPC Sign Off | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 19/03/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.185 | Open / Ongoing Works | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 19/03/2020 | 11 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.307 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/03/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.363771 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | JPC-QA-RP-003 - Site Audit Report | 19/03/2020 | 2 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1329 | Open | 3
F102314.28 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-006 Site Welfare Inspection | 19/03/2020 | 9 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.184 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/03/2020 | 11 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F92677.183 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/03/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F1.363390 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 19/03/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.306 | Closed | 1329 - 19-22 Kildare Street | CM-EHS-FRM-006 Site Welfare Inspection | 18/03/2020 | 9 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.305 | Closed | 1329 - 19-22 Kildare Street | EHS Inspection. | 13/03/2020 | 9 | 31/03/2020 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.304 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/3/2020 | 9 | 12/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.303 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/3/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.182 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 12/3/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.181 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/3/2020 | 11 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.180 | Closed JPC Sign Off | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/3/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.179 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/3/2020 | 9 | 12/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.358470 | Completed and signed off | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 12/3/2020 | 9 | 12/3/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.358444 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 12/3/2020 | 6 | 12/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.358123 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 11/3/2020 | 6 | 11/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.302 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/3/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.301 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/3/2020 | 9 | 10/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.300 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/3/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.299 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/3/2020 | 9 | 25/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.298 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/3/2020 | 6 | 19/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.297 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/3/2020 | 6 | 9/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.296 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/3/2020 | 9 | 6/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.178 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 6/3/2020 | 11 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.177 | Closed | 1329 - 19-22 Kildare Street | EHS Inspection. | 6/3/2020 | 9 | 31/03/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.354709 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 6/3/2020 | 6 | 6/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.176 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 5/3/2020 | 11 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.175 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 5/3/2020 | 11 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.174 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 5/3/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.173 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/3/2020 | 9 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.295 | Closed | 1329 - 19-22 Kildare Street | EHS Inspection. | 5/3/2020 | 9 | 9/3/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.294 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/3/2020 | 6 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.172 | Closed | 1329 - 19-22 Kildare Street | EHS Inspection. | 4/3/2020 | 9 | 31/03/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.293 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/3/2020 | 6 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.171 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 4/3/2020 | 7 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.170 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/3/2020 | 11 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.292 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/3/2020 | 6 | 6/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.291 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/3/2020 | 6 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.290 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/3/2020 | 6 | 6/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.289 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/02/2020 | 9 | 29/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.169 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 28/02/2020 | 11 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.288 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/02/2020 | 6 | 29/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.287 | Completed and signed off | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 28/02/2020 | 9 | 21/05/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F116350.10 | Opened | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 28/02/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F92677.168 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 28/02/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F92677.167 | Test Results Required | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 28/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.166 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/02/2020 | 11 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.348817 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/02/2020 | 11 | 27/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.286 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/02/2020 | 6 | 29/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.165 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 26/02/2020 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.164 | JPC Sign Off / Closed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 26/02/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.163 | Open / Ongoing Works | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 26/02/2020 | 12 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 5
F92677.162 | Open / Ongoing Works | Lvl -01 Basement Plan>New Building>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 26/02/2020 | 12 | 26/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 5
F92677.161 | Notification | Lvl -01 Basement Plan>New Building>ITP 02 Architectural>Quality Control & BC(A)R | BCAR Inspection Form | 26/02/2020 | 3 | 26/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F91214.285 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/02/2020 | 9 | 29/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.284 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/02/2020 | 6 | 29/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F116350.8 | Open / Ongoing Works | Quality Audits & Assessments>Quality Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 25/02/2020 | 10 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F116350.7 | Closed | Quality Audits & Assessments>Quality Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 25/02/2020 | 10 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.283 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/02/2020 | 9 | 24/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.282 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/02/2020 | 6 | 29/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.281 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/02/2020 | 9 | 24/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.280 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/02/2020 | 6 | 21/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F119089.3 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/02/2020 | 9 | 21/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.26 | Opened | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 21/02/2020 | 9 | 21/02/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F102314.25 | Opened | 1329 - 19-22 Kildare Street | EHS Inspection. | 20/02/2020 | 9 | 20/02/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F102314.24 | Completed and signed off | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 20/02/2020 | 9 | 21/02/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.160 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 20/02/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F92677.159 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 20/02/2020 | 11 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F91214.279 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 20/02/2020 | 11 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.278 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/02/2020 | 6 | 21/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.158 | JPC Sign Off / Closed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 20/02/2020 | 11 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F92677.157 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 20/02/2020 | 11 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.156 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 20/02/2020 | 7 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.344064 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 20/02/2020 | 6 | 20/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.344046 | Completed and signed off | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 20/02/2020 | 9 | 20/02/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.155 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/02/2020 | 9 | 19/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.277 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/02/2020 | 6 | 21/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.276 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-114 Blockwork / Brickwork Inspection | 19/02/2020 | 11 | 19/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.275 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/02/2020 | 6 | 19/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.342402 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 18/02/2020 | 6 | 18/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.274 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/02/2020 | 6 | 21/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.273 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/02/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F119089.2 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/02/2020 | 9 | 14/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.272 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/02/2020 | 6 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.271 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/02/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.154 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 14/02/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F92677.153 | Open / Ongoing Works | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-111 Pre-cast Concrete Inspection | 14/02/2020 | 11 | 14/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F102314.22 | Opened | JPC Project Management | EHS Inspection. | 13/02/2020 | 9 | 13/02/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.270 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/02/2020 | 6 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.269 | Opened | JPC Project Management | EHS Managment Inspection - Daily | 13/02/2020 | 9 | 13/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.268 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/02/2020 | 6 | 13/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.152 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 13/02/2020 | 11 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F116350.6 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 13/02/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.339179 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 13/02/2020 | 6 | 13/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.21 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/2/2020 | 9 | 26/08/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.151 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/2/2020 | 9 | 12/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.150 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/2/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F1.337259 | Completed and signed off | 1329 - 19-22 Kildare Street | EHS Managment Inspection - Daily | 11/2/2020 | 9 | 11/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.267 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/2/2020 | 6 | 13/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.337233 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 11/2/2020 | 6 | 11/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.266 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/2/2020 | 6 | 11/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.336685 | JPC Inspected | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 10/2/2020 | 7 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.265 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/2/2020 | 9 | 7/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F102314.20 | Opened | 1329 - 19-22 Kildare Street | EHS Inspection. | 7/2/2020 | 9 | 7/2/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.264 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/2/2020 | 6 | 11/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.335463 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 7/2/2020 | 6 | 7/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.263 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/2/2020 | 6 | 7/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.334570 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 6/2/2020 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.149 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 6/2/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F119089.1 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/2/2020 | 9 | 5/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.261 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/2/2020 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.148 | Open | JPC Project Management | QM-FRM-QC005 - Training Record | 5/2/2020 | 10 | 5/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F102314.19 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/2/2020 | 9 | 10/2/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.259 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/2/2020 | 6 | 5/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.258 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/2/2020 | 9 | 4/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.333027 | JPC Sign Off / Closed | 1329 - 19-22 Kildare Street | QM-FRM-QC-004 QC Observation Report | 4/2/2020 | 10 | 4/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F1.333011 | JPC Sign Off / Closed | 1329 - 19-22 Kildare Street | QM-FRM-QC-004 QC Observation Report | 4/2/2020 | 10 | 4/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F1.333003 | JPC Sign Off / Closed | 1329 - 19-22 Kildare Street | QM-FRM-QC-004 QC Observation Report | 4/2/2020 | 10 | 4/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F1.332503 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 4/2/2020 | 6 | 4/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.257 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/2/2020 | 6 | 5/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.256 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/2/2020 | 9 | 3/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.332008 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | QM-FRM-QC-004 QC Observation Report | 3/2/2020 | 10 | 3/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.147 | Closed JPC Sign Off | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/2/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F116350.3 | Opened | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 3/2/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F116350.2 | Closed | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 3/2/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.330992 | Open / Ongoing Works | 1329 - 19-22 Kildare Street | QM-FRM-QC-009 Quality Control Record | 31/01/2020 | 10 | 31/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.255 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 31/01/2020 | 9 | 31/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.254 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/01/2020 | 6 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.146 | JPC Sign Off / Closed | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 31/01/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.330495 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 31/01/2020 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.145 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 30/01/2020 | 9 | 30/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F102314.17 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 30/01/2020 | 9 | 10/2/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.144 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 30/01/2020 | 6 | 30/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.253 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/01/2020 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.143 | Works Complete / Resolved | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 30/01/2020 | 10 | 12/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Open | 4
F92677.142 | Closed JPC Sign Off | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 30/01/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.252 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/01/2020 | 9 | 29/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.251 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/01/2020 | 6 | 29/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.250 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/01/2020 | 9 | 29/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.249 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/01/2020 | 6 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.141 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 29/01/2020 | 6 | 30/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.140 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 29/01/2020 | 6 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.328795 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 29/01/2020 | 6 | 29/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.16 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/01/2020 | 9 | 31/01/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.139 | JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 28/01/2020 | 11 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.227 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/12/2019 | 6 | 20/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.312337 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 20/12/2019 | 6 | 20/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.111 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 20/12/2019 | 6 | 20/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.109 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 20/12/2019 | 6 | 20/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.108 | Closed JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/12/2019 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F91214.226 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/12/2019 | 6 | 20/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.311579 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 19/12/2019 | 6 | 19/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.10 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 18/12/2019 | 9 | 27/01/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.225 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/12/2019 | 6 | 19/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.107 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 18/12/2019 | 6 | 18/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.310900 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 18/12/2019 | 6 | 18/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.224 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/12/2019 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.223 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/12/2019 | 6 | 19/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.106 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 17/12/2019 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F1.310084 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 17/12/2019 | 6 | 17/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.105 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/12/2019 | 6 | 16/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.222 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/12/2019 | 6 | 17/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.104 | JPC Sign Off / Closed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 16/12/2019 | 10 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.103 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 16/12/2019 | 11 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.309270 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 16/12/2019 | 6 | 16/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.221 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/12/2019 | 6 | 16/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.102 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 13/12/2019 | 11 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.220 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/12/2019 | 6 | 16/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.219 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/12/2019 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.218 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/12/2019 | 6 | 16/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.217 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/12/2019 | 6 | 12/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.216 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/12/2019 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.101 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 10/12/2019 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.100 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 10/12/2019 | 6 | 10/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.99 | Completed and signed off | 03 Safety Notices>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/12/2019 | 9 | 10/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.305960 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 10/12/2019 | 6 | 10/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.215 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/12/2019 | 6 | 12/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.98 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 9/12/2019 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F92677.97 | Open | JPC Project Management | QM-FRM-QC005 - Training Record | 9/12/2019 | 10 | 9/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.96 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 9/12/2019 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.305067 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 9/12/2019 | 6 | 9/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.95 | Closed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 6/12/2019 | 10 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.214 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/12/2019 | 6 | 11/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.94 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 6/12/2019 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.304298 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 6/12/2019 | 6 | 6/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.212 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/12/2019 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F102314.9 | Closed | EHS Management>JPC Project Management | EHS Inspection. | 5/12/2019 | 9 | 27/01/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.211 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/12/2019 | 6 | 11/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.303902 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | QM-FRM-QC005 - Training Record | 5/12/2019 | 10 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F92677.93 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/12/2019 | 6 | 11/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.303439 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 5/12/2019 | 6 | 5/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.303435 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | QM-FRM-QC005 - Training Record | 5/12/2019 | 10 | 5/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F1.303421 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 5/12/2019 | 6 | 5/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.8 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/12/2019 | 9 | 27/01/2020 | 0 | 1 | parent | FALSE | FALSE | TRUE | FALSE | 1329 | Closed | 2
F91214.210 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/12/2019 | 6 | 4/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.91 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/12/2019 | 6 | 4/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.36 | Open | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 4/12/2019 | 9 | 4/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F92677.90 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 4/12/2019 | 11 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.89 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 4/12/2019 | 11 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.209 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/12/2019 | 9 | 3/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.208 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/12/2019 | 6 | 4/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.207 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/12/2019 | 6 | 3/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.206 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/12/2019 | 6 | 2/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.88 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 2/12/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.301051 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 2/12/2019 | 6 | 2/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F88470.35 | Open | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 29/11/2019 | 9 | 29/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F92677.85 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 29/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.300200 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 29/11/2019 | 6 | 29/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.7 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 28/11/2019 | 9 | 27/01/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.84 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/11/2019 | 9 | 28/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.205 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/11/2019 | 6 | 2/12/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 3
F1.299495 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 28/11/2019 | 6 | 28/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.83 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 28/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.82 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 27/11/2019 | 6 | 27/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.81 | Open | JPC Project Management | QM-FRM-QC005 - Training Record | 27/11/2019 | 10 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.204 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/11/2019 | 6 | 28/11/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 3
F1.298622 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 27/11/2019 | 6 | 27/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.203 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/11/2019 | 6 | 28/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.202 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/11/2019 | 9 | 3/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.80 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/11/2019 | 9 | 26/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.79 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 26/11/2019 | 6 | 26/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.78 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 26/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.297758 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 26/11/2019 | 6 | 26/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.201 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/11/2019 | 9 | 3/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.77 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/11/2019 | 6 | 25/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.200 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/11/2019 | 6 | 27/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.6 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 25/11/2019 | 9 | 10/2/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.75 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 25/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.297061 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 25/11/2019 | 6 | 25/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.199 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/11/2019 | 9 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.198 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/11/2019 | 6 | 22/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.296326 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 22/11/2019 | 6 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.296314 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | QM-FRM-QC005 - Training Record | 22/11/2019 | 10 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F92677.74 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 22/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.295456 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | QM-FRM-QC005 - Training Record | 21/11/2019 | 10 | 21/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F91214.197 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 21/11/2019 | 6 | 21/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.196 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 21/11/2019 | 6 | 21/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.195 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 21/11/2019 | 6 | 11/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1329 | Closed | 3
F91214.191 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 21/11/2019 | 6 | 21/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.73 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 21/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.188 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/11/2019 | 6 | 22/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.187 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/11/2019 | 9 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.295202 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 21/11/2019 | 6 | 21/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.186 | Closed JPC Reviewed | EHS Management>JPC Project Management | SM-FRM-001 Site Diary | 20/11/2019 | 6 | 20/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.182 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/11/2019 | 9 | 20/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.181 | Open / Ongoing Works | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 20/11/2019 | 11 | 20/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F102314.5 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/11/2019 | 9 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.180 | JPC Inspected | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 20/11/2019 | 11 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.72 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 20/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.294416 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 20/11/2019 | 6 | 20/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.179 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-001 Site Diary | 19/11/2019 | 6 | 19/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.71 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/11/2019 | 9 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.294087 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | QM-FRM-QC005 - Training Record | 19/11/2019 | 10 | 19/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F1.294081 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | QM-FRM-QC005 - Training Record | 19/11/2019 | 10 | 19/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F92677.70 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 19/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.293539 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 19/11/2019 | 6 | 19/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.178 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | EHS Managment Inspection - Daily | 18/11/2019 | 9 | 18/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.177 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 18/11/2019 | 6 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.175 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 18/11/2019 | 6 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.173 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 18/11/2019 | 6 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F88470.34 | Open / Ongoing Works | Quality Control & BC(A)R | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 18/11/2019 | 10 | 18/11/2019 | 1 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F91214.171 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 18/11/2019 | 6 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.165 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/11/2019 | 6 | 11/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.164 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 18/11/2019 | 6 | 18/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.293098 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 18/11/2019 | 6 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.69 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 18/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F102314.4 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/11/2019 | 9 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.68 | JPC Inspected | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 15/11/2019 | 11 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 4
F92677.67 | JPC Sign Off / Closed | East Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 15/11/2019 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.163 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/11/2019 | 6 | 18/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.66 | Open / Ongoing Works | West Elevation>Elevations>Existing Buildings>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 15/11/2019 | 11 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.63 | Closed JPC Reviewed | QC Training Records>Quality Management>JPC Project Management | QM-FRM-QC005 - Training Record | 15/11/2019 | 10 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F88470.32 | Open | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 15/11/2019 | 9 | 15/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F1.291879 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 15/11/2019 | 6 | 15/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.3 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 14/11/2019 | 9 | 10/2/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.62 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 14/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.291294 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 14/11/2019 | 6 | 14/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.162 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/11/2019 | 6 | 14/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.161 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/11/2019 | 6 | 13/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.61 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 13/11/2019 | 9 | 27/01/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.290628 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 13/11/2019 | 6 | 13/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.60 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/11/2019 | 9 | 12/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.290054 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 12/11/2019 | 6 | 12/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.160 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/11/2019 | 6 | 13/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.159 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/11/2019 | 6 | 12/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.59 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 11/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.158 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/11/2019 | 9 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.288593 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 11/11/2019 | 6 | 11/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.327561 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 27/01/2020 | 6 | 27/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.137 | Closed JPC Sign Off | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/01/2020 | 11 | 1/4/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F91214.248 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/01/2020 | 6 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.247 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/01/2020 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.246 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/01/2020 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F102314.15 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/01/2020 | 9 | 31/01/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.245 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/01/2020 | 6 | 25/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.14 | Closed | 03 Safety Notices>EHS Management>JPC Project Management | EHS Inspection. | 23/01/2020 | 9 | 10/2/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.244 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/01/2020 | 6 | 25/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.136 | JPC Sign Off | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 22/01/2020 | 11 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.323999 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 22/01/2020 | 6 | 22/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.243 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/01/2020 | 6 | 22/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.135 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 20/01/2020 | 6 | 20/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.242 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/01/2020 | 6 | 22/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.241 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/01/2020 | 6 | 20/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.134 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/01/2020 | 9 | 17/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.240 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/01/2020 | 6 | 19/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.321403 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | QM-FRM-QC005 - Training Record | 17/01/2020 | 10 | 17/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F102314.13 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/01/2020 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F102314.12 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 16/01/2020 | 9 | 27/01/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 2
F92677.133 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/01/2020 | 6 | 16/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.239 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/01/2020 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.132 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 15/01/2020 | 6 | 15/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.238 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/01/2020 | 6 | 19/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.131 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 14/01/2020 | 6 | 14/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.237 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/01/2020 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.236 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/01/2020 | 6 | 19/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.130 | Closed | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/01/2020 | 10 | 12/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.318535 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 14/01/2020 | 6 | 14/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.128 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/01/2020 | 9 | 13/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.126 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 13/01/2020 | 6 | 13/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.125 | Closed | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/01/2020 | 10 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.124 | Open / Ongoing Works | New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 13/01/2020 | 10 | 13/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F91214.235 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/01/2020 | 6 | 14/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.123 | JPC Sign Off / Closed | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CE-302-Bulk Excavation Inspection | 13/01/2020 | 7 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F92677.122 | Open / Ongoing Works | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CE-302-Bulk Excavation Inspection | 13/01/2020 | 7 | 13/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F1.317612 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 13/01/2020 | 6 | 13/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.121 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 10/1/2020 | 6 | 10/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.234 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/1/2020 | 6 | 14/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.316606 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 10/1/2020 | 6 | 10/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.120 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 9/1/2020 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.233 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/1/2020 | 6 | 10/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F102314.11 | Closed | 1329 - 19-22 Kildare Street | EHS Inspection. | 9/1/2020 | 9 | 27/01/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.315820 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 9/1/2020 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.119 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 8/1/2020 | 6 | 8/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.118 | Completed and signed off | 03 Safety Notices>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/1/2020 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.232 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/1/2020 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.315033 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 8/1/2020 | 6 | 8/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.116 | Closed JPC Reviewed | 03 Material Deliveries>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 7/1/2020 | 6 | 7/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.231 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/1/2020 | 6 | 8/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.314425 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 7/1/2020 | 6 | 7/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.115 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 6/1/2020 | 6 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.229 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/1/2020 | 6 | 8/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.228 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/1/2020 | 9 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.114 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 3/1/2020 | 6 | 3/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.113 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 3/1/2020 | 6 | 3/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.313468 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 3/1/2020 | 6 | 7/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.313465 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 3/1/2020 | 6 | 3/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.112 | Open / Ongoing Works | Lvl-01 Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 20/12/2019 | 11 | 20/12/2019 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F92677.138 | Open / Ongoing Works | Lvl -02 Lower Basement>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-116 Concrete Cube Record | 28/01/2020 | 11 | 28/01/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F88470.31 | Open | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 8/11/2019 | 9 | 8/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F1.287955 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 8/11/2019 | 6 | 8/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.156 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/11/2019 | 6 | 8/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.155 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/11/2019 | 9 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.154 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/11/2019 | 6 | 8/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F102314.2 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 7/11/2019 | 9 | 10/2/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.58 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 7/11/2019 | 11 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 4
F92677.57 | Open | JPC Project Management | QM-FRM-QC005 - Training Record | 7/11/2019 | 10 | 7/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 4
F1.287103 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 7/11/2019 | 6 | 7/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.153 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/11/2019 | 6 | 7/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.152 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 6/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.286395 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 6/11/2019 | 6 | 6/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.56 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/11/2019 | 9 | 10/2/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.151 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 5/11/2019 | 11 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.150 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/11/2019 | 6 | 6/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.285423 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.285364 | Closed JPC Sign Off | Lvl -01 Piling Layout>New Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 4/11/2019 | 11 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1329 | Closed | 4
F91214.149 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/11/2019 | 6 | 6/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.55 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/11/2019 | 9 | 4/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.148 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 1/11/2019 | 9 | 1/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.147 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.30 | Open | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 1/11/2019 | 9 | 1/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F92677.54 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 31/10/2019 | 9 | 10/2/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.146 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 31/10/2019 | 9 | 1/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.145 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/10/2019 | 6 | 1/11/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.144 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/10/2019 | 6 | 31/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.53 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 30/10/2019 | 9 | 30/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.142 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/10/2019 | 9 | 1/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.141 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/10/2019 | 6 | 30/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.140 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/10/2019 | 6 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.52 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 25/10/2019 | 9 | 31/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.51 | Closed JPC Reviewed | JPC Project Management | QM-FRM-QC005 - Training Record | 25/10/2019 | 10 | 31/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F88470.28 | Open | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 25/10/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Open | 2
F91214.139 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/10/2019 | 6 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 3
F92677.50 | Closed JPC Reviewed | JPC Project Management | QM-FRM-QC005 - Training Record | 24/10/2019 | 10 | 31/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F91214.138 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/10/2019 | 9 | 23/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.137 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/10/2019 | 6 | 23/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.49 | Closed JPC Reviewed | JPC Project Management | QM-FRM-QC005 - Training Record | 23/10/2019 | 10 | 13/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F92677.48 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/10/2019 | 9 | 22/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.136 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/10/2019 | 6 | 23/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.46 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/10/2019 | 9 | 31/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.134 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/10/2019 | 6 | 23/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.133 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/10/2019 | 9 | 18/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F88470.27 | Closed | Site Logistics Plan>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 18/10/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.132 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/10/2019 | 6 | 22/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.45 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 17/10/2019 | 9 | 31/10/2019 | 0 | 2 | parent | FALSE | FALSE | TRUE | FALSE | 1329 | Closed | 2
F91214.131 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/10/2019 | 9 | 31/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.130 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/10/2019 | 6 | 18/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.129 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/10/2019 | 9 | 16/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.128 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/10/2019 | 6 | 17/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.274188 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 15/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.273808 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 14/10/2019 | 6 | 14/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.44 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/10/2019 | 9 | 11/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.43 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 11/10/2019 | 9 | 31/10/2019 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F88470.26 | Closed | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 11/10/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F1.272608 | JPC Sign Off / Closed | 1329 - 19-22 Kildare Street | QM-FRM-QC-004 QC Observation Report | 11/10/2019 | 10 | 11/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F1.272584 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 11/10/2019 | 6 | 14/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F1.272564 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 11/10/2019 | 6 | 11/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.42 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/10/2019 | 9 | 10/2/2020 | 0 | 1 | parent | FALSE | FALSE | TRUE | FALSE | 1329 | Closed | 2
F92677.41 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/10/2019 | 9 | 11/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F1.270950 | JPC Sign Off / Closed | 1329 - 19-22 Kildare Street | QM-FRM-QC-004 QC Observation Report | 8/10/2019 | 10 | 11/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 4
F91214.127 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/10/2019 | 6 | 8/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.40 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/10/2019 | 9 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F88470.25 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 4/10/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.126 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/10/2019 | 9 | 3/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.125 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/10/2019 | 6 | 4/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.39 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 3/10/2019 | 9 | 31/10/2019 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.124 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/10/2019 | 6 | 3/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.123 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/10/2019 | 9 | 3/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.38 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 1/10/2019 | 9 | 3/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 2
F91214.117 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/10/2019 | 6 | 2/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.116 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/10/2019 | 6 | 2/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.37 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/09/2019 | 9 | 3/10/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.115 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/09/2019 | 6 | 1/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.23 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 27/09/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.114 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/09/2019 | 9 | 26/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.35 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 26/09/2019 | 9 | 14/01/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.112 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/09/2019 | 6 | 1/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.111 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/09/2019 | 6 | 25/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.110 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/09/2019 | 9 | 25/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.107 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/09/2019 | 6 | 25/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.105 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/09/2019 | 6 | 25/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.34 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/09/2019 | 9 | 24/09/2019 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F88470.21 | Opened | 01 Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 23/09/2019 | 9 | 23/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Open | 2
F91214.104 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/09/2019 | 9 | 26/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1329 | Closed | 2
F91214.103 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/09/2019 | 6 | 25/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.20 | Closed | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 20/09/2019 | 9 | 26/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.33 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/09/2019 | 9 | 2/10/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.102 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/09/2019 | 6 | 20/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.261704 | JPC Sign Off / Closed | 1329 - 19-22 Kildare Street | QM-CL-CS-102 Demolition Inspection | 19/09/2019 | 11 | 25/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 4
F91214.101 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/09/2019 | 9 | 18/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F92677.32 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 18/09/2019 | 9 | 14/01/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.100 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/09/2019 | 6 | 20/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.97 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/09/2019 | 9 | 17/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.96 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/09/2019 | 6 | 18/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.95 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/09/2019 | 9 | 16/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.93 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/09/2019 | 6 | 18/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.91 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/09/2019 | 6 | 13/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.31 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/09/2019 | 9 | 3/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F88470.19 | Closed | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 13/09/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.90 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/9/2019 | 6 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.89 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/9/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.88 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 12/9/2019 | 9 | 14/01/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.87 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/9/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.86 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/9/2019 | 6 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.85 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/9/2019 | 6 | 11/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.84 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/9/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.79 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2019 | 6 | 11/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.77 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/9/2019 | 6 | 9/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.18 | Closed | JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 6/9/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.75 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 5/9/2019 | 6 | 5/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.73 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/9/2019 | 6 | 11/2/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1329 | Closed | 3
F91214.72 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 5/9/2019 | 6 | 5/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.68 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 5/9/2019 | 6 | 6/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.30 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 5/9/2019 | 9 | 12/9/2019 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.63 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/9/2019 | 6 | 5/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.62 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/9/2019 | 9 | 4/9/2019 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.60 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 3/9/2019 | 6 | 5/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.58 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 3/9/2019 | 6 | 5/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.56 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 2/9/2019 | 6 | 5/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.55 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/9/2019 | 9 | 4/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.54 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/9/2019 | 6 | 2/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.53 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 30/08/2019 | 6 | 30/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.50 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 30/08/2019 | 6 | 5/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.49 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 30/08/2019 | 9 | 12/9/2019 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F88470.17 | Closed | Site Logistics Plan>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 30/08/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.48 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/08/2019 | 9 | 12/9/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.47 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 29/08/2019 | 6 | 29/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.46 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 29/08/2019 | 6 | 29/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.44 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 28/08/2019 | 6 | 30/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.43 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 28/08/2019 | 6 | 30/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.42 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/08/2019 | 9 | 30/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.40 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 27/08/2019 | 6 | 5/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.39 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 27/08/2019 | 6 | 5/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.38 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/08/2019 | 9 | 30/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.37 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 27/08/2019 | 6 | 28/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.36 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 26/08/2019 | 6 | 27/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.29 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/08/2019 | 9 | 30/08/2019 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.35 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 23/08/2019 | 6 | 27/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.34 | Completed and signed off | 04 Staturatury Forms>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/08/2019 | 9 | 30/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F88470.16 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 23/08/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.33 | Completed and signed off | 03 Safety Notices>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/08/2019 | 9 | 22/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.31 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 22/08/2019 | 6 | 27/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.28 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/08/2019 | 9 | 12/9/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.28 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 21/08/2019 | 6 | 27/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.27 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 20/08/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.23 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 19/08/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.21 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/08/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.15 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 16/08/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.18 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 15/08/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F96227.2 | Closed | QC Training Records>Quality Management>JPC Project Management | JPC-HR-FRM-001 - Training Record | 15/08/2019 | 2 | 16/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F91214.17 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 15/08/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.16 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 13/08/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.15 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 12/8/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.14 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 10/8/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.13 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 10/8/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.12 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 8/8/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.11 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 7/8/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.26 | Closed | 01 Inspections>EHS Management>JPC Project Management | EHS Inspection. | 7/8/2019 | 9 | 12/9/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F91214.10 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 6/8/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.25 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/8/2019 | 6 | 2/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.24 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/8/2019 | 6 | 2/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.14 | Closed | 03 Safety Notices>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 1/8/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.17 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/8/2019 | 6 | 1/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.15 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/8/2019 | 6 | 1/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.14 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 30/07/2019 | 6 | 1/8/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.13 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 30/07/2019 | 6 | 1/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F1.236999 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 30/07/2019 | 6 | 30/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F92677.11 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 29/07/2019 | 6 | 29/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.6 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/07/2019 | 6 | 25/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.8 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 25/07/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F92677.5 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 24/07/2019 | 6 | 25/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.4 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 23/07/2019 | 6 | 23/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F92677.2 | Closed JPC Reviewed | 1329 - 19-22 Kildare Street | SM-FRM-001 Site Diary | 22/07/2019 | 6 | 22/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.9 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 19/07/2019 | 6 | 19/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.7 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 18/07/2019 | 6 | 19/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.7 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 18/07/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.6 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 17/07/2019 | 6 | 19/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.5 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 17/07/2019 | 6 | 19/07/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 3
F90860.4 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 15/07/2019 | 6 | 19/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F90860.2 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 15/07/2019 | 6 | 19/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.4 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 12/7/2019 | 6 | 19/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.6 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 12/7/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F91214.3 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 11/7/2019 | 6 | 19/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F91214.2 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 19/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.5 | Closed | EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 5/7/2019 | 9 | 25/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F90857.3 | Completed and signed off | 01 Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/7/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1329 | Closed | 2
F90857.2 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/7/2019 | 6 | 13/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 3
F88470.4 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 27/06/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F88470.3 | Closed | 01 Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 19/06/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1329 | Closed | 2
F114176.43 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/9/2020 | 9 | 11/9/2020 | 6 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F131516.51 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/9/2020 | 9 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F121399.368 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.384 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.383 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.382 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F86424.561 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.367 | Open / Ongoing Works | Site Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/9/2020 | 9 | 10/9/2020 | 1 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F86424.560 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.366 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F86424.559 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.558 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.380 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 9/9/2020 | 9 | 9/9/2020 | 7 | 11 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F86424.557 | Open / Ongoing Works | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 9/9/2020 | 8 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.556 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.364 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F121399.363 | Open | Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F121399.362 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F86424.555 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.554 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.50 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/9/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F131515.40 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 8/9/2020 | 9 | 14/09/2020 | 0 | 27 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.553 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 8/9/2020 | 0 | 24 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.379 | Closed JPC Reviewed | 19-L1-14 Phone Booths>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.378 | Closed | 19-L1-49 Female WC>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 8/9/2020 | 10 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.377 | Open / Ongoing Works | 19-L1-49 Female WC>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 8/9/2020 | 8 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.552 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.551 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/9/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.376 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F114176.42 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/9/2020 | 9 | 7/9/2020 | 3 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F86424.550 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.375 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 3
F121399.361 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F114176.40 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F114176.39 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 4/9/2020 | 4 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F92044.374 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F121399.360 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 3/9/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F121399.359 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 3/9/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F121399.358 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 3/9/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.49 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F121399.356 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 3/9/2020 | 9 | 3/9/2020 | 0 | 10 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F121399.355 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.354 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.373 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 2/9/2020 | 9 | 2/9/2020 | 2 | 7 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 2
F92044.372 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 3
F139497.2 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 2/9/2020 | 9 | 7/9/2020 | 0 | 29 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.371 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F92044.370 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F86424.549 | Closed | 19-L1-03 Stair 3>Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.548 | Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 1/9/2020 | 8 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.353 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.546 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 1/9/2020 | 9 | 8/9/2020 | 0 | 16 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F1.482250 | Closed | 1330 - Regeneron Building 19 | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 31/08/2020 | 9 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F1.482249 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 31/08/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.539 | Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 31/08/2020 | 8 | 31/08/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.352 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/08/2020 | 6 | 30/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F131516.48 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/08/2020 | 9 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F124251.157 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/08/2020 | 9 | 28/08/2020 | 2 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F124251.156 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F121399.351 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 30/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.369 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F139497.1 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 27/08/2020 | 9 | 2/9/2020 | 0 | 17 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.155 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F121399.350 | Closed | 19-L2-19 PS Media and Buffer Prep>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.349 | Closed | 19-L2-13 Access>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.348 | Closed | 19-L2-06 Access>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.347 | Closed | 19-L2-47 Dis WC>WC's>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.346 | Closed | 19-L2-48 Femal WC's>WC's>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.345 | Closed | 19-L2-46 Male WC's>WC's>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.344 | Closed | 19-L1-82 Lobby>Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.343 | Closed | 19-L2-37 Micro Investigation Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.342 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.341 | Closed | 19-L2-14 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-208 Suspended Ceiling Inspection | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.340 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-208 Suspended Ceiling Inspection | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.339 | Closed | 19-L2-19 PS Media and Buffer Prep>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-208 Suspended Ceiling Inspection | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.338 | Closed | 19-L2-16 Electric>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.337 | Closed | 19-L2-04 Electric>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.336 | Closed | 19-L2-05 Electric>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.335 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.334 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.333 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.332 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.331 | Closed | 19-L3-18 Electric Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.330 | Closed | Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.329 | Closed | 19-L3-24 Social Hub>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.328 | Closed | 19-L3-14 Telepresence Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.327 | Closed | 19-L3-04 Office 4>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.326 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 26/08/2020 | 8 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.368 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.367 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 26/08/2020 | 9 | 26/08/2020 | 3 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F121399.325 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F92044.366 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F92044.365 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F121399.324 | Closed | Site Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 26/08/2020 | 9 | 3/9/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.323 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.322 | Closed | 19-L3-30 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 26/08/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.154 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F92044.362 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 3
F131516.47 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/08/2020 | 9 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F121399.321 | Closed | 19-L3-20 Female WC>WC's & Shower Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 25/08/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.320 | Closed | 19-L3-21 Male WC>WC's & Shower Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 25/08/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.319 | Closed | 19-L3-22 Service Void>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 25/08/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.318 | Closed | 19-L3-22 Service Void>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 25/08/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.317 | Closed | 19-l3-19 Dis WC>WC's & Shower Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 25/08/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.361 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 25/08/2020 | 9 | 25/08/2020 | 6 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F121399.315 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 25/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.153 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F109023.281 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F114176.37 | Closed | 03 Safety Notices>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 24/08/2020 | 9 | 26/08/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.314 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 24/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F124251.152 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F92044.360 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F121399.313 | Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 21/08/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F114176.38 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 31/08/2020 | 4 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F86424.545 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 31/08/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.543 | Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 31/08/2020 | 8 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.541 | Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 31/08/2020 | 8 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.540 | Notification | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | BCAR Inspection Form | 31/08/2020 | 3 | 31/08/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.312 | Closed | 19-L1-02 Stair 2>Stairs>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 21/08/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.151 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 21/08/2020 | 9 | 21/08/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F124251.148 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F121399.310 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.147 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.146 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/08/2020 | 9 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.359 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.358 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.357 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.356 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 20/08/2020 | 9 | 21/08/2020 | 3 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F121399.309 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.308 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.143 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/08/2020 | 9 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F131516.46 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 20/08/2020 | 9 | 20/08/2020 | 2 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F131515.39 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 20/08/2020 | 9 | 27/08/2020 | 0 | 26 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.141 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.307 | Open / Ongoing Works | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 19/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 4
F121399.305 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 19/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.472019 | Open / Ongoing Works | 1330 - Regeneron Building 19 | JPC-QA-RP-003 - Site Audit Report | 19/08/2020 | 2 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 3
F1.472001 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.304 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.140 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.355 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 18/08/2020 | 9 | 20/08/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.303 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.139 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.302 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/08/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.354 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.353 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F121399.301 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 17/08/2020 | 9 | 3/9/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.138 | Open / Ongoing Works | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.137 | Open / Ongoing Works | Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 17/08/2020 | 8 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F124251.136 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.352 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.351 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.350 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.349 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.348 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.347 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.345 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.344 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.343 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.342 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.341 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.340 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.338 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F124251.135 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/08/2020 | 9 | 18/08/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.134 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.45 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/08/2020 | 6 | 13/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F131516.44 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 13/08/2020 | 9 | 13/08/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.133 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.38 | Opened | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 12/8/2020 | 9 | 12/8/2020 | 1 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F131515.37 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 12/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F1.464878 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 12/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.337 | Open | 19-L2-20 Cell Bank>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.336 | Open | 19-L1-82 Lobby>Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.335 | Open | 19-L1-82 Lobby>Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.334 | Open | 19-L1-82 Lobby>Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.331 | Open | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.330 | Open | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 12/8/2020 | 8 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F124251.132 | Open / Ongoing Works | 03 Ducting>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 12/8/2020 | 10 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.131 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/8/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.36 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 12/8/2020 | 9 | 18/08/2020 | 0 | 23 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.463740 | Closed | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 11/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.329 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 11/8/2020 | 9 | 20/08/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.130 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/8/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.43 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.42 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/8/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F124251.129 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/8/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.461280 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.461261 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.461248 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F131516.41 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.40 | Open / Ongoing Works | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 7/8/2020 | 10 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F124251.128 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/8/2020 | 9 | 18/08/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F1.460326 | Closed | 1330 - Regeneron Building 19 | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/8/2020 | 9 | 7/8/2020 | 1 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F131516.39 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.38 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.37 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 6/8/2020 | 9 | 6/8/2020 | 1 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F131515.35 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 6/8/2020 | 9 | 12/8/2020 | 0 | 22 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.127 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.328 | Open / Ongoing Works | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 6/8/2020 | 8 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F1.458739 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 5/8/2020 | 9 | 5/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F92044.327 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F92044.326 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F131516.36 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.325 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.126 | Open / Ongoing Works | Surface Water>02 Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 5/8/2020 | 7 | 5/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F124251.125 | Open / Ongoing Works | Surface Water>02 Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 5/8/2020 | 7 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F131516.35 | Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 5/8/2020 | 8 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131516.34 | Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 5/8/2020 | 8 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131516.31 | Open / Ongoing Works | 19-L3-35 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.324 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 5/8/2020 | 9 | 20/08/2020 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.124 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.30 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.29 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.323 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F124251.123 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86421.37 | Closed | JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 31/07/2020 | 9 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86421.36 | Closed | Quality Control & BC(A)R | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 31/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.121 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/07/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.120 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/07/2020 | 9 | 18/08/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F131516.28 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/07/2020 | 6 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.300 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 30/07/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.27 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.118 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/07/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.299 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 30/07/2020 | 9 | 3/9/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F1.450976 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.450974 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.450935 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.298 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 29/07/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.297 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 29/07/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.296 | Closed | 19-L3-35 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 29/07/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.293 | Closed | 19-L3-18 Electric Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 29/07/2020 | 8 | 3/9/2020 | 0 | 0 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F121399.291 | Open / Ongoing Works | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 29/07/2020 | 8 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F131516.26 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 29/07/2020 | 9 | 7/8/2020 | 0 | 22 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.290 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F124251.117 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.25 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.322 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 28/07/2020 | 9 | 20/08/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F114176.34 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 28/07/2020 | 9 | 26/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F114176.33 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/07/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.116 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/07/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.289 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/07/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F114176.32 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/07/2020 | 6 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.288 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/07/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.115 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/07/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.294 | Notification | 19-L3-18 Electric Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | BCAR Inspection Form | 29/07/2020 | 3 | 29/07/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.332 | Notification | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | BCAR Inspection Form | 12/8/2020 | 3 | 12/8/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.534 | Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 24/07/2020 | 8 | 8/9/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.114 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 24/07/2020 | 9 | 18/08/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F124251.113 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.112 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 24/07/2020 | 9 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F86424.533 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.532 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.319 | Closed | 19-L1-72 Social Area>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 23/07/2020 | 8 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.318 | Closed | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/07/2020 | 8 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.317 | Closed | 19-L1-56 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/07/2020 | 8 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.316 | Closed | Conf Room 1>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/07/2020 | 8 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.315 | Closed | Conf Room 3>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/07/2020 | 8 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.286 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | EHS Managment Inspection - Daily | 23/07/2020 | 9 | 24/07/2020 | 0 | 10 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F121399.285 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F124251.111 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.531 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.530 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.529 | Closed | 19-L2-27 Wash>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006A Element Handover | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.284 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F124251.110 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.31 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 22/07/2020 | 9 | 7/8/2020 | 0 | 20 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.528 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 22/07/2020 | 9 | 8/9/2020 | 0 | 21 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.527 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.526 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.525 | Closed | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 21/07/2020 | 8 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.109 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/07/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.283 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F114176.31 | Opened | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 20/07/2020 | 9 | 20/07/2020 | 1 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F86424.524 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.523 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.522 | Open / Ongoing Works | 19-L1-01 Stair 1>Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 20/07/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.314 | JPC Sign Off | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 20/07/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.521 | JPC Sign Off | 19-L2-05 Electric>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 20/07/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.282 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 20/07/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.281 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | QM-FRM-QC-003 Protection of Finishes Inspection | 20/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.280 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | QM-FRM-QC-003 Protection of Finishes Inspection | 20/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.279 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.108 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.278 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F1.441018 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-004 QC Observation Report | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F1.440831 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F1.440817 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 17/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F1.440766 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 17/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.520 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.519 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.107 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 17/07/2020 | 9 | 23/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F131515.30 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/07/2020 | 10 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.518 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131515.29 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.517 | Closed | 19-L2-57 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131515.28 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131515.27 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.516 | Closed | 19-L2-31 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131515.26 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131515.25 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F131515.24 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.440316 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 17/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.313 | Open / Ongoing Works | 1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F114176.30 | Closed | Site Management>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.277 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.106 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.276 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.515 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.514 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.275 | Closed JPC Reviewed | Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.274 | Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 16/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.273 | Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 16/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F124251.105 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control & BC(A)R | QM-CL-ME-405 Lightning Protection & Earthing Inspection | 16/07/2020 | 1 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.272 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 16/07/2020 | 9 | 24/07/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.280 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.271 | Closed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 16/07/2020 | 8 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F109023.279 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.278 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.277 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.276 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.275 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.274 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.273 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.272 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.271 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.270 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.269 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.270 | Closed | Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 16/07/2020 | 8 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.269 | Closed | Quality Control & BC(A)R | CM-QM-CL-ARC-007 Metal Door Inspection | 16/07/2020 | 8 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.268 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/07/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.267 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 16/07/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F124251.104 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.265 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.267 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.266 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.265 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.264 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F109023.263 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.262 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F109023.261 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.260 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.259 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.312 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F1.438720 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438708 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438705 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438703 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438701 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438699 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438500 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438457 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438430 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438416 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438338 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.438288 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.513 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.512 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.437834 | Open | 1330 - Regeneron Building 19 | CM-QM-CL-ARC-007 Metal Door Inspection | 15/07/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.511 | Closed | Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-205 Joinery Inspection | 15/07/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F86424.510 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006A Element Handover | 15/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.311 | Open / Ongoing Works | 19-L1-36 Cent Lab Store>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 3
F92044.310 | Open / Ongoing Works | 19-L1-36 Cent Lab Store>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 3
F114176.29 | Closed | 19-L2-27 Wash>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 15/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.263 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.103 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.23 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 15/07/2020 | 9 | 22/07/2020 | 0 | 31 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.509 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 15/07/2020 | 9 | 22/07/2020 | 0 | 19 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.309 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.308 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.506 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 14/07/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.505 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.307 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 14/07/2020 | 9 | 20/08/2020 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.504 | Closed | 19-L2-19 PS Media and Buffer Prep>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 14/07/2020 | 8 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.503 | Closed | 19-L2-27 Wash>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 14/07/2020 | 8 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.502 | Closed | 19-L2-19 PS Media and Buffer Prep>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006A Element Handover | 14/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.262 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.102 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.501 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 13/07/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F114176.28 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/07/2020 | 9 | 16/07/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.500 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.101 | Closed | Foul Water>02 Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 13/07/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.435596 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F86424.499 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/07/2020 | 8 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F1.435594 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.100 | Opened | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/07/2020 | 9 | 13/07/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F86424.498 | Open / Ongoing Works | 19-L2-04 Electric>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 13/07/2020 | 8 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.497 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-208 Suspended Ceiling Inspection | 13/07/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.496 | Closed | 19-L2-19 PS Media and Buffer Prep>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-208 Suspended Ceiling Inspection | 13/07/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.261 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.99 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.22 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131515.21 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.495 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.494 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.20 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131515.19 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 10/7/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.260 | Closed JPC Reviewed | JPC Project Management | SM-FRM-002 Progress Record | 10/7/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.18 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 10/7/2020 | 9 | 15/07/2020 | 0 | 25 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.98 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.97 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.493 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.492 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F131515.17 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F1.433423 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 9/7/2020 | 10 | 9/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F121399.259 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 9/7/2020 | 9 | 12/7/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.491 | JPC Sign Off | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 9/7/2020 | 10 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.256 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.255 | Completed and signed off | 01 Daily Site Diary>Site Management>JPC Project Management | EHS Managment Inspection - Daily | 9/7/2020 | 9 | 12/7/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.258 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.257 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.490 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.306 | Open / Ongoing Works | 19-L1-34 Inactive Waste>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 8/7/2020 | 8 | 8/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.489 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.305 | Open / Ongoing Works | 19-l1-36 - Incoming Staging>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 8/7/2020 | 8 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.304 | Open / Ongoing Works | 19-L1-36 Cent Lab Store>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 8/7/2020 | 8 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.488 | Open / Ongoing Works | 19-L1-01 Stair 1>Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 8/7/2020 | 10 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.303 | Open / Ongoing Works | 19-L1-36 Cent Lab Store>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 8/7/2020 | 8 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F131515.16 | In Process / Manufactor | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 8/7/2020 | 10 | 8/7/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 4
F121399.254 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/7/2020 | 10 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.253 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.95 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.487 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2020 | 9 | 11/7/2020 | 0 | 15 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86424.485 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.302 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 7/7/2020 | 9 | 7/7/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.484 | Closed JPC Reviewed | JPC Project Management | QM-FRM-QC005 - Training Record | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.482 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.481 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.480 | Open / Ongoing Works | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 7/7/2020 | 10 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.479 | Closed | 19-L2-14 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.478 | Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.477 | Closed | Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.252 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.94 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F114176.27 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 6/7/2020 | 9 | 16/07/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F1.429775 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.429757 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.475 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 6/7/2020 | 6 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.474 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.473 | Closed | 19-L2-14 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 6/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.251 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.472 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 6/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.471 | Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 6/7/2020 | 8 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.93 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.92 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 3/7/2020 | 9 | 15/07/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F114176.26 | Closed | ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 3/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131516.24 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 3/7/2020 | 10 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131516.23 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 3/7/2020 | 10 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131516.22 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 3/7/2020 | 10 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.470 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 3/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.469 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.468 | Closed | 19-L2-49 Service Void>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 3/7/2020 | 8 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.250 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | QM-FRM-QC-003 Protection of Finishes Inspection | 3/7/2020 | 10 | 12/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.249 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 3/7/2020 | 10 | 12/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.248 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 3/7/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.247 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/7/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.427330 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.246 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.467 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 2/7/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.466 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/7/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.465 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 2/7/2020 | 10 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.464 | Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 2/7/2020 | 10 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.245 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 2/7/2020 | 9 | 7/7/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.463 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 2/7/2020 | 8 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.462 | Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 2/7/2020 | 8 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.91 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.426186 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 1/7/2020 | 10 | 1/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F1.426185 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 1/7/2020 | 10 | 1/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F1.426173 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 1/7/2020 | 10 | 1/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F1.425953 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F131515.15 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F86424.461 | Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 1/7/2020 | 8 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.460 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 1/7/2020 | 10 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.459 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.455 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.454 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 1/7/2020 | 8 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.244 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.90 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.14 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 1/7/2020 | 9 | 6/7/2020 | 0 | 27 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.301 | Open / Ongoing Works | 19-L1-25 Boiler Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F86424.453 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 1/7/2020 | 9 | 6/7/2020 | 0 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.256 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.300 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 30/06/2020 | 9 | 20/08/2020 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.299 | JPC Sign Off | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F1.424399 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 30/06/2020 | 10 | 30/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.452 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.451 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.243 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.242 | Closed | Site Management>JPC Project Management | SM-FRM-006A Element Handover | 30/06/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.241 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 30/06/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.240 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 30/06/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.89 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F114176.25 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/06/2020 | 9 | 1/7/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.255 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.321 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/07/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.537 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.536 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.287 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.34 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 24/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F131515.33 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 24/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131515.32 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 24/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F134368.1 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 24/07/2020 | 9 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F86424.535 | Works Complete | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | BCAR Inspection Form | 24/07/2020 | 3 | 8/9/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86421.28 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 29/05/2020 | 10 | 29/05/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92636.33 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 29/05/2020 | 9 | 2/6/2020 | 0 | 15 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.215 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/05/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.214 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 28/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.193 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/05/2020 | 6 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.386 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 28/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.383 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 28/05/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.382 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 28/05/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.381 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 28/05/2020 | 10 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.380 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127802.16 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/05/2020 | 9 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F109023.213 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 28/05/2020 | 10 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.262 | JPC Inspected | 19-L1-13 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.261 | JPC Inspected | 19-L1-13 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.379 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 28/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.192 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 28/05/2020 | 9 | 4/6/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.191 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F1.399155 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.209 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.377 | Closed JPC Reviewed | ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.260 | Closed | 19-L1-54 Janitor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.259 | Closed | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.258 | Closed | 19-L1-25 Boiler Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.257 | Closed | 19-L1-28 Goods Lift>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.256 | Closed | 19-L1-36 Cent Lab Store>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.255 | Closed | 19-L1-36 Cent Lab Store>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.254 | JPC Sign Off / Closed | 19-L1-83 Stair 2>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.253 | Closed | I9- L1-01 Stair 1>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.252 | JPC Sign Off / Closed | 19-L1-11 Dat Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.376 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 27/05/2020 | 9 | 28/05/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.251 | Closed | 19-L1-09 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 27/05/2020 | 8 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.250 | Closed JPC Reviewed | Conf Room 4>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.249 | Closed JPC Reviewed | Conf Room 4>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.248 | Closed JPC Reviewed | Conf Room 5>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.247 | Closed JPC Reviewed | Conf Room 3>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.246 | Closed JPC Reviewed | Conf Room 3>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.245 | Closed JPC Reviewed | Conf Room 2>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.244 | Closed JPC Reviewed | Conf Room 1>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.243 | Closed JPC Reviewed | 19-L1-56 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.242 | Closed JPC Reviewed | 19-L1-66 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.241 | Closed JPC Reviewed | 19-l1-61 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.240 | Closed JPC Reviewed | 19-L1- 60 Meeting room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127802.15 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.375 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.189 | Closed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-210 Metalwork Inspection | 26/05/2020 | 8 | 26/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.188 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 26/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.186 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 26/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.208 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 26/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.68 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/05/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.239 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F1.398045 | JPC Sign Off / Closed | 1330 - Regeneron Building 19 | QM-CL-ARC-202 Partitions Inspection | 26/05/2020 | 8 | 26/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.374 | 3rd Party Sign Off - Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 26/05/2020 | 10 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.373 | Works Complete / Resolved | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 26/05/2020 | 10 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.372 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 26/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F127802.14 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.185 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.371 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.370 | Closed | 19-L2-54 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/05/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.369 | Closed | 19-L2-45 Data Room>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/05/2020 | 8 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F109023.207 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 26/05/2020 | 9 | 2/6/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.206 | Closed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 25/05/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.205 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 25/05/2020 | 6 | 25/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.67 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/05/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F114176.21 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 25/05/2020 | 9 | 26/05/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.237 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.66 | Closed | 1330 - Regeneron Building 19 | CM-EHS-FRM-007 COVID-19 Inspection | 25/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.236 | JPC Inspected | I9- L1-01 Stair 1>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.184 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.368 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/05/2020 | 6 | 25/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.367 | Closed | 19-L2-18 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 25/05/2020 | 8 | 25/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.366 | Closed | 19-L1-01 Stair 1>Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/05/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.365 | Closed | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/05/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F109023.204 | Closed | 19-l1-07 Gen purpose 3>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 24/05/2020 | 10 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F109023.203 | JPC Inspected | 19-l1-07 Gen purpose 3>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 24/05/2020 | 8 | 24/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F109023.200 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.199 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.198 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.197 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.196 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.195 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.194 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.193 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.192 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.191 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.190 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.189 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.188 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.187 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.186 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.185 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.184 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.183 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.182 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.181 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.180 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.179 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.178 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.177 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.176 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.175 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.174 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.173 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.172 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.171 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.170 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.169 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F97233.42 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 23/05/2020 | 9 | 3/6/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.168 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.167 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.166 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.165 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.164 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.163 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.162 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.161 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.160 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.159 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.158 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.157 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.156 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.155 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.154 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.153 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.152 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.151 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.150 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.148 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.147 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.146 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.145 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.144 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.143 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.142 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.141 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.140 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.139 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.138 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.137 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/05/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.65 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/05/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127802.13 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.364 | Closed | 19-L1-01 Stair 1>Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 22/05/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.363 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.362 | Closed | 19-L2-24 Lobby>Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 22/05/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.361 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 22/05/2020 | 9 | 29/05/2020 | 0 | 16 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121401.7 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121401.6 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121401.5 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121401.4 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.183 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/05/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F121399.182 | Closed | 19-L3-24 Social Hub>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.181 | Closed | 19-L3-15 Lobby>Lobbies>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.180 | Closed | 19-L1-02 Stair 2>Stairs>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.179 | Closed | 19-L1-01 Stair 1>Stairs>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.178 | Closed | 19-L3-30 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.177 | Closed | 19-L3-27 Male Shower>WC's & Shower Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.176 | Closed | 19-L3-25 Waiting Area>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.175 | Closed | 19-L3-28 Female Toilet>WC's & Shower Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.174 | Closed | 19-L3-16 Janitors Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.173 | Closed | 19-L3-18 Electric Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.172 | Closed | 19-L3-30 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.170 | Closed | Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.169 | Closed | 19-L3-37 Archive>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.168 | Closed | 19-L3-42 Plant Room 2>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.167 | Closed | 19- L3-41 Kardex>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.166 | Closed | 19-L3-40 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.165 | Closed | 19-L3-38 Automation Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.164 | Closed | 19-L3-37 Archive>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F124251.64 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/05/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.163 | Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.162 | Closed | 19-L3-35 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.235 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.134 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.133 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.132 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.131 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.130 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.129 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.128 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.127 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.126 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.125 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.124 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.123 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.122 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.120 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.119 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.118 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.117 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.116 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.115 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.114 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.113 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.112 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.111 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.110 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.109 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.108 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 21/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127802.12 | Closed | JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.360 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.234 | Open / Ongoing Works | 19-L1-11 Dat Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.233 | JPC Inspected | 19-L1-05 Gen Purpose 1>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.232 | JPC Inspected | 19-L1-83 Stair 2>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.231 | JPC Inspected | 19-L1-83 Stair 2>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.359 | Closed | 19-L2-55 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.358 | Closed | 19-L2-46 Male WC's>WC's>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/05/2020 | 8 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.161 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 21/05/2020 | 9 | 9/6/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.107 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.106 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.105 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.104 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.103 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.102 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.101 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.100 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.99 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.98 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.97 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.96 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.95 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.94 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.93 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.92 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.91 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.230 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.229 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.228 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.227 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.226 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.225 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.224 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.223 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.222 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.221 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.63 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.395423 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-002 Progress Record | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.395357 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F127802.11 | Closed | JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.160 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.357 | Closed | 19-L2-06 Access>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/05/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.220 | JPC Inspected | 19-L1-09 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.219 | JPC Inspected | 19-L1-09 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.218 | Open / Ongoing Works | 19-l1-07 Gen purpose 3>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/05/2020 | 8 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.356 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86421.27 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 20/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.355 | Closed | 19-L2-44 Fallow Area 2>Fallow Areas>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/05/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.354 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 20/05/2020 | 9 | 23/06/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.90 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.89 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/05/2020 | 9 | 20/05/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.62 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127802.10 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 19/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.217 | JPC Sign Off | 19-L1-03 Stair 3W>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 19/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.216 | JPC Inspected | 19-l1-50 Male Locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/05/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.215 | JPC Inspected | 19-l1-50 Male Locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/05/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.159 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.352 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 19/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.214 | Open / Ongoing Works | 19-L1-55 Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/05/2020 | 8 | 19/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.213 | JPC Inspected | 19-l1-50 Male Locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/05/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.211 | JPC Inspected | Meeting 6>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F109023.232 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F131515.2 | Closed | JPC Project Management | JPC-HR-FRM-001 - Training Record | 15/06/2020 | 2 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.411716 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/06/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.411330 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/06/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F1.411319 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/06/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.411318 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/06/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.84 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/6/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.410867 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/6/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.220 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.83 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 12/6/2020 | 9 | 24/06/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F127802.26 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.425 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/6/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.19 | Open / Ongoing Works | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.18 | Open / Ongoing Works | 19-L1-56 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.17 | Open / Ongoing Works | 19-L1-13 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.16 | Open / Ongoing Works | 19- L1-62 Meeting room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.15 | Open / Ongoing Works | 19- L1-62 Meeting room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.14 | Open / Ongoing Works | 19-l1-61 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.13 | Open / Ongoing Works | 19-L1-25 Boiler Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.12 | Open / Ongoing Works | 19-L1-55 Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-007 Lessons Learned Report | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F1.410508 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-007 Lessons Learned Report | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 4
F131516.11 | Open / Ongoing Works | 19-L1-13 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-208 Suspended Ceiling Inspection | 12/6/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.10 | Open / Ongoing Works | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-208 Suspended Ceiling Inspection | 12/6/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.9 | Open / Ongoing Works | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-208 Suspended Ceiling Inspection | 12/6/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131516.8 | Open / Ongoing Works | 19-L1-56 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-208 Suspended Ceiling Inspection | 12/6/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F109023.231 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 12/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.230 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 12/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.229 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 12/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.424 | Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.423 | Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 12/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.422 | Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 12/6/2020 | 10 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131516.6 | JPC Sign Off / Closed | 19-L1-14 Phone Booths>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 12/6/2020 | 8 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131516.5 | Open / Ongoing Works | 19-L1-13 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 12/6/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F109023.228 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/6/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F127802.25 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/6/2020 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.421 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 11/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.219 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 11/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F121399.218 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 11/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F121399.217 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 11/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F121399.215 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 11/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.420 | JPC Sign Off | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 11/6/2020 | 10 | 13/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.419 | JPC Sign Off | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 11/6/2020 | 10 | 13/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.418 | JPC Sign Off | 19-L1-82 Lobby>Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 11/6/2020 | 10 | 13/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.214 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2020 | 9 | 16/06/2020 | 0 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F131515.1 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 11/6/2020 | 9 | 16/06/2020 | 0 | 17 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.417 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131516.3 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 11/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.416 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 11/6/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.415 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 11/6/2020 | 10 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.413 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 11/6/2020 | 10 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.412 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 11/6/2020 | 10 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F92044.285 | JPC Sign Off / Closed | 19-L1-14 Phone Booths>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131516.2 | JPC Signed Off / Closed | Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 11/6/2020 | 12 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 5
F124251.82 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/6/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.411 | Closed | 19-L2-35 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F109023.226 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/6/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.213 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127802.24 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/6/2020 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.410 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 10/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.409 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.408 | Completed and signed off | 03 Safety Notices>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 10/6/2020 | 9 | 23/06/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.407 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 10/6/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F92044.284 | Open / Ongoing Works | 19-L1-11 Dat Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 10/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F86424.406 | Closed | 19-L2-46 Male WC's>WC's>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 10/6/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F109023.225 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/6/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.81 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/6/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.224 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 9/6/2020 | 9 | 16/06/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F127802.23 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/6/2020 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.283 | Open / Ongoing Works | 19-L1-66 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 9/6/2020 | 10 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.282 | Open | 19-L1-25 Boiler Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 9/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F92044.281 | Closed | 19-L1-25 Boiler Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 9/6/2020 | 10 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.212 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.405 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.211 | Closed | 19-L3-42 Plant Room 2>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 9/6/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.80 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/6/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F114176.22 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 9/6/2020 | 9 | 15/06/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.223 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/6/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.222 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/6/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.221 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/6/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.220 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/6/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.218 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.210 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F127802.22 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/6/2020 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.404 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.403 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/6/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.402 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.406518 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F97233.44 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 8/6/2020 | 9 | 9/6/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.209 | Closed | Site Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/6/2020 | 10 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.79 | Closed JPC Sign Off | 05 Watermain>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-ME-401 Services Test | 6/6/2020 | 1 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.78 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/6/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.77 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/6/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121401.9 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 5/6/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121401.8 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 5/6/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.208 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 5/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127802.21 | Closed | JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/6/2020 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.207 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/6/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.206 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/6/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.280 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.279 | Open / Ongoing Works | Wash Area>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.278 | JPC Inspected | 19-L1-54 Janitor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.277 | Open / Ongoing Works | 19-L1-72 Social Area>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 4/6/2020 | 10 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.276 | Open / Ongoing Works | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.401 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 4/6/2020 | 6 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127802.20 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.275 | JPC Inspected | 19-l1-50 Male Locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.274 | JPC Inspected | 19-L1-83 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.273 | JPC Inspected | 19-L1-53 Female locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.272 | JPC Inspected | 19-L1-53 Female locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.271 | JPC Inspected | 19-L1-53 Female locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.270 | JPC Inspected | 19-L1-52 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.400 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 4/6/2020 | 9 | 4/6/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.269 | JPC Inspected | 19-L1-53 Female locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.268 | JPC Inspected | 19-L1-53 Female locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.267 | JPC Inspected | 19-L1-53 Female locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 4/6/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.399 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/6/2020 | 6 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.398 | Open / Ongoing Works | 19-L2-25 Technical Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 4/6/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F121399.205 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 4/6/2020 | 9 | 9/6/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92636.34 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 4/6/2020 | 9 | 11/6/2020 | 0 | 22 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.204 | JPC Signed Off / Closed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 3/6/2020 | 12 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 5
F121399.203 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 3/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.202 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 3/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.201 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 3/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.200 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 3/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.199 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 3/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.76 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.75 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.403803 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F121399.198 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.266 | JPC Sign Off | 19-L1-03 Stair 3W>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 3/6/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F127802.19 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.397 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 3/6/2020 | 6 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.197 | Closed | Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 3/6/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.196 | Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 3/6/2020 | 8 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.74 | Open / Ongoing Works | Surface Water>02 Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 3/6/2020 | 10 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.396 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.217 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 2/6/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.216 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 2/6/2020 | 9 | 9/6/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.73 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 2/6/2020 | 10 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.265 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F127802.18 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.264 | JPC Inspected | 19-L1-09 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 2/6/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.395 | Closed | 19-L2-23 (-40) Cold Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 2/6/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.393 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 2/6/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.392 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/6/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.194 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/6/2020 | 6 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.72 | Closed | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CE-302-Bulk Excavation Inspection | 2/6/2020 | 7 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F97233.43 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 2/6/2020 | 9 | 22/06/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.391 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 29/05/2020 | 6 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.71 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/05/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.70 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/05/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.69 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/05/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.390 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 29/05/2020 | 10 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.389 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 29/05/2020 | 10 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.388 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 29/05/2020 | 10 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.400509 | JPC Sign Off | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 29/05/2020 | 10 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86421.30 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 29/05/2020 | 9 | 12/6/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F127802.17 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.387 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/05/2020 | 6 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.254 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.251 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86421.35 | Opened | 1330 - Regeneron Building 19 | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 29/06/2020 | 9 | 29/06/2020 | 1 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F121399.239 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.450 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 29/06/2020 | 6 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.449 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.88 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.87 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 26/06/2020 | 9 | 15/07/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.237 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/06/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.447 | Closed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.446 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 26/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.445 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 26/06/2020 | 10 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.421611 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 26/06/2020 | 10 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Open | 4
F92044.298 | JPC Inspected | 19-L1-05 Gen Purpose 1>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 26/06/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.297 | Open / Ongoing Works | 19-L1-06 Gen purpose 2>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 26/06/2020 | 11 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.296 | Open / Ongoing Works | 19-L1-09 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.295 | Open / Ongoing Works | 19-L1-12 Facilities Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.294 | Open / Ongoing Works | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.293 | Open / Ongoing Works | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.292 | Open / Ongoing Works | 19-L1-40 Meeting Room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.291 | Open / Ongoing Works | 19-L1-72 Social Area>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.290 | Open / Ongoing Works | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.289 | Open / Ongoing Works | 19-L1-72 Social Area>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.444 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 25/06/2020 | 10 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.443 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 25/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.442 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 25/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.236 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 25/06/2020 | 9 | 12/7/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.441 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 25/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.440 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F131515.13 | Open | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 25/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 3
F131516.21 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 25/06/2020 | 9 | 6/7/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.235 | Closed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 25/06/2020 | 10 | 12/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.234 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/06/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.419821 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.419818 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.439 | Closed | 19-L2-35 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 24/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.233 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.438 | Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 24/06/2020 | 10 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.437 | Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-209 Glazing Inspection - Windows & Doors | 24/06/2020 | 8 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.435 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 24/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.434 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F131515.12 | Open / Ongoing Works | 04 Progress Photos>Site Management>JPC Project Management | QM-FRM-QC-009 Quality Control Record | 24/06/2020 | 10 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.288 | Open / Ongoing Works | 19-l1-10 DIS WC>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/06/2020 | 8 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F121399.232 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 12/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.433 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 24/06/2020 | 9 | 26/06/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.432 | Open / Ongoing Works | 19-L1-01 Stair 1>Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 23/06/2020 | 10 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.431 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 23/06/2020 | 10 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.430 | Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 23/06/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F131515.11 | Open / Ongoing Works | 04 Progress Photos>Site Management>JPC Project Management | QM-FRM-QC-009 Quality Control Record | 23/06/2020 | 10 | 23/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F131515.10 | Open / Ongoing Works | 04 Progress Photos>Site Management>JPC Project Management | QM-FRM-QC-009 Quality Control Record | 23/06/2020 | 10 | 23/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.429 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 23/06/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.428 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/06/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.249 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 23/06/2020 | 9 | 3/7/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.417529 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.427 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 22/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F114176.24 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 22/06/2020 | 9 | 23/06/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.426 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.230 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 22/06/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86421.33 | Open / Ongoing Works | Quality Control & BC(A)R | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 22/06/2020 | 10 | 22/06/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F121399.229 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F121399.228 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.248 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.247 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.246 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 19/06/2020 | 6 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.245 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 19/06/2020 | 6 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.86 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/06/2020 | 9 | 24/06/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.244 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.243 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F92044.287 | Open / Ongoing Works | 19-L1-12 Facilities Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/06/2020 | 8 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.286 | Closed | 19-L1-05 Gen Purpose 1>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/06/2020 | 8 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F131515.6 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-009 Quality Control Record | 18/06/2020 | 10 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F131515.4 | Closed | 04 Progress Photos>Site Management>JPC Project Management | QM-FRM-QC-009 Quality Control Record | 18/06/2020 | 10 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.227 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.226 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 18/06/2020 | 9 | 24/06/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.242 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.241 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.225 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.240 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.239 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F109023.237 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F131516.20 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 17/06/2020 | 9 | 17/06/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F131515.3 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 17/06/2020 | 9 | 6/7/2020 | 0 | 24 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F114176.23 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 16/06/2020 | 9 | 22/06/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.236 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.235 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F121401.10 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.224 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.234 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 16/06/2020 | 9 | 17/06/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.222 | JPC Sign Off | Site Management>JPC Project Management | QM-FRM-ARC-201 Benchmark / Sample Form | 16/06/2020 | 8 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F121399.221 | Closed | Site Management>JPC Project Management | SM-FRM-006 Area Handover | 16/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F1.412744 | Closed | JPC Project Management | JPC-QA-RP-003 - Site Audit Report | 16/06/2020 | 2 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F124251.85 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.412389 | Closed (Design Team Acceptance) | 1330 - Regeneron Building 19 | BCAR Inspection Form | 15/06/2020 | 3 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86421.29 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 29/05/2020 | 10 | 29/05/2020 | 0 | 0 | child | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F86421.34 | Open / Ongoing Works | Quality Control & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 22/06/2020 | 10 | 22/06/2020 | 0 | 0 | child | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F1.384022 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-006 Area Handover | 30/04/2020 | 6 | 30/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F1.384020 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-006 Area Handover | 30/04/2020 | 6 | 30/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F86421.24 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 30/04/2020 | 10 | 30/04/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.144 | JPC Inspected | Conf Room 1>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.142 | JPC Inspected | 19-L1-56 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.141 | JPC Inspected | 19-L1- 60 Meeting room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.140 | JPC Inspected | 19-l1-61 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.139 | JPC Inspected | 19-l1-61 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.138 | JPC Inspected | 19-l1-61 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.137 | Open / Ongoing Works | 19-L1-11 Dat Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 30/04/2020 | 8 | 30/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.136 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/04/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F127802.1 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 30/04/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.306 | Closed | 19-L2-14 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/04/2020 | 8 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.305 | Closed | 19-L2-33 Cold Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 30/04/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92636.27 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 30/04/2020 | 9 | 5/5/2020 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.109 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 30/04/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.108 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 30/04/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F86424.304 | Closed | 10-L2-36 Fallow Area 1>Fallow Areas>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 30/04/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.107 | Closed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 30/04/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.301 | Closed | 19-L2-34 Freezer Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/04/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F92044.135 | JPC Inspected | 19-L1-56 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.29 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.28 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.300 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/04/2020 | 6 | 30/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.106 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 30/04/2020 | 9 | 11/5/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.299 | Closed | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 30/04/2020 | 8 | 30/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.27 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.134 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/04/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F127085.6 | Closed | 1330 - Regeneron Building 19 | CM-EHS-FRM-007 COVID-19 Inspection | 29/04/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.298 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/04/2020 | 8 | 30/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.297 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/04/2020 | 6 | 29/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.296 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 29/04/2020 | 9 | 1/5/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.133 | JPC Inspected | 19-L1-39 Conf Room>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.295 | Closed | 19-L2-14 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/04/2020 | 8 | 30/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.294 | Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/04/2020 | 8 | 30/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.105 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/04/2020 | 9 | 3/7/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.84 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 28/04/2020 | 9 | 20/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.104 | Closed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 28/04/2020 | 8 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.103 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/04/2020 | 6 | 28/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.26 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.25 | Open / Ongoing Works | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/04/2020 | 9 | 28/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F92044.131 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/04/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.129 | Open / Ongoing Works | Data Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 28/04/2020 | 8 | 28/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F1.382233 | Closed | 1st Floor Plan>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 28/04/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.127 | Works Complete / Resolved | 1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 28/04/2020 | 8 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 4
F86424.293 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 29/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.292 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 29/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.291 | Closed | 19-L2-15 Janitors Store>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.126 | JPC Inspected | Conf Room 1>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.125 | JPC Inspected | 19-L1-66 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.124 | JPC Inspected | 19-l1-61 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.123 | JPC Inspected | 19-l1-61 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.122 | JPC Inspected | 19- L1-62 Meeting room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.121 | JPC Inspected | 19-L1-66 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.120 | JPC Inspected | Conf Room 4>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.119 | JPC Inspected | Conf Room 4>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.118 | JPC Inspected | Conf Room 4>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.290 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/04/2020 | 6 | 28/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.117 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.116 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F114176.17 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 28/04/2020 | 9 | 25/05/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.289 | Closed | 19-L2-45 Data Room>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 28/04/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.288 | JPC Sign Off / Closed | Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 28/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.287 | Closed | Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/04/2020 | 8 | 29/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F109023.83 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/04/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.286 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/04/2020 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.285 | Closed | 19-L2-23 (-40) Cold Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/04/2020 | 8 | 30/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.284 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/04/2020 | 6 | 28/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.283 | Closed | 19-L2-27 Wash>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/04/2020 | 8 | 28/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.102 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/04/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.24 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.279 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/04/2020 | 6 | 25/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F97233.38 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 24/04/2020 | 9 | 27/04/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.113 | JPC Inspected | 19-l1-61 Lobby>Lobbies>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 24/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.111 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 24/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.110 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.109 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 24/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.108 | Open / Ongoing Works | 19-L1-72 Social Area>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 24/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.107 | JPC Inspected | 19-L1-69 disabled WC>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 24/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.106 | JPC Inspected | Conf Room 4>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.105 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.104 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.103 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.99 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/04/2020 | 6 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.102 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/04/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F124251.23 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 24/04/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F124251.22 | Open / Ongoing Works | ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F86424.278 | Closed | Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/04/2020 | 8 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.277 | Closed | 19-L2-33 Cold Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/04/2020 | 8 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.276 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/04/2020 | 6 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.275 | Closed | Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.21 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.274 | Closed | 19-L2-34 Freezer Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 24/04/2020 | 8 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.273 | Closed | 19-L2-32 Duct>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 24/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.380352 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 23/04/2020 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F92044.101 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.100 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/04/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.98 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 23/04/2020 | 9 | 27/04/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.97 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/04/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.99 | Works Complete / Resolved | Electric riser>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 23/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F121399.95 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/04/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.98 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 23/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F124251.20 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 23/04/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.97 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 23/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F92044.96 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 23/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F86424.272 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/04/2020 | 6 | 23/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.95 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.94 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.93 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.271 | Closed | 19-L2-27 Wash>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/04/2020 | 8 | 30/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.270 | Closed | 19-L2-29 Clean Hold>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/04/2020 | 8 | 28/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.269 | JPC Sign Off / Closed | 19-L2-29 Clean Hold>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.19 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.268 | JPC Sign Off / Closed | 19-L2-31 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/04/2020 | 8 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.91 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/04/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F124251.18 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/04/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F121399.94 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 22/04/2020 | 6 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92636.25 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 22/04/2020 | 9 | 5/5/2020 | 0 | 17 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.89 | Closed | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 22/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.267 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/04/2020 | 6 | 23/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.266 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 22/04/2020 | 9 | 1/5/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.88 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 22/04/2020 | 9 | 24/04/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.93 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 22/04/2020 | 9 | 15/05/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.17 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.82 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 21/04/2020 | 9 | 24/04/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.16 | Open / Ongoing Works | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/04/2020 | 9 | 21/04/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F92044.87 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/04/2020 | 9 | 21/04/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F121399.90 | Closed | 19-L3-23 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.89 | Closed | 19-L3-23 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.88 | Closed | 19-L3-13 Conf 3>Conference Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.87 | Closed | 19-L3-12 Conf 2>Conference Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.86 | Closed | 19-L3-11 Conf 1>Conference Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.85 | Closed | 19-L3-07 Office 7>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.84 | Closed | 19-L3-06 Office 6>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.83 | Closed | 19-L3-05 Office 5>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.82 | Closed | 19-L3-04 Office 4>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.86 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/04/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.265 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/04/2020 | 6 | 21/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.81 | Closed | 19-L3-02 PA Area>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.264 | Closed | 19-L2-45 Data Room>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/04/2020 | 8 | 21/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.15 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.378363 | Closed | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 21/04/2020 | 6 | 21/04/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F121399.80 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/04/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.85 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/04/2020 | 6 | 21/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.263 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/04/2020 | 6 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.262 | Closed | 19-L2-37 Micro Investigation Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 20/04/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F92044.84 | Closed | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.83 | Closed | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.14 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.76 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/04/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F97233.37 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 17/04/2020 | 9 | 3/6/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.82 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/04/2020 | 6 | 18/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.81 | Closed | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 17/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.261 | JPC Sign Off / Closed | 19-L2-42 Office 1>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 17/04/2020 | 8 | 17/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.260 | Closed | 19-L1-82 Lobby>Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 17/04/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.259 | JPC Sign Off / Closed | Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 17/04/2020 | 8 | 20/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.258 | Closed | 19-L2-37 Micro Investigation Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 17/04/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.257 | Closed | 19-L2-35 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 17/04/2020 | 8 | 17/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.256 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 17/04/2020 | 8 | 17/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F127085.5 | Closed | 1330 - Regeneron Building 19 | CM-EHS-FRM-007 COVID-19 Inspection | 17/04/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.80 | Closed | 19-l1-36 - Incoming Staging>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 17/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.79 | Closed | 19-L1-03 Stair 3W>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 17/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.78 | Closed | 19-L1-04 Stair 4>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 17/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.77 | Closed | 19-L1-04 Stair 4>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 17/04/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.255 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/04/2020 | 6 | 17/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.254 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/04/2020 | 6 | 17/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.253 | JPC Sign Off / Closed | 19-L2-18 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 17/04/2020 | 8 | 20/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.13 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.75 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/04/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.74 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/04/2020 | 6 | 16/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.81 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 16/04/2020 | 9 | 19/04/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.75 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/04/2020 | 6 | 18/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.74 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/04/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.252 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/04/2020 | 6 | 16/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127129.4 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 16/04/2020 | 9 | 17/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F127129.3 | Open / Ongoing Works | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 16/04/2020 | 9 | 16/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F86424.251 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/04/2020 | 6 | 16/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.73 | Closed | 19-L1-34 Inactive Waste>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.72 | Closed | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.71 | Closed | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.70 | Closed | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/04/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.12 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.73 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 15/04/2020 | 9 | 15/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.69 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/04/2020 | 6 | 16/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.250 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/04/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.249 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/04/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.68 | Open / Ongoing Works | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/04/2020 | 8 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F127085.4 | Closed | 1330 - Regeneron Building 19 | CM-EHS-FRM-007 COVID-19 Inspection | 15/04/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.248 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 15/04/2020 | 9 | 20/04/2020 | 0 | 11 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F127129.2 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 15/04/2020 | 9 | 17/04/2020 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.11 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.247 | Closed | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/04/2020 | 8 | 27/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.246 | Closed | 19-L2-18 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/04/2020 | 8 | 17/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.10 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/04/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.245 | JPC Sign Off / Closed | 19-L2-21 PPE>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/04/2020 | 8 | 16/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.244 | JPC Sign Off / Closed | Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/04/2020 | 8 | 16/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.72 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/04/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F114176.16 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 14/04/2020 | 9 | 25/05/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.66 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/04/2020 | 6 | 18/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127085.3 | Closed | 1330 - Regeneron Building 19 | CM-EHS-FRM-007 COVID-19 Inspection | 14/04/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.243 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/04/2020 | 6 | 14/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.242 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/04/2020 | 6 | 14/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.241 | JPC Sign Off / Closed | Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 14/04/2020 | 8 | 14/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.240 | JPC Sign Off / Closed | 19-L2-20 Cell Bank>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 14/04/2020 | 8 | 14/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.239 | JPC Sign Off / Closed | 19-L2-21 PPE>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 14/04/2020 | 8 | 14/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.65 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/04/2020 | 6 | 18/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.64 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/04/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.63 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/04/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.62 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/04/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.61 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/04/2020 | 6 | 13/04/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F92044.60 | Closed | 19-L1-30 Decon>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 10/4/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.9 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 9/4/2020 | 9 | 9/4/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F127085.2 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/4/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.238 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.237 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.8 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.7 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.80 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/4/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F97233.36 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 8/4/2020 | 9 | 3/6/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.71 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/4/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.70 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/4/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.373812 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | QM-FRM-QC005 - Training Record | 8/4/2020 | 10 | 8/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F127085.1 | Closed | JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/4/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F127129.1 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 8/4/2020 | 9 | 15/04/2020 | 0 | 15 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.79 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 7/4/2020 | 9 | 19/04/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.373328 | Open / Ongoing Works | 1330 - Regeneron Building 19 | CM-EHS-FRM-007 COVID-19 Inspection | 7/4/2020 | 9 | 7/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F126982.2 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 7/4/2020 | 9 | 8/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F124251.6 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/4/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.69 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 6/4/2020 | 6 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.236 | JPC Sign Off / Closed | Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/4/2020 | 8 | 23/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.235 | JPC Sign Off / Closed | 19-L1-03 Stair 3>Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/4/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.234 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 6/4/2020 | 9 | 15/04/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F126982.1 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 6/4/2020 | 9 | 7/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F124251.5 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/4/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.68 | Closed | 19-L3-03 Office 3>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/4/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.67 | Closed | 19-L3-01 Office 1>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/4/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.66 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/4/2020 | 6 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F97233.35 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 3/4/2020 | 9 | 25/05/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.65 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/4/2020 | 6 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F97233.34 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 3/4/2020 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.59 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/4/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.233 | Closed | 19-L2-49 Service Void>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 3/4/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.232 | Closed | 19-L2-10 Culture Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 3/4/2020 | 8 | 16/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.231 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/4/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92636.24 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 3/4/2020 | 9 | 24/04/2020 | 0 | 18 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.78 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/4/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.64 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/4/2020 | 6 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.230 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/4/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.63 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 2/4/2020 | 9 | 15/05/2020 | 0 | 12 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F124251.4 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 2/4/2020 | 9 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F124251.3 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 2/4/2020 | 9 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.370521 | Closed | JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 1/4/2020 | 10 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.58 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/4/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86421.23 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 1/4/2020 | 9 | 22/05/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86424.229 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/4/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.228 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 1/4/2020 | 9 | 15/04/2020 | 0 | 7 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F124251.2 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 1/4/2020 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.77 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.76 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 31/03/2020 | 9 | 19/04/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.369871 | Opened | 01 Inspections>EHS Forms>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 31/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F124251.1 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 31/03/2020 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86424.227 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/03/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F114176.15 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 31/03/2020 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.54 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.226 | Closed | 19-L2-47 Dis WC>WC's>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/03/2020 | 8 | 30/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.225 | JPC Sign Off / Closed | 19-L2-35 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/03/2020 | 8 | 30/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.224 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/03/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.53 | JPC Inspected | 1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 30/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F121399.62 | 3rd Party Sign Off - Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 30/03/2020 | 8 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F121399.61 | Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 30/03/2020 | 8 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F121399.60 | Closed | 19-L3-14 Telepresence Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.59 | Closed | 19-L3-59 Boardroom Lobby>Lobbies>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.58 | Closed | 19-L3-31 Board Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.57 | Closed | 19-L3-32 Executive Kitchen>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/03/2020 | 8 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.56 | Closed | 19-L3-06 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F92044.52 | JPC Inspected | 19-L1-56 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F86424.223 | JPC Sign Off / Closed | 19-L2-35 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/03/2020 | 8 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.222 | Closed | Atrium>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/03/2020 | 8 | 16/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F97233.33 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 27/03/2020 | 9 | 1/4/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.221 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/03/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.219 | JPC Sign Off / Closed | 19-L2-37 Micro Investigation Lab>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/03/2020 | 8 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.54 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 26/03/2020 | 9 | 15/05/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86424.218 | Closed | 19-L2-07 Cold Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 26/03/2020 | 10 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.217 | JPC Sign Off / Closed | 19-L2-45 Data Room>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 26/03/2020 | 8 | 14/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.216 | JPC Sign Off / Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 26/03/2020 | 8 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F92044.51 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92636.23 | Closed | 1330 - Regeneron Building 19 | EHS Inspection. | 26/03/2020 | 9 | 1/4/2020 | 0 | 28 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F86424.215 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/03/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.50 | Closed | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/03/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.49 | Closed | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/03/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.48 | Closed JPC Reviewed | 19-L1-34 Inactive Waste>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 25/03/2020 | 6 | 18/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.47 | Open / Ongoing Works | Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/03/2020 | 8 | 25/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F121399.53 | Closed | 19-L1-03 Stair 3>Stairs>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/03/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.46 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.214 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 25/03/2020 | 9 | 26/03/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.213 | JPC Sign Off / Closed | 19-L2-46 Male WC's>WC's>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/03/2020 | 8 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.212 | JPC Sign Off / Closed | 19-L2-46 Male WC's>WC's>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/03/2020 | 8 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F109023.75 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 24/03/2020 | 9 | 27/03/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.211 | Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 24/03/2020 | 8 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.210 | JPC Sign Off / Closed | 19-L1-28 Goods Lift>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 24/03/2020 | 8 | 14/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.52 | Closed | 19-L3-48 Office 8>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/03/2020 | 8 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.51 | Closed | 19-L3-56- Office 16>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.50 | Closed | 19-L3-55 Office 15>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.49 | Closed | 19-L3-53 Office 13>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 24/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.48 | Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 24/03/2020 | 8 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.47 | JPC Sign Off / Closed | 19-L3-06 Office 6>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 24/03/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F109023.74 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F114176.14 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 23/03/2020 | 9 | 25/05/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.209 | JPC Sign Off / Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 23/03/2020 | 8 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.208 | JPC Sign Off / Closed | 19-L2-44 Fallow Area 2>Fallow Areas>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 23/03/2020 | 8 | 30/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.207 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/03/2020 | 6 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.206 | JPC Sign Off | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 23/03/2020 | 10 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.204 | JPC Sign Off / Closed | 19-L2-19 PS Media and Buffer Prep>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 23/03/2020 | 8 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.203 | 3rd Party Sign Off - Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 23/03/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F97233.32 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 22/03/2020 | 9 | 3/6/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.46 | Closed | 19-L3-54 Office 14>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.45 | Closed | 19-L3-52 Office 12>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.44 | Closed | 19-L3-51 Office 11>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.43 | Closed | 19-L3-50 Office 10>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.42 | JPC Sign Off / Closed | 19-L3-50 Office 10>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 20/03/2020 | 8 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.41 | Closed | 19-L3-49 Office 9>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 20/03/2020 | 8 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.39 | JPC Sign Off / Closed | 19-L3-49 Office 9>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 20/03/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.202 | Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 20/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.201 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/03/2020 | 6 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.200 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/03/2020 | 6 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.38 | Closed | 19-L3-58 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/03/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.37 | Closed | 19-L3-42 Plant Room 2>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/03/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.36 | Closed | 19-L3-40 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/03/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.199 | 3rd Party Sign Off - Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/03/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F114176.13 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/03/2020 | 9 | 25/05/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.198 | 3rd Party Sign Off - Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/03/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F121399.34 | Closed | 19-L3-37 Archive>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/03/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.197 | 3rd Party Sign Off - Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/03/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F121399.31 | Closed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 19/03/2020 | 8 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.30 | JPC Inspected | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 19/03/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F121399.29 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/03/2020 | 9 | 15/05/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.196 | 3rd Party Sign Off - Closed | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/03/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F92636.22 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 19/03/2020 | 9 | 1/4/2020 | 0 | 17 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F86424.195 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/03/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86424.194 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/03/2020 | 9 | 20/03/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.73 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/03/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.44 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/03/2020 | 6 | 14/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.359918 | 3rd Party Sign Off - Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-001 Benchmark / Sample Form | 13/03/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86424.190 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/03/2020 | 9 | 20/03/2020 | 0 | 7 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86424.189 | Closed | 19-L2-45 Data Room>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 13/03/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.188 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/03/2020 | 6 | 18/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.27 | JPC Inspected | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 13/03/2020 | 8 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.26 | Closed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-210 Metalwork Inspection | 13/03/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.25 | Completed and signed off | 03 Safety Notices>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 12/3/2020 | 9 | 18/03/2020 | 0 | 5 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F1.359135 | JPC Sign Off | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 12/3/2020 | 10 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F113852.50 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/3/2020 | 6 | 16/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F92044.43 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 12/3/2020 | 8 | 22/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Open | 4
F92044.40 | Works Complete | 19-L1-56 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | BCAR Inspection Form | 12/3/2020 | 3 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.187 | Closed | JPC Project Management | EHS Inspection. | 12/3/2020 | 9 | 15/06/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.23 | Completed and signed off | 03 Safety Notices>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 12/3/2020 | 9 | 18/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F92044.39 | JPC Inspected | 19-L1-38 Switch room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 12/3/2020 | 8 | 22/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Open | 4
F121399.21 | JPC Sign Off / Closed | 19-L3-40 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 12/3/2020 | 8 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.20 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 12/3/2020 | 6 | 12/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.72 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 11/3/2020 | 9 | 27/03/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.186 | JPC Sign Off / Closed | 19-L2-32 Duct>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 11/3/2020 | 8 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.185 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 11/3/2020 | 8 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.18 | JPC Sign Off / Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.17 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.16 | JPC Sign Off / Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 11/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.184 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 11/3/2020 | 9 | 20/03/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.183 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/3/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F1.357905 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 11/3/2020 | 10 | 11/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F1.357904 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-001 Benchmark / Sample Form | 11/3/2020 | 10 | 11/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F121399.15 | JPC Sign Off / Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.14 | Closed | 19-L3-35 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/3/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F1.357387 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 10/3/2020 | 6 | 10/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 3
F1.357336 | 3rd Party Sign Off - Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 10/3/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F1.357303 | 3rd Party Sign Off - Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 10/3/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F1.357300 | JPC Sign Off | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 10/3/2020 | 10 | 10/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F1.357278 | JPC Sign Off | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 10/3/2020 | 10 | 7/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86424.178 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/3/2020 | 6 | 16/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.177 | JPC Sign Off / Closed | 19-L2-50 Conf Room 3>Conference Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 10/3/2020 | 8 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.176 | JPC Sign Off / Closed | 19-L2-03 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 10/3/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.175 | Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 10/3/2020 | 8 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.174 | JPC Sign Off / Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 10/3/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.356183 | Closed | Training Area | QM-CL-ARC-225-Firestopping Inspection Checklist | 9/3/2020 | 8 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F114176.12 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 9/3/2020 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.173 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/3/2020 | 6 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F97233.31 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 9/3/2020 | 9 | 3/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F97233.30 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 9/3/2020 | 9 | 5/6/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F121399.13 | Closed | 19-L3-38 Automation Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 9/3/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.172 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/3/2020 | 6 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.171 | JPC Sign Off / Closed | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 6/3/2020 | 8 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F113852.49 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/3/2020 | 6 | 11/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F86424.169 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 5/3/2020 | 9 | 5/6/2020 | 0 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.168 | JPC Sign Off / Closed | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 4/3/2020 | 8 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F109023.71 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/3/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.166 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 4/3/2020 | 9 | 20/03/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86424.165 | JPC Sign Off / Closed | 19-L2-30 Stability Chambers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 4/3/2020 | 8 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F109023.70 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 3/3/2020 | 9 | 27/03/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.61 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.393495 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.158 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 18/05/2020 | 6 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.157 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F114176.20 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 18/05/2020 | 9 | 19/05/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F114176.19 | Closed | EHS Forms>JPC Project Management | EHS Inspection. | 18/05/2020 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F127802.9 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 18/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.210 | Open / Ongoing Works | 19-L1-72 Social Area>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/05/2020 | 8 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.209 | Open / Ongoing Works | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/05/2020 | 8 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.208 | Open / Ongoing Works | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/05/2020 | 8 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.351 | Closed | Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 18/05/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.350 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F97233.41 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 15/05/2020 | 9 | 25/05/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F127802.8 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 15/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.349 | Closed | 19-L2-48 Femal WC's>WC's>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/05/2020 | 8 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.348 | Closed | 19-L2-25 Technical Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 15/05/2020 | 8 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.156 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/05/2020 | 6 | 18/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.155 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 15/05/2020 | 6 | 18/05/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F86424.347 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/05/2020 | 6 | 15/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.153 | Closed | 02 Allocation Sheets>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 15/05/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F124251.59 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/05/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.152 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 14/05/2020 | 9 | 18/05/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F127802.7 | Closed | 03 Safety Notices>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.207 | JPC Inspected | 19-L1-12 Facilities Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 14/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.346 | Closed | 19-L2-11 Cold Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 14/05/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.345 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/05/2020 | 6 | 14/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.150 | Closed JPC Reviewed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 14/05/2020 | 6 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.149 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/05/2020 | 6 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.206 | JPC Inspected | 19-L1-40 Meeting Room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 14/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.58 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control & BC(A)R | QM-CL-ME-401 Services Test | 13/05/2020 | 1 | 13/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F121399.148 | Closed | 19-L3-57 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.55 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/05/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.205 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/05/2020 | 6 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F127802.6 | Closed | EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 13/05/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.344 | Closed | 19-L2-05 Electric>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 13/05/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F92044.204 | JPC Inspected | 19-L1-12 Facilities Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.203 | JPC Inspected | 19-L1-12 Facilities Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.202 | JPC Inspected | 19-l1-10 DIS WC>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.201 | Open / Ongoing Works | 19-L1-55 Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/05/2020 | 8 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.200 | JPC Inspected | 19-l1-50 Male Locker>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/05/2020 | 8 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.198 | JPC Inspected | 19-L1-49 Female WC>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.196 | JPC Inspected | 19-L1-47 Male WC>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/05/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.343 | Closed | 19-L2-51 Conf Room 4>Conference Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/05/2020 | 8 | 14/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.146 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/05/2020 | 6 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.342 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/05/2020 | 6 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.145 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/05/2020 | 6 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.341 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/05/2020 | 9 | 13/05/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92636.32 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 13/05/2020 | 9 | 23/05/2020 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F124251.54 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/5/2020 | 6 | 17/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.195 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/5/2020 | 6 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.194 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 12/5/2020 | 9 | 20/05/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.340 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/5/2020 | 6 | 12/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92636.31 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/5/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.389144 | JPC Sign Off / Closed | 1330 - Regeneron Building 19 | QM-CL-ARC-206 Painting Inspection | 12/5/2020 | 8 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F114176.18 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 12/5/2020 | 9 | 15/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F127802.5 | Closed | JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/5/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.193 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/5/2020 | 6 | 12/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.388610 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-CL-ARC-206 Painting Inspection | 11/5/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F121399.144 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 11/5/2020 | 8 | 12/5/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F92044.192 | Closed | Meeting 6>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.143 | Closed | 19-L3-17 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.191 | JPC Inspected | Meeting 5>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.142 | Closed | 19-L3-60 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.188 | JPC Inspected | Meeting 5>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.187 | JPC Inspected | Meeting 5>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.186 | JPC Inspected | Meeting 4>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.185 | JPC Inspected | Meeting 4>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.184 | JPC Inspected | Meeting 3>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.183 | JPC Inspected | Meeting 3>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.182 | JPC Inspected | 19-L1-40 Meeting Room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.181 | JPC Inspected | 19-L1-40 Meeting Room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.180 | JPC Inspected | 19-L1-40 Meeting Room>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.179 | JPC Inspected | Meeting 6>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.177 | JPC Inspected | Meeting 6>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.140 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/5/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.339 | Closed | 19-L2-04 Electric>Services and Risers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 11/5/2020 | 8 | 13/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.53 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/5/2020 | 6 | 17/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.338 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.337 | Closed | Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.139 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/5/2020 | 6 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.335 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/5/2020 | 8 | 15/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F97233.40 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 10/5/2020 | 9 | 19/05/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.388025 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-008 Non Conformance Record (NCR) | 8/5/2020 | 10 | 8/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.176 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F127802.4 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/5/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F1.387951 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/5/2020 | 8 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.175 | 3rd Party Sign Off - Closed | 19-l1-07 Gen purpose 3>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/5/2020 | 8 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F1.387950 | JPC Sign Off | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/5/2020 | 8 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.334 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/5/2020 | 8 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.333 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/5/2020 | 8 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.332 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/5/2020 | 8 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.331 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/5/2020 | 8 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.330 | 3rd Party Sign Off - Closed | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/5/2020 | 8 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.52 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/5/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.387924 | JPC Sign Off | 19-L1-11 Dat Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 8/5/2020 | 8 | 8/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.328 | Closed | 19-L2-09 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 8/5/2020 | 8 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.327 | Closed | 19-L1-67 Per Lift>Lifts>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/5/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.326 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/5/2020 | 6 | 8/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.325 | Closed | 19-L2-45 Data Room>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 8/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.172 | Open / Ongoing Works | 19-L1-38 Switch room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 8/5/2020 | 10 | 8/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.171 | Closed | Data Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 8/5/2020 | 10 | 24/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.170 | JPC Inspected | Data Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 8/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.169 | Open / Ongoing Works | 19-l1-36 - Incoming Staging>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 8/5/2020 | 8 | 8/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.168 | Open / Ongoing Works | Data Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 8/5/2020 | 8 | 8/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.324 | Closed | 19-L2-54 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/5/2020 | 8 | 8/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.138 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.137 | Closed | 19-L3-40 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 7/5/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.136 | Closed | 19-L3-37 Archive>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 7/5/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F121399.135 | Closed | 19-L3-36 Electrical Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 7/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.134 | Closed | 19-L3-40 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 7/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.131 | Closed | 19-L3-30 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 7/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.130 | Closed | 19-L3-10 Open Office>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.129 | Closed | 19-L3-09 Conference Room>Conference Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.127 | Closed | 19-L1-02 Stair 2>Stairs>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.51 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/5/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.323 | Closed | 19-L2-57 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 8/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.322 | Closed | 19-L2-45 Data Room>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 7/5/2020 | 8 | 8/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F124251.50 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/5/2020 | 6 | 12/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.49 | JPC Inspected | 19-L1-39 Conf Room>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F124251.48 | JPC Inspected | 19-L1-39 Conf Room>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.47 | JPC Inspected | 19-L1-04 Stair 4>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.46 | Open / Ongoing Works | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 7/5/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.45 | JPC Inspected | 19-L1-38 Switch room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.44 | JPC Inspected | 19-L1-03 Stair 3W>Stairs>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 7/5/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F124251.43 | Open / Ongoing Works | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 7/5/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F127802.3 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 7/5/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F124251.42 | JPC Inspected | Meeting 1>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F124251.41 | JPC Inspected | 19-L1-56 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.40 | JPC Inspected | Meeting 2>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.321 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/5/2020 | 6 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F124251.39 | JPC Inspected | Meeting 1>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.38 | JPC Inspected | Meeting 1>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.320 | Closed | 19-L2-15 Janitors Store>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 7/5/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.319 | Closed | 19-L2-19 PS Media and Buffer Prep>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-206 Painting Inspection | 7/5/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.37 | JPC Inspected | Meeting 3>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.36 | JPC Inspected | Meeting 2>Meeting Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F124251.35 | JPC Inspected | 19-L1-54 Janitor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.126 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 7/5/2020 | 9 | 11/5/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.167 | JPC Inspected | 19-L1-56 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 7/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F121399.125 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F124251.34 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/5/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.166 | JPC Inspected | 19-L1-56 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.165 | Open / Ongoing Works | 19-L1-72 Social Area>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 6/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.162 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92636.30 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 6/5/2020 | 9 | 12/5/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92636.29 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 6/5/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.318 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/5/2020 | 6 | 6/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.386486 | Closed | JPC Project Management | JPC-HR-FRM-001 - Training Record | 6/5/2020 | 2 | 6/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F92044.161 | JPC Inspected | 19-L1-69 disabled WC>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.160 | JPC Inspected | 19-L1-69 disabled WC>WC's & Locker Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.317 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 6/5/2020 | 9 | 11/5/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.159 | JPC Inspected | Conf Room 5>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.158 | JPC Inspected | Conf Room 4>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.157 | JPC Inspected | Conf Room 5>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.156 | JPC Inspected | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F121399.123 | Closed | 19-l3-19 Dis WC>WC's & Shower Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.122 | Closed | 19-L3-20 Female WC>WC's & Shower Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.121 | Closed | 19-L3-21 Male WC>WC's & Shower Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.120 | Closed | 19-L3-16 Janitors Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.119 | Closed | 19-L3-33 Open Offices 2>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.316 | Closed | 19-L2-43 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.315 | Closed | 19-L2-56 Social Space>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 8/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.314 | Closed | 19-L2-40 Lobby>Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 8/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.313 | Closed | Fallow Areas>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 6/5/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F124251.33 | Open / Ongoing Works | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/5/2020 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F124251.32 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/5/2020 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F124251.31 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/5/2020 | 6 | 14/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.155 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/5/2020 | 6 | 6/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.154 | JPC Inspected | 19-L1-56 Store>Stores>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 5/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 4
F121399.118 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/5/2020 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.88 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 5/5/2020 | 9 | 20/05/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.312 | Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006A Element Handover | 5/5/2020 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.117 | Closed | 19-L3-40 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 5/5/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.310 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F121399.116 | Closed | 19-L3-30 Data Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-212 Floor Finish Inspection | 5/5/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F92636.28 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/5/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F121399.115 | Closed | 19-L3-26 Male Toilet>WC's & Shower Rooms>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 5/5/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.152 | Closed | Data Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006 Area Handover | 5/5/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.149 | Open / Ongoing Works | 19-L1-11 Dat Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-006A Element Handover | 5/5/2020 | 6 | 5/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F97233.39 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 4/5/2020 | 9 | 25/05/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.384686 | Closed | 1st Floor Plan>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 1/5/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F1.384657 | Closed | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 1/5/2020 | 6 | 22/05/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F121399.114 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-006A Element Handover | 1/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.113 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 1/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.112 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-006 Area Handover | 1/5/2020 | 6 | 11/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F121399.111 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/5/2020 | 6 | 1/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.309 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/5/2020 | 6 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.308 | Closed | 19-L2-35 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 1/5/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.307 | Closed | 19-L2-44 Fallow Area 2>Fallow Areas>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 1/5/2020 | 8 | 11/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F1.384391 | Open / Ongoing Works | 1330 - Regeneron Building 19 | QM-FRM-QC-009 Quality Control Record | 1/5/2020 | 10 | 1/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.147 | JPC Inspected | Conf Room 2>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 1/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F92044.146 | JPC Inspected | Conf Room 1>Conference Rooms>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 1/5/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F127802.2 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 1/5/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.145 | 3rd Party Sign Off - Closed | 19-L1-11 Dat Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 1/5/2020 | 8 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.110 | JPC Sign Off | 19-L3-02 PA Area>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 1/5/2020 | 10 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F109023.87 | JPC Inspected | 1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-225-Firestopping Inspection Checklist | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F109023.86 | JPC Inspected | 1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-210 Metalwork Inspection | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F109023.85 | JPC Inspected | 1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 30/04/2020 | 8 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F1.384067 | Works Complete / Resolved | 1330 - Regeneron Building 19 | QM-FRM-QC-001 Benchmark / Sample Form | 30/04/2020 | 10 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86421.26 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 30/04/2020 | 9 | 12/6/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F1.384036 | Works Complete / Resolved | 1330 - Regeneron Building 19 | QM-FRM-QC-001 Benchmark / Sample Form | 30/04/2020 | 10 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F1.384026 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-006A Element Handover | 30/04/2020 | 6 | 30/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F86421.25 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-008 Non Conformance Record (NCR) | 30/04/2020 | 10 | 30/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.164 | JPC Sign Off / Closed | 19-L2-18 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 3/3/2020 | 8 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.163 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/3/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.69 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/3/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.162 | Closed | 19-L1-38 Switch room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 2/3/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.161 | JPC Inspected | 19-L1-36 Cent Lab Store>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 2/3/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.160 | Closed | 19-l1-36 - Incoming Staging>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 2/3/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.159 | Closed | 19-L1-32 Waste Staging>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 2/3/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.158 | Closed | 19-L1-28 Goods Lift>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 2/3/2020 | 8 | 1/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F114176.11 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 2/3/2020 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86421.22 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 29/02/2020 | 10 | 29/02/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86421.21 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 29/02/2020 | 9 | 22/05/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F97233.29 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/02/2020 | 9 | 5/6/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.65 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.157 | JPC Inspected | 19-L1-38 Switch room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/02/2020 | 8 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 4
F86424.154 | JPC Sign Off / Closed | Data Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/02/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.153 | Closed | 19-L1-11 Dat Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 28/02/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.11 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F121399.10 | Closed | 04 Progress Photos>Site Management>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 28/02/2020 | 10 | 28/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92636.21 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 28/02/2020 | 9 | 5/6/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F1.349489 | JPC Sign Off | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 27/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86430.21 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 27/02/2020 | 9 | 8/5/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.152 | JPC Sign Off / Closed | Utillities Corridor>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/02/2020 | 8 | 28/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.151 | JPC Sign Off / Closed | 19-L1-38 Switch room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.150 | JPC Sign Off / Closed | 19-L1-38 Switch room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.149 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/02/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.148 | JPC Sign Off / Closed | Stairs>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/02/2020 | 8 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F121399.9 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 27/02/2020 | 9 | 15/05/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F1.348902 | Open / Ongoing Works | 1330 - Regeneron Building 19 | JPC-QA-RP-003 - Site Audit Report | 27/02/2020 | 2 | 27/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 3
F121399.8 | Closed | Goods Lifts>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/02/2020 | 8 | 7/5/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.7 | Closed | 19-L3-38 Automation Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 27/02/2020 | 8 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.147 | JPC Inspected | 19-L1-25 Boiler Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 26/02/2020 | 8 | 22/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Open | 4
F86424.146 | JPC Sign Off / Closed | Data Room>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 26/02/2020 | 8 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.145 | JPC Sign Off / Closed | 19-L1-28 Goods Lift>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 26/02/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.144 | JPC Sign Off / Closed | 19-L2-20 Cell Bank>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 26/02/2020 | 8 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.348487 | JPC Sign Off | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 26/02/2020 | 10 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F121399.6 | Closed | 19-L3-34 Plant Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 26/02/2020 | 8 | 12/7/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.143 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F1.348406 | JPC Sign Off | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 26/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F1.348378 | JPC Sign Off | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 26/02/2020 | 10 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F86424.140 | JPC Sign Off / Closed | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 26/02/2020 | 8 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.139 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 26/02/2020 | 9 | 2/3/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.138 | Closed | 19-L1-28 Goods Lift>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/02/2020 | 8 | 16/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F109023.64 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 25/02/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.63 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 25/02/2020 | 9 | 19/04/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.347568 | Open / Ongoing Works | 1330 - Regeneron Building 19 | JPC-QA-RP-003 - Site Audit Report | 25/02/2020 | 2 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F121401.1 | Closed JPC Reviewed | 3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 25/02/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.136 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F95601.3 | Closed | 1330 - Regeneron Building 19 | JPC-HR-FRM-001 - Training Record | 25/02/2020 | 2 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.347367 | Open / Ongoing Works | 1330 - Regeneron Building 19 | JPC-QA-RP-003 - Site Audit Report | 25/02/2020 | 2 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F86424.135 | JPC Sign Off / Closed | 19-L1-30 Decon>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.134 | JPC Sign Off / Closed | 19-L1-32 Waste Staging>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.133 | JPC Sign Off / Closed | 19-L2-29 Clean Hold>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.132 | JPC Sign Off / Closed | 19-L2-30 Stability Chambers>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.131 | JPC Sign Off / Closed | 19-L2-20 Cell Bank>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/02/2020 | 8 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.130 | JPC Sign Off | 19-L2-22 Corridor>Corridors>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 25/02/2020 | 10 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F121399.3 | JPC Sign Off / Closed | 19-L3-50 Office 10>Offices>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 25/02/2020 | 8 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F121399.2 | Closed | 19-L3-35 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/02/2020 | 8 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.129 | JPC Sign Off / Closed | Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/02/2020 | 8 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F114176.10 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 25/02/2020 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.128 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/02/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F97233.26 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 23/02/2020 | 9 | 5/6/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.127 | JPC Sign Off / Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 21/02/2020 | 8 | 21/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.126 | JPC Inspected | Lifts>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 21/02/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.125 | JPC Inspected | 19-L2-34 Freezer Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 21/02/2020 | 8 | 22/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Open | 4
F86424.124 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/02/2020 | 6 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.62 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F109023.61 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86430.20 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 20/02/2020 | 9 | 20/02/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F86424.123 | Closed | 19-L1-70 Open Office 2>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 19/02/2020 | 8 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.122 | JPC Inspected | 19-L1-13 Open office>Offices>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 19/02/2020 | 8 | 22/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Open | 4
F86424.121 | JPC Sign Off / Closed | 19-L2-35 Open Office>Offices>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-210 Metalwork Inspection | 19/02/2020 | 8 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.120 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.118 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/02/2020 | 9 | 6/3/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.36 | JPC Sign Off | 19-L3-35 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/02/2020 | 10 | 19/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F92044.35 | JPC Sign Off | 19-L3-35 Corridor>Corridors>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/02/2020 | 10 | 19/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86424.117 | JPC Sign Off / Closed | 19-L2-23 (-40) Cold Room>Cold / Freezer Rooms>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 19/02/2020 | 8 | 19/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.116 | Closed | 19-L2-26 Storage>Stores>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/02/2020 | 8 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F109023.60 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/02/2020 | 9 | 19/04/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.115 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.114 | Closed | 19-L2-24 Lobby>Lobbies>2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 18/02/2020 | 8 | 16/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F109023.59 | Closed | JPC Project Management | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 18/02/2020 | 10 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.113 | JPC Sign Off / Closed | 19-L1-14 Phone Booths>1st Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-202 Partitions Inspection | 17/02/2020 | 8 | 19/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.111 | JPC Sign Off / Closed | 1330 - Regeneron Building 19 | QM-CL-ARC-202 Partitions Inspection | 17/02/2020 | 8 | 19/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.341897 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 17/02/2020 | 6 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F86424.108 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/02/2020 | 6 | 26/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F86424.107 | JPC Sign Off | 19-L3-38 Automation Room>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/02/2020 | 10 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86424.106 | JPC Sign Off | 19-L3-37 Archive>3rd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/02/2020 | 10 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F86424.105 | JPC Sign Off | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/02/2020 | 10 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86424.104 | 3rd Party Sign Off - Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/02/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86424.103 | 3rd Party Sign Off - Closed | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/02/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86424.102 | JPC Sign Off | 2nd Floor Plan>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/02/2020 | 10 | 28/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F97233.25 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 17/02/2020 | 9 | 5/6/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86430.19 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 14/02/2020 | 9 | 14/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F86430.18 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 14/02/2020 | 9 | 8/5/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92636.20 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 14/02/2020 | 9 | 1/4/2020 | 0 | 21 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.99 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F1.340000 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 13/02/2020 | 10 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F113852.48 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/02/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F114176.9 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/02/2020 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.47 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/2/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86424.98 | Closed | JPC Project Management | QM-FRM-QC-004 QC Observation Report | 12/2/2020 | 10 | 9/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.97 | Closed JPC Reviewed | JPC Project Management | QM-FRM-QC005 - Training Record | 12/2/2020 | 10 | 12/2/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F113852.46 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 12/2/2020 | 9 | 6/3/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.58 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 11/2/2020 | 9 | 19/04/2020 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.57 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/2/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F109023.56 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/2/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.55 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/2/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F113852.45 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/2/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F97233.24 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 9/2/2020 | 9 | 5/6/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86421.20 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 7/2/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F113852.44 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/2/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86430.17 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 6/2/2020 | 9 | 9/7/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.43 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/2/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86430.16 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 6/2/2020 | 9 | 6/2/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F113852.42 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/2/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.34 | Closed | EHS Forms>JPC Project Management | EHS Inspection. | 5/2/2020 | 9 | 6/3/2020 | 0 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F1.333703 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 5/2/2020 | 6 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F113852.40 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 5/2/2020 | 9 | 6/3/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.54 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 4/2/2020 | 9 | 19/04/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.39 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/2/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F113852.37 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/2/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F114176.8 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 3/2/2020 | 9 | 25/05/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F114176.7 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 3/2/2020 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F114176.6 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 3/2/2020 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.32 | Closed JPC Reviewed | JPC Project Management | QM-FRM-QC005 - Training Record | 3/2/2020 | 10 | 3/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 4
F1.331599 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/2/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F1.331597 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 3/2/2020 | 6 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F97233.23 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 1/2/2020 | 9 | 5/6/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86421.18 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 31/01/2020 | 9 | 22/05/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F114176.5 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CE-315-Liner Installation Inspection | 31/01/2020 | 7 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F113852.35 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92636.19 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 30/01/2020 | 9 | 6/2/2020 | 0 | 11 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.330136 | JPC Sign Off | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 30/01/2020 | 10 | 30/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86430.14 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 30/01/2020 | 9 | 30/01/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F113852.34 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F113852.33 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/01/2020 | 9 | 6/3/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.32 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.53 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 28/01/2020 | 9 | 24/04/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F114176.4 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 27/01/2020 | 9 | 25/05/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.31 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86418.12 | Closed | JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 24/01/2020 | 10 | 27/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F97233.22 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 24/01/2020 | 9 | 5/6/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.29 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.30 | Closed | EHS Forms>JPC Project Management | EHS Inspection. | 24/01/2020 | 9 | 6/2/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F113852.28 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86430.13 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 23/01/2020 | 9 | 23/01/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F1.324910 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 23/01/2020 | 6 | 23/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 3
F86418.11 | Closed | JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 22/01/2020 | 10 | 27/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F113852.27 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F113852.26 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 22/01/2020 | 9 | 3/3/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.52 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 21/01/2020 | 9 | 8/5/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.25 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F114176.3 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 21/01/2020 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F113852.24 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F92044.29 | 3rd Party Sign Off - Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 20/01/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F92044.28 | 3rd Party Sign Off - Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 20/01/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F113852.23 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F97233.21 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 18/01/2020 | 9 | 5/6/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F113852.22 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/01/2020 | 6 | 26/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F1.321725 | 3rd Party Sign Off - Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 17/01/2020 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F1.321721 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 17/01/2020 | 10 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F113852.20 | Closed | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F95601.2 | Closed | 1330 - Regeneron Building 19 | JPC-HR-FRM-001 - Training Record | 16/01/2020 | 2 | 16/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.51 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/01/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F113852.17 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 16/01/2020 | 6 | 23/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92636.18 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 16/01/2020 | 9 | 22/01/2020 | 0 | 19 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86430.12 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 16/01/2020 | 9 | 8/5/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.16 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/01/2020 | 6 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F113852.15 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 15/01/2020 | 9 | 3/3/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.14 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/01/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.50 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 14/01/2020 | 9 | 19/04/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.49 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/01/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F86421.15 | Closed | Site Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 14/01/2020 | 10 | 12/6/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.318847 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 14/01/2020 | 6 | 14/01/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F114176.2 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/01/2020 | 9 | 25/05/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.48 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/01/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 3
F97233.20 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 12/1/2020 | 9 | 5/6/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92636.17 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 10/1/2020 | 9 | 22/01/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.13 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/1/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F113852.12 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/1/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86430.11 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 9/1/2020 | 9 | 8/5/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86430.10 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 9/1/2020 | 9 | 8/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F86430.9 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 9/1/2020 | 9 | 8/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F109023.47 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 8/1/2020 | 6 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F113852.10 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 8/1/2020 | 9 | 3/3/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.9 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 8/1/2020 | 9 | 3/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F113852.7 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 8/1/2020 | 9 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.46 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 7/1/2020 | 9 | 20/05/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F113852.5 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/1/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F113852.4 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/1/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.45 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 6/1/2020 | 6 | 6/1/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F109023.43 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 6/1/2020 | 6 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F109023.42 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 6/1/2020 | 6 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F114176.1 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 6/1/2020 | 9 | 25/05/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.41 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 6/1/2020 | 6 | 6/1/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F113852.2 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/1/2020 | 6 | 3/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F113852.1 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/1/2020 | 6 | 2/1/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F86430.7 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 2/1/2020 | 9 | 2/1/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F86430.6 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 19/12/2019 | 9 | 1/1/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.311389 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 18/12/2019 | 9 | 1/1/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 2
F109023.40 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 16/12/2019 | 6 | 16/12/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F92044.27 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 16/12/2019 | 9 | 1/1/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.39 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 15/12/2019 | 6 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F97233.19 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 15/12/2019 | 9 | 1/1/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92636.16 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 12/12/2019 | 9 | 22/01/2020 | 0 | 17 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86430.5 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 12/12/2019 | 9 | 1/1/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86430.4 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 12/12/2019 | 9 | 12/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F109023.38 | Open / Ongoing Works | JPC Project Management | SM-FRM-001 Daily Site Diary | 11/12/2019 | 6 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F109023.37 | Closed | JPC Project Management | SM-FRM-001 Daily Site Diary | 11/12/2019 | 6 | 24/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.35 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 11/12/2019 | 6 | 11/12/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F109023.34 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 10/12/2019 | 9 | 1/1/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.305932 | Closed | 1330 - Regeneron Building 19 | EHS Inspection. | 10/12/2019 | 9 | 12/12/2019 | 0 | 13 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F109023.33 | Open / Ongoing Works | 1330 - Regeneron Building 19 | SM-FRM-001 Daily Site Diary | 9/12/2019 | 6 | 9/12/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F109023.32 | Closed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/12/2019 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.31 | Open | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 7/12/2019 | 6 | 7/12/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 3
F97233.18 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 7/12/2019 | 9 | 1/1/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86430.3 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 5/12/2019 | 9 | 1/1/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86424.93 | Closed | Ground Floor GA>02 Co-ordinated Service Drawings>ITP 04 M&E Services>Quality Control & BC(A)R | QM-CL-ME-403 Mechanical Inspection | 5/12/2019 | 1 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F109023.30 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 5/12/2019 | 6 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.26 | Closed JPC Reviewed | 3rd Floor Plan>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | SM-FRM-002 Progress Record | 4/12/2019 | 6 | 4/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.25 | Closed JPC Sign Off | 3rd Floor Plan>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 4/12/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.24 | Closed JPC Reviewed | JPC Project Management | SM-FRM-002 Progress Record | 4/12/2019 | 6 | 22/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.29 | Closed JPC Reviewed | JPC Project Management | SM-FRM-001 Site Diary | 3/12/2019 | 6 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F1.302348 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 3/12/2019 | 10 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F109023.28 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 3/12/2019 | 9 | 19/04/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F109023.27 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/12/2019 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.26 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 2/12/2019 | 6 | 1/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.301536 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-002 Progress Record | 2/12/2019 | 6 | 2/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F93432.9 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 2/12/2019 | 9 | 25/05/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86421.13 | Closed | 01 Inspections>EHS Forms>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 2/12/2019 | 9 | 22/05/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F92636.15 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 29/11/2019 | 9 | 5/12/2019 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.25 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 29/11/2019 | 6 | 1/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.24 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 29/11/2019 | 6 | 1/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86430.2 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 28/11/2019 | 9 | 1/1/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.23 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 28/11/2019 | 9 | 28/11/2019 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F109023.21 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 27/11/2019 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.20 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 27/11/2019 | 6 | 1/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.19 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 27/11/2019 | 6 | 1/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.18 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 26/11/2019 | 6 | 1/1/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.17 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 26/11/2019 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.16 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 26/11/2019 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.15 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 26/11/2019 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.13 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 26/11/2019 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F109023.11 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 26/11/2019 | 9 | 19/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.10 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 26/11/2019 | 9 | 3/1/2020 | 0 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F109023.9 | Completed and signed off | JPC Project Management | CM-SM-FRM-002 White Board Meeting | 26/11/2019 | 6 | 19/04/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.8 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 26/11/2019 | 6 | 1/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F109023.7 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/11/2019 | 6 | 19/04/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F109023.6 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 25/11/2019 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F93432.8 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 25/11/2019 | 9 | 25/05/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F97233.17 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 24/11/2019 | 9 | 5/6/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F97233.16 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 21/11/2019 | 9 | 5/6/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.91 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 21/11/2019 | 9 | 21/11/2019 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F92636.14 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 21/11/2019 | 9 | 29/11/2019 | 0 | 15 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.5 | Completed and signed off | JPC Project Management | CM-SM-FRM-002 White Board Meeting | 20/11/2019 | 6 | 19/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.294908 | 3rd Party Sign Off - Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 20/11/2019 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F1.294905 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 20/11/2019 | 10 | 3/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.90 | Opened | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 20/11/2019 | 9 | 20/11/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F109023.4 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/11/2019 | 9 | 19/04/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F93432.7 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 18/11/2019 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F92636.13 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 15/11/2019 | 9 | 22/11/2019 | 0 | 11 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F97233.15 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 14/11/2019 | 9 | 5/6/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.22 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 14/11/2019 | 9 | 3/1/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F97233.14 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 14/11/2019 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F109023.3 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/11/2019 | 9 | 19/04/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F109023.2 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/11/2019 | 9 | 19/04/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F93432.6 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/11/2019 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.89 | Opened | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/11/2019 | 9 | 13/11/2019 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F92636.12 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 8/11/2019 | 9 | 16/11/2019 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.88 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 8/11/2019 | 9 | 25/05/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.21 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 7/11/2019 | 9 | 7/11/2019 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F92636.11 | Closed | EHS Forms>JPC Project Management | EHS Inspection. | 7/11/2019 | 9 | 22/01/2020 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86418.10 | Completed and signed off | JPC Project Management | CM-SM-FRM-002 White Board Meeting | 6/11/2019 | 6 | 3/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.286774 | Open / Ongoing Works | Ground Floor Plan>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 6/11/2019 | 10 | 19/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F92044.20 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 5/11/2019 | 9 | 6/11/2019 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F93432.5 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 4/11/2019 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.285453 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 6/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285452 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 6/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285448 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 6/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285447 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 6/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285446 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285445 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285442 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285440 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285438 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285437 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.285436 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 4/11/2019 | 6 | 4/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F92636.10 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 1/11/2019 | 9 | 10/11/2019 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.19 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 31/10/2019 | 9 | 31/10/2019 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Open | 2
F1.283204 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 30/10/2019 | 6 | 8/5/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.87 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/10/2019 | 9 | 4/11/2019 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86418.9 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 29/10/2019 | 6 | 29/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92636.9 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 25/10/2019 | 9 | 1/11/2019 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.84 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 24/10/2019 | 9 | 24/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F97233.13 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 24/10/2019 | 9 | 5/6/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.83 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 22/10/2019 | 9 | 4/11/2019 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F1.277967 | Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-007 Lessons Learned Report | 22/10/2019 | 10 | 27/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F1.276707 | Closed | Ground Floor Plan>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-007 Lessons Learned Report | 18/10/2019 | 10 | 27/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86418.8 | 3rd Party Sign Off - Closed | JPC Project Management | QM-FRM-QC-001 Benchmark / Sample Form | 18/10/2019 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F92636.8 | Closed | EHS Forms>JPC Project Management | EHS Inspection. | 18/10/2019 | 9 | 1/4/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F97233.12 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 18/10/2019 | 9 | 5/6/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.82 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 17/10/2019 | 9 | 17/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F86424.81 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 17/10/2019 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.80 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 17/10/2019 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.275412 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/10/2019 | 6 | 17/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.275411 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/10/2019 | 6 | 17/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.275410 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/10/2019 | 6 | 17/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.275409 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/10/2019 | 6 | 17/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.275408 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/10/2019 | 6 | 17/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.275407 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 16/10/2019 | 6 | 17/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F86424.78 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 15/10/2019 | 9 | 16/10/2019 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86418.7 | Closed | Site Management>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 14/10/2019 | 10 | 27/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F97233.11 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 14/10/2019 | 9 | 14/10/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86421.12 | Closed | Site Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 11/10/2019 | 10 | 11/10/2019 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.77 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 10/10/2019 | 9 | 10/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F1.271761 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 9/10/2019 | 6 | 16/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.271760 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 9/10/2019 | 6 | 16/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.271759 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 9/10/2019 | 6 | 16/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F86424.76 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 8/10/2019 | 9 | 8/10/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F97233.10 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 8/10/2019 | 9 | 5/6/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F93432.4 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 7/10/2019 | 9 | 25/05/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.18 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 3/10/2019 | 9 | 3/10/2019 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F92044.16 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 3/10/2019 | 9 | 3/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 2
F1.268249 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 16/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268248 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268247 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268246 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268245 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268244 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268243 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268242 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268241 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268240 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268224 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268223 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268222 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268221 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268220 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268219 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268218 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268217 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268216 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268215 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268214 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268213 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.268212 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 2/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F96080.2 | Closed | EHS Forms>JPC Project Management | EHS Inspection. | 2/10/2019 | 9 | 15/06/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F1.267563 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267562 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267561 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267560 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267559 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267558 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267557 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267556 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267555 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267554 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267553 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267552 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267551 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267550 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267549 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267548 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267547 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267546 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267545 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267544 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267543 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267542 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267541 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267540 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267539 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267538 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267537 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267536 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.267535 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 1/10/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F86424.75 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 1/10/2019 | 9 | 2/10/2019 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F86424.66 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 30/09/2019 | 9 | 25/05/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F97233.9 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 30/09/2019 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F97233.8 | JPC Inspected | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-002a Off Site Inspection - Concrete Precast | 30/09/2019 | 10 | 30/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F97233.7 | In Process / Manufactor | Site Management>JPC Project Management | QM-FRM-QC-002 Off Site Inspection | 30/09/2019 | 10 | 30/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F97233.6 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/09/2019 | 9 | 5/6/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92636.7 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 27/09/2019 | 6 | 27/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92636.6 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 26/09/2019 | 6 | 27/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92636.5 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 26/09/2019 | 9 | 1/4/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86418.6 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 25/09/2019 | 6 | 25/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92636.4 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 25/09/2019 | 6 | 25/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.263518 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 24/09/2019 | 6 | 25/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92636.3 | Completed and signed off | Site Management>JPC Project Management | CM-SM-FRM-002 White Board Meeting | 24/09/2019 | 6 | 24/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92636.2 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 24/09/2019 | 9 | 25/09/2019 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.263242 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 23/09/2019 | 6 | 24/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F92044.15 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 23/09/2019 | 9 | 23/09/2019 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F92044.14 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 23/09/2019 | 9 | 1/7/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86418.5 | Closed | JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 22/09/2019 | 10 | 27/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F92044.13 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 20/09/2019 | 9 | 25/09/2019 | 0 | 11 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.262081 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 19/09/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.262077 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 19/09/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F97233.5 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/09/2019 | 9 | 5/6/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F92044.12 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 19/09/2019 | 9 | 19/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F93432.3 | Completed and signed off | Site Management>JPC Project Management | EHS Managment Inspection - Daily | 18/09/2019 | 9 | 25/05/2020 | 0 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F86424.64 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 17/09/2019 | 9 | 18/09/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F97233.4 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 15/09/2019 | 9 | 5/6/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F93432.2 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 13/09/2019 | 6 | 19/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.259469 | Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 13/09/2019 | 11 | 9/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F92044.11 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 13/09/2019 | 9 | 20/09/2019 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.259082 | JPC Sign Off / Closed | Ground Floor Plan>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 12/9/2019 | 10 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 4
F92044.10 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 12/9/2019 | 9 | 12/9/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 2
F86418.3 | JPC Sign Off / Closed | Ground Floor Plan>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-008 Non Conformance Record (NCR) | 11/9/2019 | 10 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F1.258308 | Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 11/9/2019 | 11 | 9/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86418.2 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 10/9/2019 | 6 | 27/09/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.63 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 10/9/2019 | 9 | 10/9/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.9 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 9/9/2019 | 9 | 18/09/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.256371 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2019 | 6 | 8/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.256370 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2019 | 6 | 8/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.256368 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2019 | 6 | 8/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.256367 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2019 | 6 | 8/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.256366 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2019 | 6 | 8/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.256365 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2019 | 6 | 8/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.256364 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2019 | 6 | 8/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F1.256363 | Closed JPC Reviewed | 04 Progress Photos>Site Management>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2019 | 6 | 8/9/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86421.11 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 5/9/2019 | 9 | 12/6/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F92044.8 | Opened | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 5/9/2019 | 9 | 5/9/2019 | 0 | 3 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 2
F97233.3 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 4/9/2019 | 9 | 5/6/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.62 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 3/9/2019 | 9 | 3/9/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86422.5 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 3/9/2019 | 9 | 15/06/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86421.10 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 2/9/2019 | 10 | 2/9/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Open | 4
F86421.9 | Open / Ongoing Works | Site Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 2/9/2019 | 10 | 12/1/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Open | 4
F86422.4 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 1/9/2019 | 9 | 15/06/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.61 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 30/08/2019 | 9 | 13/09/2019 | 0 | 11 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.60 | Closed JPC Sign Off | 03 Ducting>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-108 Underground Services Test | 29/08/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.59 | Closed JPC Sign Off | 03 Ducting>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 29/08/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.58 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/08/2019 | 9 | 25/05/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.56 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/08/2019 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F97233.2 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/08/2019 | 9 | 5/6/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.53 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 28/08/2019 | 9 | 28/08/2019 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.52 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 28/08/2019 | 9 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.7 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 27/08/2019 | 9 | 27/08/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86422.3 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 26/08/2019 | 9 | 15/06/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F92044.6 | Closed JPC Sign Off | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 23/08/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F92044.5 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 23/08/2019 | 9 | 23/08/2019 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.249383 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 22/08/2019 | 6 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.249370 | JPC Sign Off | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 22/08/2019 | 10 | 22/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F92044.4 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 22/08/2019 | 9 | 4/9/2019 | 0 | 17 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.248549 | 3rd Party Sign Off - Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 21/08/2019 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F86424.51 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 21/08/2019 | 9 | 21/08/2019 | 0 | 3 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F86424.50 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/08/2019 | 9 | 23/08/2019 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.246285 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 16/08/2019 | 6 | 16/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.49 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 15/08/2019 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.245518 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 15/08/2019 | 6 | 15/08/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 3
F1.245473 | Open | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 15/08/2019 | 6 | 15/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 3
F1.244672 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 14/08/2019 | 6 | 14/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.48 | Closed JPC Sign Off | Foul Water>02 Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 14/08/2019 | 7 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.47 | Closed JPC Sign Off | Foul Water>02 Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 14/08/2019 | 7 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.46 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 13/08/2019 | 9 | 13/08/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.243918 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 13/08/2019 | 6 | 13/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.45 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 12/8/2019 | 9 | 23/08/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.243211 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 12/8/2019 | 6 | 12/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.242063 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 9/8/2019 | 6 | 9/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.44 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 9/8/2019 | 9 | 4/9/2019 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.241460 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 8/8/2019 | 6 | 8/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.241047 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 7/8/2019 | 6 | 7/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.240383 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 6/8/2019 | 6 | 6/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.240068 | Open | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 6/8/2019 | 6 | 23/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Open | 3
F1.240067 | Open | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 6/8/2019 | 6 | 6/8/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Open | 3
F1.240061 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 6/8/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1330 | Closed | 3
F1.239002 | Closed | Site Management>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 2/8/2019 | 10 | 15/06/2020 | 0 | 1 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F92044.3 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 2/8/2019 | 9 | 8/8/2019 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.43 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 2/8/2019 | 9 | 23/08/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.238760 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 2/8/2019 | 6 | 2/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.238010 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 31/07/2019 | 6 | 1/8/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F1.237361 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 30/07/2019 | 6 | 30/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F86424.42 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 30/07/2019 | 9 | 23/08/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.236854 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 30/07/2019 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 3
F86424.41 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 29/07/2019 | 9 | 23/08/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.236147 | Completed and signed off | 1330 - Regeneron Building 19 | CM-SM-FRM-002 White Board Meeting | 29/07/2019 | 6 | 29/07/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 3
F92044.2 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 26/07/2019 | 9 | 8/8/2019 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.235424 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-GEN-001 Non Conformance Record (NCR) | 26/07/2019 | 10 | 31/03/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 4
F86424.39 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 25/07/2019 | 9 | 23/08/2019 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.37 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 22/07/2019 | 9 | 23/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.36 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 19/07/2019 | 9 | 4/9/2019 | 0 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.35 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 19/07/2019 | 9 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.231564 | Closed | 1330 - Regeneron Building 19 | QM-FRM-QC-007 Lessons Learned Report | 18/07/2019 | 10 | 27/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 4
F86424.34 | Completed and signed off | EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 16/07/2019 | 9 | 19/09/2019 | 0 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1330 | Closed | 2
F1.230426 | 3rd Party Sign Off - Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 16/07/2019 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 4
F1.230079 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 16/07/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1330 | Closed | 3
F86424.30 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 12/7/2019 | 9 | 23/08/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.29 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 12/7/2019 | 9 | 4/9/2019 | 0 | 16 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.28 | Closed JPC Reviewed | Site Management>JPC Project Management | QM-FRM-QC005 - Training Record | 12/7/2019 | 10 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.228086 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1330 | Closed | 3
F1.227934 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.227902 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.227886 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.227862 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.227798 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.227752 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.227750 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 19/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.227708 | Closed JPC Reviewed | 01 Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Site Diary | 10/7/2019 | 6 | 19/09/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F86424.27 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2019 | 9 | 23/08/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 2
F1.226445 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 8/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.226382 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 8/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.226355 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 8/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F1.226325 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 8/7/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1330 | Closed | 3
F86424.26 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 5/7/2019 | 9 | 10/7/2019 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.25 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 2/7/2019 | 9 | 23/08/2019 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 2
F86424.24 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 28/06/2019 | 9 | 10/7/2019 | 0 | 14 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.22 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 26/06/2019 | 9 | 23/08/2019 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.21 | Closed | 01 Inspections>EHS Forms>JPC Project Management | EHS Inspection. | 26/06/2019 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F86424.20 | Completed and signed off | 01 Inspections>EHS Forms>JPC Project Management | EHS Managment Inspection - Daily | 26/06/2019 | 9 | 23/08/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.221103 | Completed and signed off | 1330 - Regeneron Building 19 | EHS Managment Inspection - Daily | 26/06/2019 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 2
F1.220772 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 25/06/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1330 | Closed | 3
F1.220167 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 24/06/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 3
F1.220166 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 24/06/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1330 | Closed | 3
F86424.17 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 24/06/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F86424.16 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 24/06/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.13 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CE-303-Sub-Grade Inspection | 21/06/2019 | 7 | 1/7/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1330 | Closed | 4
F1.218776 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 20/06/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F86424.12 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 20/06/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.10 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 20/06/2019 | 11 | 1/7/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.9 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 20/06/2019 | 11 | 1/7/2019 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F86424.7 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 20/06/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F1.218093 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 19/06/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1330 | Closed | 3
F86424.4 | JPC Inspected | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/06/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F86424.3 | JPC Sign Off | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 19/06/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F86424.2 | JPC Inspected | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 19/06/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Open | 4
F1.217492 | Notification | 1330 - Regeneron Building 19 | BCAR Inspection Form | 18/06/2019 | 3 | 18/06/2019 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1330 | Closed | 4
F1.217489 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 18/06/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F1.216932 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 17/06/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F1.215780 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 13/06/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F1.215401 | JPC Sign Off / Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 13/06/2019 | 11 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F1.215358 | 3rd Party Sign Off - Closed | Foundations>Block 1 & 2>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 13/06/2019 | 10 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1330 | Closed | 4
F1.215031 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 12/6/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F1.214407 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 11/6/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F1.213170 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 8/6/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F1.213169 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 8/6/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F1.212240 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | QM-FRM-QC005 - Training Record | 6/6/2019 | 10 | 6/6/2019 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1330 | Closed | 4
F1.211958 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 15/10/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F1.211957 | Closed JPC Reviewed | 1330 - Regeneron Building 19 | SM-FRM-001 Site Diary | 5/6/2019 | 6 | 19/09/2019 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1330 | Closed | 3
F127607.137 | Open / Ongoing Works | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/09/2020 | 6 | 16/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F103672.178 | Open / Ongoing Works | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 15/09/2020 | 9 | 15/09/2020 | 2 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 2
F127607.136 | Open / Ongoing Works | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/09/2020 | 6 | 15/09/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F127607.135 | Open / Ongoing Works | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/09/2020 | 9 | 14/09/2020 | 1 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 2
F103672.177 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/09/2020 | 9 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.134 | Open / Ongoing Works | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/09/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F127607.133 | Open / Ongoing Works | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/9/2020 | 6 | 12/9/2020 | 3 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F132578.135 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/9/2020 | 9 | 15/09/2020 | 0 | 8 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F1.493042 | Open / Ongoing Works | 1335 - Adare Manor GAB | JPC-QA-RP-003 - Site Audit Report | 11/9/2020 | 2 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE |  | 1335 | Open | 3
F127607.132 | Open / Ongoing Works | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F1.491403 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 10/9/2020 | 1 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F127607.131 | Open / Ongoing Works | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F127607.130 | Open / Ongoing Works | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F103672.176 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 15/09/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F127607.129 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/9/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.128 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/9/2020 | 9 | 13/09/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F127607.127 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/9/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.487956 | Open / Ongoing Works | ITP 03 External Works>Quality Control | QM-CL-ME-401 Services Test | 7/9/2020 | 1 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.126 | Open / Ongoing Works | Training & Practice Area | QM-CL-ME-401 Services Test | 7/9/2020 | 1 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103672.175 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 15/09/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F132578.134 | Rejected / Action Required | North South Pool Elevations>Pool Elevations>Elevations>ITP 02 Architectural>Quality Control | QM-CL-ARC-207 Tiling Inspection (Floor & Wall) | 4/9/2020 | 8 | 4/9/2020 | 2 | 2 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.133 | Open / Ongoing Works | East West Pool Elevations>Pool Elevations>Elevations>ITP 02 Architectural>Quality Control | QM-CL-ARC-207 Tiling Inspection (Floor & Wall) | 4/9/2020 | 8 | 4/9/2020 | 19 | 19 | parent | FALSE | FALSE | TRUE |  | 1335 | Open | 4
F132578.132 | Open / Ongoing Works | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-207 Tiling Inspection (Floor & Wall) | 4/9/2020 | 8 | 4/9/2020 | 2 | 2 | parent | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.125 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/9/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.174 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 3/9/2020 | 9 | 15/09/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.173 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 3/9/2020 | 9 | 15/09/2020 | 0 | 14 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.124 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/9/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.123 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/9/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.130 | JPC Inspected | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 1/9/2020 | 8 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F141020.3 | Open / Ongoing Works | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 1/9/2020 | 9 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 2
F103672.172 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 1/9/2020 | 9 | 8/9/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F127607.122 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 1/9/2020 | 9 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F127607.121 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.120 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 13/09/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F127607.119 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132607.17 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-404 Electrical Inspection Report | 29/08/2020 | 1 | 29/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132607.16 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 29/08/2020 | 1 | 29/08/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132607.15 | Closed | Quality Control | CM-EHS-FRM-001 EHS Daily Management Inspection | 29/08/2020 | 9 | 15/09/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F132578.129 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/08/2020 | 9 | 15/09/2020 | 0 | 12 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.118 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.171 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 27/08/2020 | 9 | 3/9/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.479781 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 27/08/2020 | 9 | 15/09/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F127607.117 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.479027 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 26/08/2020 | 1 | 27/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F132607.14 | Closed | 1335 - Adare Manor GAB | CM-EHS-FRM-001 EHS Daily Management Inspection | 26/08/2020 | 9 | 15/09/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F132607.13 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 26/08/2020 | 9 | 15/09/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.116 | Open / Ongoing Works | LV -01 Basement>ITP 02 Architectural>Quality Control | QM-FRM-QC-008 Non Conformance Record (NCR) | 26/08/2020 | 10 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.115 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F141020.2 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/08/2020 | 9 | 15/09/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.170 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 25/08/2020 | 9 | 1/9/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.114 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.113 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 24/08/2020 | 9 | 13/09/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.112 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F127607.111 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F132607.12 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 21/08/2020 | 1 | 21/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132607.11 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-404 Electrical Inspection Report | 21/08/2020 | 1 | 21/08/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F1.474068 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 21/08/2020 | 1 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.474062 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 21/08/2020 | 1 | 25/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.474039 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 21/08/2020 | 1 | 27/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F127607.110 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.128 | Works Complete / Resolved | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 20/08/2020 | 8 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.168 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 20/08/2020 | 9 | 15/09/2020 | 0 | 13 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.109 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F141020.1 | Open / Ongoing Works | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 19/08/2020 | 9 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 2
F132578.127 | Open / Ongoing Works | Fitness Suite>Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/08/2020 | 8 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.108 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F132578.126 | Open / Ongoing Works | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 18/08/2020 | 8 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.107 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/08/2020 | 6 | 13/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F127607.106 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/08/2020 | 9 | 25/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.105 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.467815 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-404 Electrical Inspection Report | 14/08/2020 | 1 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.125 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/08/2020 | 9 | 25/08/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F1.467127 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 14/08/2020 | 1 | 14/08/2020 | 1 | 3 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.124 | JPC Inspected | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 14/08/2020 | 8 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F1.466892 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 14/08/2020 | 1 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.466843 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 14/08/2020 | 1 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F127607.104 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.123 | JPC Inspected | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/08/2020 | 8 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.122 | Open / Ongoing Works | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 13/08/2020 | 8 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.103 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F1.464873 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 12/8/2020 | 1 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.464870 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 12/8/2020 | 1 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F132607.10 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/8/2020 | 9 | 25/08/2020 | 0 | 8 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F127607.102 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/8/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.121 | JPC Inspected | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 11/8/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.167 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/8/2020 | 9 | 25/08/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F127607.101 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/8/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.100 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/8/2020 | 9 | 25/08/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F127607.99 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/8/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.462748 | Open / Ongoing Works | 1335 - Adare Manor GAB | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/8/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 2
F1.461929 | Open / Ongoing Works | 1335 - Adare Manor GAB | QM-FRM-MEP-405 Mechanical Inspection Report | 10/8/2020 | 1 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F127607.98 | In Process / Manufactor | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-QC-002 Off Site Inspection | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F1.461115 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 7/8/2020 | 1 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.461112 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 7/8/2020 | 1 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.461108 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-404 Electrical Inspection Report | 7/8/2020 | 1 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.461101 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-CL-ME-402 Electrical Inspection | 7/8/2020 | 1 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.120 | JPC Inspected | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 7/8/2020 | 8 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.119 | Closed JPC Reviewed | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-QC005 - Training Record | 7/8/2020 | 10 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE |  | 1335 | Closed | 4
F127607.97 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.166 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 6/8/2020 | 9 | 21/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F132578.118 | JPC Inspected | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 6/8/2020 | 8 | 6/8/2020 | 2 | 3 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.117 | JPC Inspected | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 6/8/2020 | 8 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.96 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 28/08/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.95 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.162 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/8/2020 | 9 | 10/8/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.94 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 28/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.116 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 31/07/2020 | 9 | 10/8/2020 | 0 | 7 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F132607.9 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-404 Electrical Inspection Report | 31/07/2020 | 1 | 14/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F103672.161 | Opened | EHS Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 31/07/2020 | 9 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 2
F132607.8 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 31/07/2020 | 1 | 14/08/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F132607.7 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 31/07/2020 | 1 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F127607.92 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/07/2020 | 6 | 28/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.115 | Works Complete / Resolved | Pool Shower 2>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 30/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.114 | Works Complete / Resolved | Pool Shower 1>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 30/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.113 | Works Complete / Resolved | Sauna>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 30/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.91 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/07/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.112 | Works Complete / Resolved | Steam Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132607.6 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/07/2020 | 9 | 10/8/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.90 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.89 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/07/2020 | 6 | 28/08/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.88 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/07/2020 | 9 | 10/8/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F132578.111 | Works Complete / Resolved | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.110 | Works Complete / Resolved | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.109 | Works Complete / Resolved | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.108 | Works Complete / Resolved | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.107 | Works Complete / Resolved | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.106 | Rejected / Action Required | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F1.448331 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 27/07/2020 | 1 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F132578.105 | Rejected / Action Required | Stairs>Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 27/07/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F1.448323 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 27/07/2020 | 1 | 27/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F132578.104 | Rejected / Action Required | Studio>Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 27/07/2020 | 1 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.103 | Rejected / Action Required | Studio>Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.102 | Rejected / Action Required | Fitness Suite>Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 27/07/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.101 | Rejected / Action Required | Fitness Suite>Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 27/07/2020 | 8 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.87 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/07/2020 | 6 | 28/08/2020 | 3 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.447355 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 24/07/2020 | 1 | 24/07/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.447349 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-404 Electrical Inspection Report | 24/07/2020 | 1 | 14/08/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.446763 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 24/07/2020 | 1 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.446759 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 24/07/2020 | 1 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.446541 | Works Complete / Resolved | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 24/07/2020 | 8 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.86 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.85 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F127607.84 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.83 | Open / Ongoing Works | Storm water>Utilities & Drainage>ITP 03 External Works>Quality Control | QM-CL-CE-303-Sub-Grade Inspection | 23/07/2020 | 7 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.82 | Open / Ongoing Works | Storm water>Utilities & Drainage>ITP 03 External Works>Quality Control | QM-CL-CE-315-Liner Installation Inspection | 23/07/2020 | 7 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F103672.159 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 23/07/2020 | 9 | 6/8/2020 | 0 | 10 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103672.158 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 23/07/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F132578.100 | JPC Inspected | Timber batten Ceiling Corridor>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-207 Tiling Inspection (Floor & Wall) | 22/07/2020 | 8 | 22/07/2020 | 7 | 7 | parent | FALSE | FALSE | TRUE |  | 1335 | Open | 4
F132578.99 | JPC Inspected | Family 2>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 22/07/2020 | 8 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.98 | JPC Inspected | Family 1>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 22/07/2020 | 8 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.81 | JPC Sign Off | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 22/07/2020 | 8 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 4
F127607.80 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.156 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/07/2020 | 9 | 10/8/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F132578.97 | JPC Inspected | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-207 Tiling Inspection (Floor & Wall) | 21/07/2020 | 8 | 21/07/2020 | 11 | 11 | parent | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.79 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.78 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/07/2020 | 9 | 10/8/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F127607.77 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.440746 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-404 Electrical Inspection Report | 17/07/2020 | 1 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.440739 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 17/07/2020 | 1 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F132578.96 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/07/2020 | 9 | 10/8/2020 | 0 | 3 | parent | FALSE | FALSE | TRUE |  | 1335 | Closed | 2
F132578.95 | JPC Inspected | Female Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 17/07/2020 | 8 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.76 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.129 | Open / Ongoing Works | Foul Water>Utilities & Drainage>ITP 03 External Works>Quality Control | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 16/07/2020 | 7 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.94 | Works Complete / Resolved | Female Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.93 | Works Complete / Resolved | Pool WC>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 16/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.155 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 16/07/2020 | 9 | 22/07/2020 | 0 | 17 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103672.154 | Open / Ongoing Works | Lvl 02 Roof Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 16/07/2020 | 8 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.75 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.92 | Works Complete / Resolved | Linen Store>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.91 | Open / Ongoing Works | WC>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132607.5 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/07/2020 | 9 | 25/08/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.153 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | Qm-CL-CS-112 Structural Steel Inspection | 15/07/2020 | 11 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.90 | Works Complete / Resolved | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F103672.152 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | Qm-CL-CS-112 Structural Steel Inspection | 15/07/2020 | 11 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.88 | Works Complete / Resolved | Timber batten Ceiling Corridor>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 7/8/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.87 | Works Complete / Resolved | Female Changing/ Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.86 | JPC Inspected | Retail / Foyer>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.85 | JPC Inspected | Golf Sim / lounge Room>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.84 | JPC Inspected | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.83 | JPC Inspected | Pantry>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.82 | JPC Inspected | Office>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 15/07/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.151 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | Qm-CL-CS-112 Structural Steel Inspection | 15/07/2020 | 11 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.73 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.150 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/07/2020 | 9 | 21/07/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.437093 | In Process / Manufactor | 1335 - Adare Manor GAB | QM-FRM-QC-002 Off Site Inspection | 14/07/2020 | 10 | 14/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F127607.72 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.71 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/07/2020 | 9 | 25/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.70 | Open / Ongoing Works | EHS Inspections>EHS Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F127607.69 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.49 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/7/2020 | 9 | 25/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F1.434558 | Open / Ongoing Works | 1335 - Adare Manor GAB | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 10/7/2020 | 13 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 6
F1.434094 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 10/7/2020 | 1 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F127607.68 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/7/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.80 | Open / Ongoing Works | Male Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 9/7/2020 | 8 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132607.4 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-404 Electrical Inspection Report | 9/7/2020 | 1 | 9/7/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.79 | Works Complete / Resolved | Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 9/7/2020 | 8 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132607.3 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 9/7/2020 | 1 | 9/7/2020 | 1 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132607.2 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-CL-ME-403 Mechanical Inspection | 9/7/2020 | 1 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.78 | Open / Ongoing Works | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-225 Firestopping Inspection Checklist | 9/7/2020 | 8 | 9/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103672.149 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 9/7/2020 | 9 | 16/07/2020 | 0 | 13 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.67 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.77 | Rejected / Action Required | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/7/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.76 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/7/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.75 | Rejected / Action Required | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/7/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.74 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/7/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.73 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/7/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.72 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/7/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.71 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/7/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.70 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 8/7/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.66 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.431206 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 7/7/2020 | 1 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.431201 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 7/7/2020 | 1 | 7/7/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.431196 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 7/7/2020 | 1 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103672.148 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 7/7/2020 | 9 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.147 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/7/2020 | 9 | 14/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.65 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.64 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/7/2020 | 9 | 25/08/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.429372 | Open / Ongoing Works | 1335 - Adare Manor GAB | JPC-QA-RP-003 - Site Audit Report | 6/7/2020 | 2 | 6/7/2020 | 0 | 0 |  | FALSE | FALSE | TRUE |  | 1335 | Open | 3
F127607.63 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.69 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/7/2020 | 9 | 17/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.62 | Open / Ongoing Works | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-QC-004 QC Observation Report | 3/7/2020 | 10 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103665.48 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/7/2020 | 9 | 25/08/2020 | 0 | 7 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F132578.68 | Rejected / Action Required | Linen Store>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 3/7/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.67 | Works Complete / Resolved | Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 3/7/2020 | 8 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.61 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.145 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 2/7/2020 | 9 | 16/07/2020 | 0 | 10 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F127607.60 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.59 | Open / Ongoing Works | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-QC-004 QC Observation Report | 1/7/2020 | 10 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.66 | JPC Inspected | Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 1/7/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.58 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F127607.57 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.144 | Open / Ongoing Works | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-FRM-QC-004 QC Observation Report | 30/06/2020 | 10 | 30/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103672.143 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 30/06/2020 | 9 | 7/7/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F132578.65 | Works Complete / Resolved | WC>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 30/06/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F127607.55 | JPC Sign Off | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F127607.54 | JPC Sign Off | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F127607.53 | JPC Sign Off | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F127607.52 | JPC Sign Off | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 30/06/2020 | 8 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F127607.51 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.50 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/06/2020 | 9 | 25/08/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F1.423562 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 29/06/2020 | 1 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103672.142 | Open / Ongoing Works | Foul Water>Utilities & Drainage>ITP 03 External Works>Quality Control | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 29/06/2020 | 7 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F1.423471 | Open / Ongoing Works | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 29/06/2020 | 1 | 29/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.423446 | JPC Sign Off | ITP 04 M&E Services>Quality Control | QM-FRM-ME-401 M&E Benchmark Inspection | 29/06/2020 | 1 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F132578.64 | Open / Ongoing Works | Retail / Foyer>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-207 Tiling Inspection (Floor & Wall) | 29/06/2020 | 8 | 29/06/2020 | 5 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.63 | JPC Inspected | Lounge>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/06/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.62 | JPC Inspected | Lounge>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/06/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.61 | JPC Inspected | Golf Sim / lounge Room>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/06/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.60 | JPC Inspected | Pantry>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/06/2020 | 8 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.59 | JPC Inspected | Pantry>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/06/2020 | 8 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.58 | JPC Inspected | Office>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/06/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.57 | JPC Inspected | Office>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 29/06/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.49 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.422442 | Open / Ongoing Works | 1335 - Adare Manor GAB | QM-CL-ME-401 Services Test | 26/06/2020 | 1 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F1.422423 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 26/06/2020 | 1 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103665.47 | Open / Ongoing Works | Quality Control | QM-FRM-QC-003 Protection of Finishes Inspection | 26/06/2020 | 10 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.56 | JPC Inspected | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.55 | Rejected / Action Required | Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.54 | Works Complete / Resolved | Storage>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.53 | JPC Inspected | Timber batten Ceiling Corridor>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.52 | JPC Inspected | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.51 | JPC Inspected | Male Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.50 | Works Complete / Resolved | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.49 | JPC Inspected | Pool WC>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.48 | JPC Inspected | Timber batten Ceiling Corridor>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 8/7/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.47 | JPC Inspected | Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.46 | JPC Inspected | Timber batten Ceiling Corridor>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 8/7/2020 | 1 | 1 | parent | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.45 | JPC Inspected | Family 1>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 8/7/2020 | 1 | 1 | parent | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.44 | JPC Inspected | Family 1>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.43 | JPC Inspected | Acc, WC/ Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.42 | JPC Inspected | Acc, WC/ Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 10/7/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.41 | JPC Inspected | Acc, WC/ Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.40 | Works Complete / Resolved | Acc, WC/ Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.39 | JPC Inspected | Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.38 | Rejected / Action Required | Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.37 | JPC Inspected | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.36 | JPC Inspected | Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.35 | JPC Inspected | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.34 | JPC Inspected | Female WC>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.33 | JPC Inspected | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.32 | JPC Inspected | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.31 | JPC Inspected | Male Changing/ :Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.30 | JPC Inspected | Male Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.29 | JPC Inspected | Male Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.28 | JPC Inspected | Male Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.27 | JPC Inspected | Male Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.26 | JPC Inspected | Male Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.24 | JPC Inspected | Male Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.23 | JPC Inspected | Female Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.22 | JPC Inspected | Female Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.21 | JPC Inspected | Reception>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 26/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.48 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/06/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.20 | JPC Inspected | Female Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.19 | JPC Inspected | Female Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.18 | JPC Inspected | Female Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.17 | JPC Inspected | Female Shower>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.16 | JPC Inspected | Female Changing/ Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.15 | JPC Inspected | Female Changing/ Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.14 | JPC Inspected | Female WC>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F132578.13 | JPC Inspected | Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.12 | JPC Inspected | Female Changing/ Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.11 | JPC Inspected | Linen Store>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 25/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.141 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 25/06/2020 | 9 | 2/7/2020 | 0 | 15 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.140 | Opened | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 25/06/2020 | 9 | 25/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 2
F127607.47 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/06/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.46 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.139 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 23/06/2020 | 9 | 7/7/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.45 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/06/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.44 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/06/2020 | 9 | 23/06/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F132607.1 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/06/2020 | 9 | 10/8/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.138 | Closed | EHS Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 22/06/2020 | 9 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.43 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/06/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F132578.10 | Rejected / Action Required | Paddle Club>Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/06/2020 | 8 | 19/06/2020 | 1 | 3 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F132578.9 | JPC Inspected | Reception>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/06/2020 | 8 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.8 | JPC Inspected | Female Changing/ Locker Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/06/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.7 | Works Complete / Resolved | Linen Store>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/06/2020 | 8 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.6 | JPC Inspected | Linen Store>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/06/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.5 | JPC Inspected | Putting Surfaces>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/06/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.4 | JPC Inspected | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/06/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.3 | JPC Inspected | Office>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/06/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F132578.2 | JPC Inspected | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 19/06/2020 | 8 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.42 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/06/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.137 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 18/06/2020 | 9 | 23/06/2020 | 0 | 14 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.41 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/06/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.136 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/06/2020 | 9 | 24/06/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F132578.1 | JPC Inspected | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 17/06/2020 | 8 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.40 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F127607.39 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.135 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/06/2020 | 9 | 24/06/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.38 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.37 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 15/06/2020 | 9 | 23/06/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.36 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.134 | JPC Sign Off / Closed | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-114 Blockwork / Brickwork Inspection | 12/6/2020 | 11 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F1.410911 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 12/6/2020 | 1 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.410884 | Open / Ongoing Works | 1335 - Adare Manor GAB | QM-CL-ME-404 Lift Installation Inspection | 12/6/2020 | 1 | 12/6/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F1.410831 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-405 Mechanical Inspection Report | 12/6/2020 | 1 | 27/07/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F125961.10 | Completed and signed off | JPC Project Management | EHS Managment Inspection - Daily | 12/6/2020 | 9 | 23/06/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.410789 | Closed | ITP 04 M&E Services>Quality Control | QM-FRM-MEP-404 Electrical Inspection Report | 12/6/2020 | 1 | 27/07/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103672.133 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.132 | JPC Inspected | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 12/6/2020 | 8 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.35 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.131 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 11/6/2020 | 9 | 18/06/2020 | 0 | 13 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F125961.9 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F125961.8 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F125961.7 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F1.409564 | Open / Ongoing Works | Items to Be Deteled>Training & Practice Area | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 11/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103672.130 | JPC Inspected | Pool Area>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 11/6/2020 | 8 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F125961.6 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 11/6/2020 | 8 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.129 | Open / Ongoing Works | ESB>Utilities & Drainage>ITP 03 External Works>Quality Control | QM-CL-CE-305 Underground Ducting Installation Inspection | 11/6/2020 | 7 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F127607.34 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.33 | JPC Inspected | Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 10/6/2020 | 8 | 16/07/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.32 | Open / Ongoing Works | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 10/6/2020 | 8 | 10/6/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.31 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.30 | JPC Inspected | Lvl 01 Floor Plan>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 9/6/2020 | 8 | 15/06/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.128 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/6/2020 | 9 | 24/06/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.127 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/6/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.29 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.27 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/6/2020 | 9 | 16/06/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.126 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/6/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.406837 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/6/2020 | 9 | 12/6/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.125 | Test Results Required | Foul Water>Utilities & Drainage>ITP 03 External Works>Quality Control | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 8/6/2020 | 7 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.124 | Test Results Required | Foul Water>Utilities & Drainage>ITP 03 External Works>Quality Control | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 8/6/2020 | 7 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.26 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.405965 | Closed | 1335 - Adare Manor GAB | QM-FRM-MEP-405 Mechanical Inspection Report | 5/6/2020 | 1 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.405964 | Closed | 1335 - Adare Manor GAB | QM-FRM-MEP-404 Electrical Inspection Report | 5/6/2020 | 1 | 27/07/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.405957 | JPC Sign Off / Closed | 1335 - Adare Manor GAB | QM-FRM-MEP-405 Mechanical Inspection Report | 5/6/2020 | 1 | 27/07/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F103672.123 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/6/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F125961.5 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/6/2020 | 9 | 12/6/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.25 | Open / Ongoing Works | Lvl 02 Roof Plan>ITP 01 Structural>Quality Control | Qm-CL-CS-112 Structural Steel Inspection | 5/6/2020 | 11 | 27/06/2020 | 1 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.24 | JPC Sign Off / Closed | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 5/6/2020 | 8 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 4
F127607.23 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.22 | Open / Ongoing Works | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 5/6/2020 | 8 | 5/6/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103672.122 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/6/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.121 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 4/6/2020 | 9 | 2/7/2020 | 0 | 13 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.21 | JPC Sign Off / Closed | Steam Room>Pool Area Facilities>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-119 Floor Screed Inspection | 4/6/2020 | 8 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F125961.4 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 4/6/2020 | 8 | 4/6/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.20 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.120 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/6/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.119 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/6/2020 | 9 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103672.118 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/6/2020 | 9 | 23/06/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F1.403719 | JPC Sign Off | 1335 - Adare Manor GAB | QM-FRM-ME-401 M&E Benchmark Inspection | 3/6/2020 | 1 | 7/7/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.403714 | JPC Sign Off | 1335 - Adare Manor GAB | QM-FRM-ME-401 M&E Benchmark Inspection | 3/6/2020 | 1 | 7/7/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F127607.19 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.117 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/6/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.116 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/6/2020 | 9 | 8/6/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.402664 | JPC Sign Off | 1335 - Adare Manor GAB | QM-FRM-ME-401 M&E Benchmark Inspection | 2/6/2020 | 1 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.402656 | JPC Sign Off | 1335 - Adare Manor GAB | QM-FRM-ME-401 M&E Benchmark Inspection | 2/6/2020 | 1 | 2/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE |  | 1335 | Closed | 4
F127607.18 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.46 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/05/2020 | 9 | 23/06/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F1.400948 | Closed | 1335 - Adare Manor GAB | QM-FRM-MEP-405 Mechanical Inspection Report | 29/05/2020 | 1 | 17/07/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.400939 | Closed | 1335 - Adare Manor GAB | QM-FRM-MEP-405 Mechanical Inspection Report | 29/05/2020 | 1 | 17/07/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103672.115 | Opened | EHS Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 29/05/2020 | 9 | 29/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 2
F103672.114 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103665.45 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 29/05/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F127607.17 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.113 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 28/05/2020 | 9 | 18/06/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.112 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103665.44 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 28/05/2020 | 6 | 28/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F127607.16 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.111 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.110 | Open / Ongoing Works | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 27/05/2020 | 9 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 2
F127607.15 | JPC Sign Off | Combined Services Plan>Utilities & Drainage>ITP 03 External Works>Quality Control | QM-CL-CS-103 Excavation Inspection | 27/05/2020 | 11 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F127607.11 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.109 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/05/2020 | 9 | 8/6/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103665.43 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F103672.108 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/05/2020 | 9 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103665.42 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/05/2020 | 6 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.10 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.9 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/05/2020 | 9 | 16/06/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.107 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/05/2020 | 9 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.8 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F125961.3 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 5/6/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.106 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/05/2020 | 9 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.396797 | JPC Sign Off | 1335 - Adare Manor GAB | QM-FRM-ME-401 M&E Benchmark Inspection | 22/05/2020 | 1 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F127607.7 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.105 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/05/2020 | 9 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.104 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 21/05/2020 | 9 | 27/05/2020 | 0 | 12 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F127607.6 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.103 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/05/2020 | 9 | 23/06/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103672.102 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/05/2020 | 9 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.101 | Test Results Required | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 20/05/2020 | 11 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F127607.5 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.100 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 19/05/2020 | 9 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.4 | JPC Sign Off | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-103 Excavation Inspection | 19/05/2020 | 11 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F103672.99 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/05/2020 | 9 | 8/6/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.3 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F127607.2 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/05/2020 | 9 | 16/06/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F127607.1 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.39 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.38 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/4/2020 | 6 | 7/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.128 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/4/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.371656 | Closed JPC Reviewed | 1335 - Adare Manor GAB | QM-FRM-QC005 - Training Record | 3/4/2020 | 10 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103673.127 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/03/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F125961.2 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/03/2020 | 9 | 31/03/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.126 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/03/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103673.125 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CE-305 Underground Ducting Installation Inspection | 27/03/2020 | 7 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103665.37 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/03/2020 | 6 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.124 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/03/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.36 | Open | Site Management>JPC Project Management | QM-FRM-QC005 - Training Record | 26/03/2020 | 10 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.97 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 26/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.96 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 26/03/2020 | 9 | 31/03/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103665.35 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/03/2020 | 6 | 26/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.95 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/03/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F102906.13 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 25/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.122 | JPC Inspected | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 25/03/2020 | 8 | 15/06/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F125961.1 | JPC Sign Off | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-ARC-201 Benchmark / Sample Form | 25/03/2020 | 8 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F103673.121 | Open | Site Management>JPC Project Management | SM-FRM-002 Progress Record | 25/03/2020 | 6 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F103673.120 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 25/03/2020 | 6 | 25/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.119 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/03/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F102906.12 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 24/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103672.94 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/03/2020 | 9 | 31/03/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.117 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 24/03/2020 | 6 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F102906.11 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 23/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F1.365211 | Open / Ongoing Works | 1335 - Adare Manor GAB | JPC-QA-RP-003 - Site Audit Report | 23/03/2020 | 2 | 23/03/2020 | 0 | 0 |  | FALSE | FALSE | TRUE |  | 1335 | Open | 3
F103673.116 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 23/03/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103672.93 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/03/2020 | 9 | 31/03/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103675.46 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/03/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.92 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 20/03/2020 | 9 | 31/03/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F102906.10 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/03/2020 | 9 | 23/03/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.91 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 20/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103665.41 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.40 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.373719 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 8/4/2020 | 11 | 8/4/2020 | 0 | 0 | child | FALSE | FALSE | TRUE |  | 1335 | Open | 4
F1.373739 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 8/4/2020 | 11 | 8/4/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.373744 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 8/4/2020 | 11 | 8/4/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.374683 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 9/4/2020 | 11 | 9/4/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.374684 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 9/4/2020 | 11 | 9/4/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.374700 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 9/4/2020 | 11 | 14/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.375694 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 14/04/2020 | 11 | 14/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.375699 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 14/04/2020 | 11 | 14/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.377442 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 17/04/2020 | 11 | 17/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.377443 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 17/04/2020 | 11 | 17/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.377444 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 17/04/2020 | 11 | 17/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.377445 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 17/04/2020 | 11 | 17/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.377446 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 17/04/2020 | 11 | 17/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.377448 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 17/04/2020 | 11 | 17/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.377449 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 17/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380598 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380607 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380614 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380626 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380633 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380643 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380704 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380707 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380715 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380722 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380729 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380747 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380762 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380781 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380804 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380837 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380845 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380865 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380882 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380935 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380941 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380942 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380944 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380959 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380963 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380964 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380967 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380969 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380972 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380973 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.380974 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-116 Concrete Cube Record | 24/04/2020 | 11 | 24/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.410886 | Works Complete | 1335 - Adare Manor GAB | BCAR Inspection Form | 12/6/2020 | 3 | 15/09/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103673.123 | Rejected / Action Required | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-QC-001 Benchmark / Sample Form | 25/03/2020 | 10 | 15/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103673.115 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 20/03/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.114 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 20/03/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F103675.45 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/03/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103672.90 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 19/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103672.89 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 19/03/2020 | 9 | 31/03/2020 | 0 | 11 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103673.111 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 19/03/2020 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.44 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/03/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F102906.9 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/03/2020 | 9 | 19/03/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F102906.8 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/03/2020 | 9 | 19/03/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F102906.7 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 18/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103672.88 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 16/03/2020 | 6 | 16/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.87 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/03/2020 | 9 | 19/03/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.86 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/03/2020 | 6 | 16/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F103672.85 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 13/03/2020 | 6 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.43 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/03/2020 | 6 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F102906.6 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 13/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.84 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/03/2020 | 9 | 19/03/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.83 | Open / Ongoing Works | General QA Records>Quality Management>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 13/03/2020 | 10 | 13/03/2020 | 7 | 7 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.82 | Open / Ongoing Works | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-QC-001 Benchmark / Sample Form | 13/03/2020 | 10 | 13/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F103675.41 | Closed JPC Sign Off | Lvl 01 Floor Plan>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/3/2020 | 11 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F103672.81 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 12/3/2020 | 9 | 19/03/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.80 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 12/3/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103675.40 | JPC Inspected | Lvl 01 Floor Plan>ITP 01 Structural>Quality Control | QM-CL-CS-111 Pre-cast Concrete Inspection | 11/3/2020 | 11 | 11/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.39 | JPC Inspected | Lvl 01 Floor Plan>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 11/3/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.110 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/3/2020 | 9 | 13/03/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103673.109 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/3/2020 | 6 | 10/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.38 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/3/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F103675.37 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/3/2020 | 9 | 13/03/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.356213 | Closed | 1335 - Adare Manor GAB | QM-FRM-MEP-404 Electrical Inspection Report | 9/3/2020 | 1 | 17/07/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103673.108 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 6/3/2020 | 6 | 6/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.107 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/3/2020 | 9 | 13/03/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.354601 | Closed | 1335 - Adare Manor GAB | JPC-HR-FRM-001 - Training Record | 5/3/2020 | 2 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F1.354594 | Closed | 1335 - Adare Manor GAB | JPC-HR-FRM-001 - Training Record | 5/3/2020 | 2 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103673.106 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 5/3/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.79 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 5/3/2020 | 9 | 19/03/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.354062 | Open / Ongoing Works | 1335 - Adare Manor GAB | SM-FRM-001 Daily Site Diary | 5/3/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F1.354053 | Open / Ongoing Works | 1335 - Adare Manor GAB | SM-FRM-001 Daily Site Diary | 5/3/2020 | 6 | 5/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F103673.105 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/3/2020 | 6 | 4/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.78 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/3/2020 | 9 | 5/3/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.104 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/3/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.103 | Open / Ongoing Works | Allocation Sheets>Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/3/2020 | 6 | 3/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F103675.36 | JPC Inspected | Lvl 01 Floor Plan>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/3/2020 | 11 | 24/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.102 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/3/2020 | 9 | 5/3/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.101 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 2/3/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103675.35 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/3/2020 | 6 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.99 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 2/3/2020 | 6 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.34 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/3/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.33 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 2/3/2020 | 9 | 5/3/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103675.32 | JPC Inspected | Lvl 01 Floor Plan>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 2/3/2020 | 11 | 24/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.31 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 2/3/2020 | 11 | 2/3/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.98 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 28/02/2020 | 6 | 28/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.97 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/02/2020 | 6 | 27/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.76 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/02/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.75 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 27/02/2020 | 9 | 5/3/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103675.28 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/02/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.27 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/02/2020 | 6 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.74 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/02/2020 | 9 | 5/3/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.96 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/02/2020 | 6 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.95 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 25/02/2020 | 6 | 25/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.73 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 25/02/2020 | 9 | 5/3/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.347381 | Open / Ongoing Works | 1335 - Adare Manor GAB | SM-FRM-005 Permit to Enter | 25/02/2020 | 6 | 25/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F103675.26 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/02/2020 | 9 | 5/3/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.94 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 24/02/2020 | 6 | 24/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.25 | JPC Inspected | Padddle Club>Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-119 Floor Screed Inspection | 24/02/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.24 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 24/02/2020 | 11 | 24/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.93 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 22/02/2020 | 9 | 19/03/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.92 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/02/2020 | 6 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.91 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 22/02/2020 | 6 | 22/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F1.345639 | Open / Ongoing Works | 1335 - Adare Manor GAB | QM-CL-ARC-204 Void Closure Sign Off (Walls and Ceilings) | 21/02/2020 | 8 | 21/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103675.22 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/02/2020 | 6 | 26/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.90 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 21/02/2020 | 6 | 21/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.21 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/02/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.20 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/02/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.89 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/02/2020 | 6 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.19 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/02/2020 | 6 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.88 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 20/02/2020 | 6 | 20/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.72 | Closed | EHS Management>JPC Project Management | EHS Inspection. | 20/02/2020 | 9 | 24/02/2020 | 0 | 10 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103675.18 | JPC Inspected | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-119 Floor Screed Inspection | 20/02/2020 | 8 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103526.10 | Closed | QC Training Records>Quality Management>JPC Project Management | JPC-HR-FRM-001 - Training Record | 20/02/2020 | 2 | 20/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE |  | 1335 | Closed | 3
F103673.86 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 19/02/2020 | 9 | 24/02/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.85 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 19/02/2020 | 6 | 19/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.17 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/02/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.71 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/02/2020 | 9 | 24/02/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.84 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 18/02/2020 | 6 | 18/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.16 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/02/2020 | 9 | 24/02/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.70 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/02/2020 | 6 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.68 | Open / Ongoing Works | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/02/2020 | 6 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F103672.67 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/02/2020 | 6 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.83 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/02/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103673.82 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 14/02/2020 | 6 | 14/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.15 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 14/02/2020 | 11 | 24/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.54 | Works Complete / Resolved | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 24/01/2020 | 7 | 22/02/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.40 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 24/01/2020 | 9 | 17/02/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.39 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 24/01/2020 | 6 | 24/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.38 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 23/01/2020 | 6 | 23/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.37 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 23/01/2020 | 9 | 17/02/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103673.53 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 23/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.52 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 23/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.51 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 22/01/2020 | 6 | 22/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.50 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 22/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.49 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.48 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/01/2020 | 11 | 24/04/2020 | 0 | 0 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103673.47 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 21/01/2020 | 11 | 24/04/2020 | 0 | 0 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103672.36 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 21/01/2020 | 9 | 29/01/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.35 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 20/01/2020 | 9 | 20/01/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.34 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 20/01/2020 | 9 | 20/01/2020 | 0 | 0 |  | FALSE | FALSE | TRUE |  | 1335 | Closed | 2
F103672.33 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 20/01/2020 | 6 | 20/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.31 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/01/2020 | 6 | 17/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.46 | Works Complete / Resolved | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 17/01/2020 | 7 | 22/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.45 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | Qm-CL-CS-112 Structural Steel Inspection | 17/01/2020 | 11 | 27/06/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.44 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 17/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.30 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/01/2020 | 9 | 20/01/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.43 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/01/2020 | 6 | 17/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.42 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 16/01/2020 | 6 | 16/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.41 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.40 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.39 | Open / Ongoing Works | LV -01 Basement>ITP 01 Structural>Quality Control | QM-FRM-QC-001 Benchmark / Sample Form | 16/01/2020 | 10 | 16/01/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.38 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.29 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 16/01/2020 | 9 | 20/01/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103673.37 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 15/01/2020 | 6 | 15/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.36 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 15/01/2020 | 11 | 29/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.35 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 15/01/2020 | 11 | 29/04/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103673.34 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 15/01/2020 | 11 | 2/3/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.33 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 15/01/2020 | 11 | 2/3/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.32 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 15/01/2020 | 11 | 29/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.31 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 15/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.30 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 15/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.28 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 14/01/2020 | 9 | 20/01/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.29 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/01/2020 | 6 | 14/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.27 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 14/01/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103672.26 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 14/01/2020 | 11 | 17/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.25 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 13/01/2020 | 9 | 20/01/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.24 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/1/2020 | 6 | 10/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.28 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/1/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.26 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/1/2020 | 9 | 10/1/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103672.23 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/1/2020 | 9 | 13/01/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.22 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/1/2020 | 11 | 29/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.21 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/1/2020 | 11 | 17/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.20 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/1/2020 | 11 | 17/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.19 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/1/2020 | 11 | 17/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.25 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/1/2020 | 11 | 17/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103526.8 | Open / Ongoing Works | JPC Project Management | JPC-HR-FRM-001 - Training Record | 9/1/2020 | 2 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F1.316281 | Open / Ongoing Works | 1335 - Adare Manor GAB | QM-FRM-QC-001 Benchmark / Sample Form | 9/1/2020 | 10 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.316177 | Open | 1335 - Adare Manor GAB | SM-FRM-002 Progress Record | 9/1/2020 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F1.316174 | Open | 1335 - Adare Manor GAB | SM-FRM-002 Progress Record | 9/1/2020 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F1.316171 | Open / Ongoing Works | 1335 - Adare Manor GAB | QM-FRM-QC-004 QC Observation Report | 9/1/2020 | 10 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103672.18 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 9/1/2020 | 9 | 14/01/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.316112 | Test Results Required | 1335 - Adare Manor GAB | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/1/2020 | 11 | 31/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103673.22 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/1/2020 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F1.316110 | Open / Ongoing Works | 1335 - Adare Manor GAB | QM-FRM-BCAR-100 Structural BCAR Inspection | 9/1/2020 | 13 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 6
F103673.21 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/1/2020 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.24 | Completed and signed off | 1335 - Adare Manor GAB | EHS Managment Inspection - Daily | 8/1/2020 | 9 | 6/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103673.20 | Test Results Required | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 8/1/2020 | 11 | 22/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.19 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 8/1/2020 | 11 | 17/04/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.18 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 8/1/2020 | 11 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.17 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/1/2020 | 9 | 20/01/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.16 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 7/1/2020 | 11 | 14/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103665.20 | Open / Ongoing Works | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 7/1/2020 | 6 | 7/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F103665.19 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 7/1/2020 | 6 | 7/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.15 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 7/1/2020 | 11 | 14/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.14 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/1/2020 | 9 | 10/1/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.12 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/1/2020 | 11 | 9/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.11 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 19/12/2019 | 11 | 14/04/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F103672.17 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 19/12/2019 | 9 | 20/12/2019 | 0 | 9 | parent | FALSE | FALSE | TRUE |  | 1335 | Closed | 2
F103665.18 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 18/12/2019 | 9 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.16 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 17/12/2019 | 9 | 6/1/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.309666 | JPC Inspected | 1335 - Adare Manor GAB | QM-CL-CS-110 Concreting Inspection (In Situ) | 16/12/2019 | 11 | 9/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.10 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-114 Blockwork / Brickwork Inspection | 16/12/2019 | 11 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.15 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 13/12/2019 | 9 | 6/1/2020 | 0 | 11 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103665.17 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 12/12/2019 | 6 | 12/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.9 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/12/2019 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 3
F103673.8 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/12/2019 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.16 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/12/2019 | 9 | 6/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103665.15 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/12/2019 | 9 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103665.14 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/12/2019 | 6 | 10/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.14 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 10/12/2019 | 9 | 6/1/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.13 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 10/12/2019 | 11 | 8/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103665.13 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/12/2019 | 6 | 10/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F103665.12 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/12/2019 | 6 | 10/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F110033.18 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/12/2019 | 9 | 6/1/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F110033.17 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/12/2019 | 9 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F110033.16 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 9/12/2019 | 9 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F110033.15 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 9/12/2019 | 11 | 8/4/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F103672.12 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 9/12/2019 | 9 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.10 | Closed | EHS Management>JPC Project Management | EHS Inspection. | 9/12/2019 | 9 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103673.7 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/12/2019 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103673.6 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/12/2019 | 6 | 9/1/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.11 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 6/12/2019 | 6 | 6/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.5 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 6/12/2019 | 9 | 6/1/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103675.13 | JPC Inspected | ITP 01 Structural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 13/02/2020 | 8 | 2/3/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103673.81 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 13/02/2020 | 6 | 13/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.12 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 13/02/2020 | 11 | 24/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.66 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 13/02/2020 | 9 | 17/02/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103673.80 | Completed and signed off | EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 12/2/2020 | 9 | 17/02/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.79 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 12/2/2020 | 6 | 12/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.11 | Closed | ITP 02 Architectural>Quality Control | QM-FRM-QC-007 Lessons Learned Report | 12/2/2020 | 10 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F103675.10 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/2/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.9 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/2/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.8 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 12/2/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.65 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 11/2/2020 | 9 | 24/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.77 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 11/2/2020 | 6 | 11/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.63 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 11/2/2020 | 9 | 17/02/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103675.7 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 10/2/2020 | 11 | 2/3/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.6 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 8/2/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103675.5 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 8/2/2020 | 9 | 17/02/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.62 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 7/2/2020 | 9 | 17/02/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.61 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 7/2/2020 | 6 | 7/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.74 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 6/2/2020 | 6 | 6/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.73 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 6/2/2020 | 9 | 17/02/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103665.32 | JPC Signed Off / Closed | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-SUB-101 Subcontractor Quality Control Record | 6/2/2020 | 12 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 5
F103665.31 | Open / Ongoing Works | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-CL-ARC-215 External Cladding Inspection | 6/2/2020 | 8 | 6/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103665.30 | Open / Ongoing Works | Level 00 Ground Floor>ITP 02 Architectural>Quality Control | QM-FRM-QC-009 Quality Control Record | 6/2/2020 | 10 | 6/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.334208 | Closed | 1335 - Adare Manor GAB | EHS Inspection. | 5/2/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103673.71 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 5/2/2020 | 9 | 17/02/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103673.70 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 5/2/2020 | 6 | 5/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.60 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 5/2/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.333741 | Closed | 1335 - Adare Manor GAB | EHS Inspection. | 5/2/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.57 | Closed | Site Office & Compound>Site Logistics Plan>JPC Project Management | EHS Inspection. | 5/2/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.56 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 5/2/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.55 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/2/2020 | 9 | 17/02/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103665.29 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 4/2/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103673.69 | Open / Ongoing Works | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/2/2020 | 6 | 4/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 3
F103675.4 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 4/2/2020 | 11 | 24/04/2020 | 0 | 0 | parent | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103672.54 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 4/2/2020 | 9 | 24/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F1.332896 | Closed | 1335 - Adare Manor GAB | EHS Inspection. | 4/2/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.52 | Closed | Training & Practice Area | EHS Inspection. | 4/2/2020 | 9 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103675.3 | Completed and signed off | 1335 - Adare Manor GAB | EHS Managment Inspection - Daily | 3/2/2020 | 9 | 17/02/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.48 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/2/2020 | 6 | 3/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103675.2 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 3/2/2020 | 11 | 24/04/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103665.28 | Closed JPC Reviewed | General QA Records>Quality Management>JPC Project Management | QM-FRM-QC-002B Off Site Inspection - Windows | 3/2/2020 | 10 | 3/2/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F103672.46 | Closed | Safety Notices>EHS Management>JPC Project Management | EHS Inspection. | 31/01/2020 | 9 | 17/02/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.45 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 31/01/2020 | 6 | 31/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.44 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 30/01/2020 | 6 | 30/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.68 | Closed | EHS Inspections>EHS Management>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 30/01/2020 | 9 | 24/02/2020 | 0 | 0 |  | FALSE | FALSE | TRUE |  | 1335 | Closed | 2
F103673.67 | Closed | EHS Inspections>EHS Management>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 30/01/2020 | 9 | 24/02/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.43 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 29/01/2020 | 6 | 29/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.66 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/01/2020 | 9 | 3/2/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F103673.65 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/01/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.64 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/01/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.62 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/01/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.61 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/01/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103672.42 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 28/01/2020 | 9 | 17/02/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103673.60 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 27/01/2020 | 9 | 29/01/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F103672.41 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/01/2020 | 6 | 27/01/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103673.59 | JPC Inspected | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-111 Pre-cast Concrete Inspection | 27/01/2020 | 11 | 2/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.58 | Closed JPC Sign Off | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | QM-CL-CS-108 Underground Services Test | 27/01/2020 | 11 | 27/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103673.57 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/01/2020 | 11 | 29/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103673.56 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 27/01/2020 | 11 | 24/04/2020 | 1 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103667.5 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/12/2019 | 6 | 12/6/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F110033.10 | Open / Ongoing Works | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 4/12/2019 | 7 | 4/12/2019 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F110033.7 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 4/12/2019 | 11 | 8/4/2020 | 0 | 0 | parent | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F110033.6 | JPC Sign Off | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-103 Excavation Inspection | 4/12/2019 | 11 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F110033.5 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 3/12/2019 | 11 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F103672.7 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 3/12/2019 | 9 | 6/1/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103672.5 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/12/2019 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F110033.4 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-104 Fill Placement Inspection | 29/11/2019 | 11 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Open | 4
F110033.3 | JPC Sign Off | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-103 Excavation Inspection | 27/11/2019 | 11 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F103673.4 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 26/11/2019 | 9 | 6/1/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F110033.2 | Open / Ongoing Works | Quality Review - Form & Checklists>Training & Practice Area | QM-CL-CE-302-Bulk Excavation Inspection | 22/11/2019 | 7 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103665.5 | JPC Sign Off | Quality Review - Form & Checklists>Training & Practice Area | QM-FRM-BCAR-800 Specialist Sub-Contractor Inspection | 22/11/2019 | 13 | 26/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 6
F102906.5 | Closed | Site Office & Compound>Site Logistics Plan>JPC Project Management | EHS Inspection. | 14/11/2019 | 9 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F102906.4 | Closed | Training & Practice Area | EHS Inspection. | 14/11/2019 | 9 | 26/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F1.290830 | Closed JPC Reviewed | 1335 - Adare Manor GAB | QM-FRM-QC005 - Training Record | 13/11/2019 | 10 | 22/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F1.282517 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/10/2019 | 6 | 17/11/2019 | 0 | 0 |  | FALSE | FALSE | TRUE |  | 1335 | Closed | 3
F103672.4 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 29/10/2019 | 9 | 13/11/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103673.2 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 23/10/2019 | 9 | 6/1/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F102906.3 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 17/10/2019 | 9 | 13/11/2019 | 0 | 1 | parent | FALSE | TRUE | TRUE |  | 1335 | Closed | 2
F1.275813 | JPC Sign Off | Site Office & Compound>Site Logistics Plan>JPC Project Management | QM-CL-CS-103 Excavation Inspection | 17/10/2019 | 11 | 11/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103665.4 | Completed and signed off | EHS Inspections>EHS Management>JPC Project Management | EHS Managment Inspection - Daily | 16/10/2019 | 9 | 13/11/2019 | 0 | 4 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F1.274706 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/10/2019 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F1.273391 | Open / Ongoing Works | 1335 - Adare Manor GAB | SM-FRM-001 Daily Site Diary | 14/10/2019 | 6 | 14/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F103526.7 | Closed JPC Reviewed | JPC Project Management | QM-FRM-QC005 - Training Record | 11/10/2019 | 10 | 10/2/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103526.5 | Open / Ongoing Works | Sample Drawing 1>Training & Practice Area | QM-CL-CS-110 Concreting Inspection (In Situ) | 11/10/2019 | 11 | 11/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103526.4 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/10/2019 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103667.4 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/10/2019 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE |  | 1335 | Closed | 3
F103667.2 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/10/2019 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103572.2 | Closed JPC Reviewed | JPC Project Management | QM-FRM-QC005 - Training Record | 11/10/2019 | 10 | 13/11/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F103526.2 | Open / Ongoing Works | Sample Drawing 1>Training & Practice Area | SM-FRM-001 Daily Site Diary | 11/10/2019 | 6 | 11/10/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Open | 3
F103573.3 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/10/2019 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103573.2 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 11/10/2019 | 9 | 6/1/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE |  | 1335 | Closed | 2
F110033.13 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-110 Concreting Inspection (In Situ) | 6/12/2019 | 11 | 8/4/2020 | 0 | 0 | parent | FALSE | TRUE | TRUE |  | 1335 | Open | 4
F103665.10 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 6/12/2019 | 6 | 6/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.9 | Closed JPC Reviewed | 1335 - Adare Manor GAB | SM-FRM-002 Progress Record | 5/12/2019 | 6 | 20/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103667.10 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/12/2019 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103667.9 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/12/2019 | 6 | 10/12/2019 | 0 | 0 |  | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103672.8 | Closed | EHS Inspections>EHS Management>JPC Project Management | EHS Inspection. | 4/12/2019 | 9 | 10/12/2019 | 0 | 11 | parent | FALSE | FALSE | FALSE |  | 1335 | Closed | 2
F103667.7 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/12/2019 | 6 | 10/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103665.8 | Closed | Site Management>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/12/2019 | 6 | 4/12/2019 | 0 | 0 |  | FALSE | TRUE | FALSE |  | 1335 | Closed | 3
F103667.6 | Closed | Daily Site Diary>Site Management>JPC Project Management | SM-FRM-008 Cause & Effect Record | 4/12/2019 | 6 | 16/06/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Closed | 3
F103673.55 | Ready to Inspect | Lvl 00 Ground Floor>ITP 01 Structural>Quality Control | BCAR Inspection Form | 24/01/2020 | 3 | 24/01/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F103675.14 | JPC Sign Off | ITP 01 Structural>Quality Control | QM-FRM-QC-001 Benchmark / Sample Form | 13/02/2020 | 10 | 2/3/2020 | 0 | 0 | child | FALSE | TRUE | FALSE |  | 1335 | Closed | 4
F110033.14 | JPC Inspected | LV -01 Basement>ITP 01 Structural>Quality Control | QM-CL-CS-116 Concrete Cube Record | 6/12/2019 | 11 | 8/4/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F110033.11 | Notification | LV -01 Basement>ITP 01 Structural>Quality Control | BCAR Inspection Form | 4/12/2019 | 3 | 4/12/2019 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Closed | 4
F110033.12 | Works Complete | LV -01 Basement>ITP 01 Structural>Quality Control | BCAR Inspection Form | 4/12/2019 | 3 | 29/04/2020 | 0 | 0 | child | FALSE | FALSE | FALSE |  | 1335 | Open | 4
F1.495302 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 14/09/2020 | 6 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.89 | Opened | EHS Inspections>JPC Project Management | AF3 - Thorough Examination of Excavations | 14/09/2020 | 9 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F122846.141 | Open / Ongoing Works | Lvl -00 Foundation>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 14/09/2020 | 11 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F122662.2 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 14/09/2020 | 9 | 14/09/2020 | 13 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F122846.140 | Open / Ongoing Works | Lvl 00 Lower Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 11/9/2020 | 10 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Open | 4
F122803.17 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/9/2020 | 9 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F129710.40 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.39 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/9/2020 | 9 | 10/9/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F1.492273 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.492261 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.492231 | In Process / Manufactor | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 10/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F122846.139 | Open / Ongoing Works | Lvl -00 Foundation>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 10/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Open | 4
F119863.87 | Open / Ongoing Works | Items to Be Deleted | CM-EHS-FRM-007 COVID-19 Inspection | 9/9/2020 | 9 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F121436.57 | Closed JPC Reviewed | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 9/9/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 4
F1.490705 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122662.1 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 9/9/2020 | 9 | 9/9/2020 | 8 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F123599.18 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 9/9/2020 | 9 | 9/9/2020 | 7 | 12 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.490281 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 9/9/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F121354.17 | Open / Ongoing Works | ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 9/9/2020 | 13 | 9/9/2020 | 6 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F121354.15 | Open / Ongoing Works | ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 9/9/2020 | 13 | 9/9/2020 | 7 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F1.490043 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.38 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.37 | Closed | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.36 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F121436.56 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 8/9/2020 | 1 | 7 | parent | FALSE | FALSE | TRUE | FALSE | 1338 | Open | 2
F1.488934 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.138 | Open / Ongoing Works | Substation 5&6>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-003 Protection of Finishes Inspection | 7/9/2020 | 10 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F129710.35 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.137 | Open / Ongoing Works | Lvl 00 Lower Ground>Carpark Entrance Building>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F122846.135 | Open / Ongoing Works | Lvl 00 Ground Floor>Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Open | 4
F122846.134 | Open / Ongoing Works | Lvl 00 Ground Floor>Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Open | 4
F122841.20 | Open / Ongoing Works | Lvl 00 Lower Ground>Carpark Entrance Building>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 7/9/2020 | 12 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 5
F142890.1 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/9/2020 | 9 | 7/9/2020 | 5 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.487765 | Open / Ongoing Works | Lvl -00 Foundation>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F121436.55 | Open / Ongoing Works | JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 4/9/2020 | 1 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.486815 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/9/2020 | 9 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122846.133 | Open / Ongoing Works | Lvl -00 Foundation>Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 4/9/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Open | 4
F119863.86 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 4/9/2020 | 5 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.486185 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.34 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.485746 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.485545 | Open / Ongoing Works | 1338 - Kildare Village | CM-EHS-FRM-001 EHS Daily Management Inspection | 3/9/2020 | 9 | 3/9/2020 | 3 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122846.132 | Open / Ongoing Works | Unit 105>Lvl 00 Ground Floor>Block B>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 3/9/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F1.485455 | Open / Ongoing Works | Block C>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 3/9/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F119863.85 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 3/9/2020 | 9 | 3/9/2020 | 7 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122846.131 | Open / Ongoing Works | Carpark>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 3/9/2020 | 10 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F121354.14 | Open / Ongoing Works | ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 3/9/2020 | 13 | 3/9/2020 | 7 | 11 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F129710.33 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.129 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 2/9/2020 | 9 | 2/9/2020 | 4 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.484380 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.128 | Open / Ongoing Works | Items to Be Deleted | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 2/9/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Open | 4
F1.483711 | Open / Ongoing Works | Lvl -00 Foundation>Block C>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 2/9/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.483705 | Open / Ongoing Works | Lvl -00 Foundation>Block C>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 2/9/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.483692 | Open / Ongoing Works | Lvl -00 Foundation>Block C>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 2/9/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.483673 | Open / Ongoing Works | Lvl -00 Foundation>Block C>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 2/9/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.483660 | Open / Ongoing Works | Lvl -00 Foundation>Block C>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 2/9/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.483625 | Open / Ongoing Works | Lvl -00 Foundation>Block C>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 2/9/2020 | 11 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.483490 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.482868 | Open | Items to Be Deleted | QM-FRM-QC005 - Training Record | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.482251 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.482248 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F119863.84 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 31/08/2020 | 2 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.482220 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 31/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.83 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 31/08/2020 | 4 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1338 | Open | 2
F1.482210 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 31/08/2020 | 10 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F119863.82 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/08/2020 | 9 | 28/08/2020 | 5 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122841.19 | Open / Ongoing Works | Lvl 00 Lower Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 28/08/2020 | 12 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 5
F121354.11 | Open / Ongoing Works | ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 28/08/2020 | 13 | 28/08/2020 | 5 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F121354.10 | Open / Ongoing Works | Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 28/08/2020 | 13 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F121354.9 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 28/08/2020 | 13 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F122803.15 | Opened | EHS Inspections>JPC Project Management | AF3 - Thorough Examination of Excavations | 28/08/2020 | 9 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122803.14 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/08/2020 | 9 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.480421 | Open / Ongoing Works | Lvl -00 Foundation>Block C>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 27/08/2020 | 11 | 27/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.480419 | Open / Ongoing Works | Lvl -00 Foundation>Block C>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 27/08/2020 | 11 | 27/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.480393 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.127 | Open / Ongoing Works | Lvl -00 Foundation>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 27/08/2020 | 11 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F122846.126 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 26/08/2020 | 9 | 26/08/2020 | 2 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F119863.81 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/08/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122841.17 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 25/08/2020 | 9 | 25/08/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.476826 | JPC Inspected | 1338 - Kildare Village | QM-FRM-MEP-404 Electrical Inspection Report | 25/08/2020 | 1 | 25/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.476816 | JPC Inspected | 1338 - Kildare Village | QM-CL-ME-402 Electrical Inspection | 25/08/2020 | 1 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.476800 | JPC Inspected | 1338 - Kildare Village | QM-FRM-MEP-404 Electrical Inspection Report | 25/08/2020 | 1 | 25/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.476756 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 25/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F123599.17 | Opened | EHS Inspections>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 25/08/2020 | 9 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.476251 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 24/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F123599.16 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 24/08/2020 | 9 | 24/08/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 2
F123599.15 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 24/08/2020 | 9 | 24/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F122846.125 | JPC Sign Off | Lvl -00 Foundation>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 21/08/2020 | 10 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 4
F121354.8 | Open / Ongoing Works | 1338 - Kildare Village | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 21/08/2020 | 13 | 21/08/2020 | 11 | 16 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 6
F1.473743 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 21/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.80 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 20/08/2020 | 9 | 20/08/2020 | 6 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F119863.79 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 20/08/2020 | 9 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F122846.124 | Open / Ongoing Works | Unit 110>Lvl 00 Ground Floor>Block B>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F122846.123 | Open / Ongoing Works | Unit 107>Lvl 00 Ground Floor>Block B>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F122846.122 | Open / Ongoing Works | Unit 105>Lvl 00 Ground Floor>Block B>ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F122846.121 | Open / Ongoing Works | Lvl 01 Mezzanine>Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F122846.120 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F122846.119 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 20/08/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F1.471387 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 19/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.471132 | Open / Ongoing Works | Lvl -00 Foundation>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 19/08/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.470618 | Closed | Block A>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 18/08/2020 | 10 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.470196 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 18/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.78 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 18/08/2020 | 9 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.469353 | Open / Ongoing Works | Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 17/08/2020 | 11 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Open | 4
F1.468895 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 17/08/2020 | 10 | 2/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.468559 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.468541 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122841.16 | JPC Signed Off / Closed | Lvl 00 Lower Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 14/08/2020 | 12 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 5
F122846.117 | Open / Ongoing Works | Lvl -00 Foundation>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 14/08/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Open | 4
F1.467276 | Open / Ongoing Works | 00 Lower Gound>Carpark>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 14/08/2020 | 10 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F119863.77 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/08/2020 | 9 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.466192 | Open / Ongoing Works | Unit 108>Lvl 00 Ground Floor>Block B>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 13/08/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.466028 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 13/08/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.76 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 12/8/2020 | 9 | 12/8/2020 | 6 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.464718 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 12/8/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.464373 | JPC Inspected | 1338 - Kildare Village | QM-FRM-QC-002 Off Site Inspection | 12/8/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F132838.4 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/8/2020 | 9 | 11/8/2020 | 3 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.463394 | Works Complete / Resolved | Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 11/8/2020 | 8 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.463289 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 11/8/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.463009 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 11/8/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.462706 | Open / Ongoing Works | 00 Lower Gound>Carpark>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.462678 | Open / Ongoing Works | 00 Lower Gound>Carpark>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.462670 | Open / Ongoing Works | Lvl -00 Foundation>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F121436.54 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/8/2020 | 9 | 10/8/2020 | 1 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F121436.53 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/8/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.462632 | Open / Ongoing Works | Unit 105>Lvl 00 Ground Floor>Block B>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.462367 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F122846.116 | Open / Ongoing Works | JPC Project Management | QM-FRM-QC-004 QC Observation Report | 10/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F122846.115 | Closed JPC Sign Off | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 9/8/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1338 | Closed | 4
F122846.114 | Closed JPC Reviewed | Training Records - EHS & Quality>JPC Project Management | QM-FRM-QC005 - Training Record | 9/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F122841.15 | Open / Ongoing Works | Lvl 00 Lower Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 7/8/2020 | 12 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 5
F119863.75 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 7/8/2020 | 9 | 7/8/2020 | 5 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F121436.52 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 7/8/2020 | 9 | 7/8/2020 | 7 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.460527 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 7/8/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.113 | Open / Ongoing Works | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 7/8/2020 | 10 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F122841.14 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/8/2020 | 9 | 7/8/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F122846.112 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.459103 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 6/8/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.32 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 5/8/2020 | 9 | 31/08/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F129710.31 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.30 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.457851 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 5/8/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.74 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/8/2020 | 9 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122846.111 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 4/8/2020 | 10 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F1.455600 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/8/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.28 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-007 - Crane Co-ordination Meeting | 31/07/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F129710.27 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/07/2020 | 6 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122841.11 | Open / Ongoing Works | 1338 - Kildare Village | QM-FRM-SUB-101 Subcontractor Quality Control Record | 31/07/2020 | 12 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 5
F1.453408 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 31/07/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.73 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 30/07/2020 | 9 | 30/07/2020 | 6 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F121436.51 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 30/07/2020 | 9 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.452189 | Open / Ongoing Works | Lvl -00 Piling>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 30/07/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.452146 | Open / Ongoing Works | Lvl -00 Piling>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 30/07/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F122846.110 | Closed JPC Sign Off | Lvl 00 Lower Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 30/07/2020 | 11 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F1.451921 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 30/07/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.26 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.25 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122803.13 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/07/2020 | 9 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122803.12 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 29/07/2020 | 9 | 29/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.450657 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 29/07/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.109 | Closed JPC Sign Off | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 28/07/2020 | 11 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.108 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/07/2020 | 9 | 28/07/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.449925 | Open / Ongoing Works | 1338 - Kildare Village | JPC-QA-RP-003 - Site Audit Report | 28/07/2020 | 2 | 28/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1338 | Open | 3
F122846.107 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 28/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.24 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.23 | Closed | Items to Be Deleted | SM-FRM-003 Daily Allocation Sheet | 27/07/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F129710.22 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/07/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122841.10 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/07/2020 | 9 | 27/07/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F122841.9 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 27/07/2020 | 9 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.448598 | Open / Ongoing Works | Lvl 00 Lower Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 27/07/2020 | 12 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 5
F122846.106 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.105 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 27/07/2020 | 10 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F1.447241 | Open / Ongoing Works | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 24/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.447078 | 3rd Party Sign Off - Closed | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 24/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F132838.3 | Closed | Statuatory Forms>JPC Project Management | AF3 - Thorough Examination of Excavations | 24/07/2020 | 9 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F132838.2 | Closed | Statuatory Forms>JPC Project Management | AF3 - Thorough Examination of Excavations | 24/07/2020 | 9 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F1.447013 | Open / Ongoing Works | 00 Lower Gound>Carpark>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 24/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F121354.6 | Open / Ongoing Works | ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 24/07/2020 | 13 | 24/07/2020 | 5 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F121354.5 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 02 Architectural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 24/07/2020 | 13 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F121354.3 | Open / Ongoing Works | 1338 - Kildare Village | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 24/07/2020 | 13 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F1.446612 | Open / Ongoing Works | 1338 - Kildare Village | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 24/07/2020 | 13 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F1.446534 | 3rd Party Sign Off - Closed | Lvl 00 Lower Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 24/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F1.446438 | 3rd Party Sign Off - Closed | Unit 105>Lvl 00 Ground Floor>Block B>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 24/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F1.446417 | 3rd Party Sign Off - Closed | 00 Lower Ground>Carpark Entrance Building>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 24/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F129710.19 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.446011 | Open / Ongoing Works | Lvl 00 Lower Ground>Carpark Entrance Building>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-ARC-201 Waterproofing / Tanking Inspection | 23/07/2020 | 8 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.445918 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 23/07/2020 | 11 | 23/07/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F1.445821 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 23/07/2020 | 11 | 23/07/2020 | 3 | 3 | parent | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 4
F119863.72 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 23/07/2020 | 9 | 23/07/2020 | 7 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F129710.18 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.17 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.16 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/07/2020 | 9 | 31/08/2020 | 0 | 11 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.103 | Closed JPC Sign Off | Lvl -00 Foundation>Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 22/07/2020 | 11 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F1.444490 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 22/07/2020 | 10 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F136508.3 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 21/07/2020 | 9 | 21/07/2020 | 1 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F136508.2 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 21/07/2020 | 9 | 21/07/2020 | 1 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F122846.102 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 21/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.15 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F136508.1 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 20/07/2020 | 9 | 20/07/2020 | 3 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122846.101 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 20/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F119863.71 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/07/2020 | 9 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122846.100 | Closed JPC Sign Off | Lvl 00 Lower Ground>Carpark Entrance Building>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 20/07/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.98 | Open / Ongoing Works | Lvl 00 Lower Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 20/07/2020 | 11 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Open | 4
F122846.97 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 20/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.14 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 3
F122846.96 | Closed JPC Sign Off | Substation 5&6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 17/07/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Closed | 4
F122846.95 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 17/07/2020 | 10 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F129710.13 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.12 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.438674 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 15/07/2020 | 10 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.438670 | Notification | 1338 - Kildare Village | BCAR Inspection Form | 15/07/2020 | 3 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.438667 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 15/07/2020 | 10 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.438664 | Open / Ongoing Works | Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 15/07/2020 | 10 | 15/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F122846.94 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 15/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122841.8 | Completed and signed off | Training Records - EHS & Quality>JPC Project Management | EHS Managment Inspection - Daily | 15/07/2020 | 9 | 7/9/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.93 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 15/07/2020 | 9 | 15/07/2020 | 0 | 7 | parent | FALSE | FALSE | TRUE | FALSE | 1338 | Open | 2
F119863.70 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 15/07/2020 | 9 | 15/07/2020 | 10 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.437438 | Open / Ongoing Works | Lessons Learned & Alerts - EHS & Quality>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 14/07/2020 | 10 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F1.437436 | Open / Ongoing Works | Substation 5&6>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 14/07/2020 | 10 | 14/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F123599.14 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 14/07/2020 | 9 | 25/08/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F129710.11 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F123599.13 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 14/07/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F121360.3 | Open / Ongoing Works | ITP 02 Architectural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 14/07/2020 | 13 | 14/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F122846.91 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 14/07/2020 | 11 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F123599.11 | JPC Inspected | Audit & Assessment - EHS & Quality>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 14/07/2020 | 10 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F119863.68 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/07/2020 | 9 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122846.90 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 14/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.89 | Closed JPC Sign Off | Lvl -00 Foundation>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 14/07/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Closed | 4
F129710.10 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 3
F122846.88 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 13/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.87 | 3rd Party Sign Off - Closed | Lvl -00 Foundation>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 12/7/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F122846.86 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 12/7/2020 | 11 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.85 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 12/7/2020 | 11 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.84 | Closed JPC Sign Off | Lvl 00 Lower Ground>Carpark Entrance Building>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 12/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Closed | 4
F122846.83 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 12/7/2020 | 11 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122841.7 | JPC Signed Off / Closed | Lvl 00 Lower Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-SUB-101 Subcontractor Quality Control Record | 10/7/2020 | 12 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 5
F122846.81 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 10/7/2020 | 10 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F119863.67 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/7/2020 | 9 | 10/8/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.66 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 10/7/2020 | 9 | 10/8/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F129710.9 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.7 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2020 | 9 | 10/8/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.80 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 8/7/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F129710.6 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F129710.5 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F122846.79 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 7/7/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F121436.49 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 7/7/2020 | 9 | 10/8/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F119863.64 | 3rd Party Sign Off - Closed | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 7/7/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 4
F122846.77 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 6/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Closed | 4
F1.429767 | JPC Sign Off / Closed | 1338 - Kildare Village | QM-CL-ME-402 Electrical Inspection | 6/7/2020 | 1 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.429753 | Closed JPC Reviewed | 1338 - Kildare Village | QM-FRM-QC005 - Training Record | 6/7/2020 | 10 | 6/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F122846.76 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 6/7/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.429714 | Open / Ongoing Works | Lessons Learned & Alerts - EHS & Quality>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 6/7/2020 | 10 | 6/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F121436.48 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/7/2020 | 9 | 10/8/2020 | 0 | 12 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F121436.47 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 6/7/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.75 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 4/7/2020 | 10 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 4
F122846.74 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 4/7/2020 | 11 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.73 | Closed JPC Sign Off | Substation 7&8>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 4/7/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Closed | 4
F122846.72 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 4/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Closed | 4
F122846.69 | Closed JPC Sign Off | Lvl -00 Foundation>Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 4/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.68 | Open / Ongoing Works | Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 4/7/2020 | 11 | 4/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Open | 4
F1.428604 | Notification | 1338 - Kildare Village | BCAR Inspection Form | 3/7/2020 | 3 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.428603 | Notification | 1338 - Kildare Village | BCAR Inspection Form | 3/7/2020 | 3 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.428602 | Notification | 1338 - Kildare Village | BCAR Inspection Form | 3/7/2020 | 3 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.428600 | Notification | 1338 - Kildare Village | BCAR Inspection Form | 3/7/2020 | 3 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.428486 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 3/7/2020 | 9 | 3/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.427962 | JPC Inspected | Quality Control & BC(A)R | QM-FRM-QC-002 Off Site Inspection | 3/7/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Open | 4
F122846.67 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/7/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F121436.46 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 2/7/2020 | 9 | 15/07/2020 | 8 | 30 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F122846.66 | Closed | EHS Inspections>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 1/7/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.65 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 1/7/2020 | 9 | 5/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.64 | Closed JPC Sign Off | Substation 7&8>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 30/06/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.63 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 30/06/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.61 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/06/2020 | 9 | 6/7/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F122846.62 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 29/06/2020 | 10 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F1.422412 | Open / Ongoing Works | Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 26/06/2020 | 10 | 26/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F122846.61 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 25/06/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.60 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/06/2020 | 9 | 5/8/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.60 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 25/06/2020 | 9 | 13/07/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.59 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 24/06/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122803.9 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 23/06/2020 | 9 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122846.58 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 23/06/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122841.6 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/06/2020 | 9 | 7/9/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.56 | Closed JPC Sign Off | Substation 7&8>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 22/06/2020 | 11 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.55 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 22/06/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F123605.2 | Works Complete / Resolved | ITP 02 Architectural>Quality Control & BC(A)R | QM-CL-ARC-218 Architectural Wall Panel Inspection | 22/06/2020 | 8 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F123605.1 | JPC Sign Off | Substation 5&6>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 22/06/2020 | 10 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F132838.1 | Open / Ongoing Works | Lvl 00 Ground Floor>Block B>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 22/06/2020 | 11 | 22/06/2020 | 5 | 5 | parent | FALSE | TRUE | TRUE | TRUE | 1338 | Open | 4
F123599.10 | Rejected / Action Required | 00 Lower Gound>Carpark>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/06/2020 | 10 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F122846.54 | Open / Ongoing Works | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/06/2020 | 10 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F122846.53 | 3rd Party Sign Off - Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/06/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 4
F122846.52 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 19/06/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 4
F122846.51 | Closed JPC Sign Off | Substation 7&8>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 19/06/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Closed | 4
F122846.50 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 19/06/2020 | 6 | 19/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F123599.9 | JPC Sign Off | 00 Lower Gound>Carpark>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/06/2020 | 10 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F123599.8 | JPC Sign Off | 00 Lower Gound>Carpark>ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 19/06/2020 | 10 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F122846.49 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 18/06/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.58 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 18/06/2020 | 9 | 6/7/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F119863.57 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 18/06/2020 | 9 | 13/07/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.48 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 17/06/2020 | 11 | 19/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.47 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/06/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.46 | Open / Ongoing Works | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 16/06/2020 | 10 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1338 | Open | 4
F122846.44 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 16/06/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.43 | Closed JPC Sign Off | Substation 7&8>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 16/06/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.42 | Closed JPC Sign Off | Substation 7&8>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 16/06/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.41 | Closed JPC Sign Off | Substation 7&8>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 16/06/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.40 | Closed JPC Sign Off | Substation 7&8>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 16/06/2020 | 11 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.38 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 16/06/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.412922 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 16/06/2020 | 10 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.412724 | Closed | Environmental Inspections>JPC Project Management | QM-FRM-QC-004 QC Observation Report | 16/06/2020 | 10 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F119863.56 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 15/06/2020 | 9 | 27/07/2020 | 0 | 10 | parent | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 2
F122846.35 | Open / Ongoing Works | Underground Services>Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 15/06/2020 | 7 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F122803.8 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 12/6/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.55 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.33 | Closed JPC Sign Off | Substation 5&6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 11/6/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.32 | Closed JPC Sign Off | Substation 5&6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 11/6/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F119863.54 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 11/6/2020 | 9 | 13/07/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122841.5 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2020 | 9 | 7/9/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F123599.6 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2020 | 9 | 17/06/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F121436.44 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/6/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.31 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 10/6/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F121436.43 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/6/2020 | 9 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.408413 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/6/2020 | 9 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F1.408365 | Completed and signed off | 1338 - Kildare Village | EHS Managment Inspection - Daily | 10/6/2020 | 9 | 6/7/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F1.408071 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 9/6/2020 | 9 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Open | 2
F121436.42 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/6/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.30 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 9/6/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F121436.41 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/6/2020 | 9 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122846.29 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 8/6/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F121436.40 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 5/6/2020 | 9 | 17/06/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.28 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 5/6/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F121436.39 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/6/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.27 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 5/6/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.52 | Open / Ongoing Works | Retail>Foul & Storm Water>Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-108 Underground Services Test | 4/6/2020 | 11 | 4/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F119863.50 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 4/6/2020 | 9 | 17/06/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F119863.49 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 4/6/2020 | 9 | 13/07/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F121436.38 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/6/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.26 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/6/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122803.7 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 3/6/2020 | 9 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F121436.37 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/6/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.25 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 3/6/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.24 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/6/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.23 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 2/6/2020 | 9 | 5/8/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F119863.46 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/6/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.22 | Closed JPC Sign Off | Lvl 01 Upper Ground>Carpark>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 2/6/2020 | 11 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.21 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 2/6/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F1.400841 | Notification | 1338 - Kildare Village | BCAR Inspection Form | 29/05/2020 | 3 | 29/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F119863.45 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/05/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.20 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 29/05/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F119863.44 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/05/2020 | 9 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F123599.2 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/05/2020 | 9 | 17/06/2020 | 0 | 9 | parent | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 2
F122846.19 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 28/05/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F121436.36 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 27/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.399245 | Notification | 1338 - Kildare Village | BCAR Inspection Form | 27/05/2020 | 3 | 27/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F122841.4 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/05/2020 | 9 | 27/05/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.399168 | Closed JPC Sign Off | Substation 5&6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 27/05/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.18 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/05/2020 | 6 | 19/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.17 | Closed JPC Sign Off | Substation 5&6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 26/05/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122846.16 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/05/2020 | 6 | 19/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F122846.15 | Closed | JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/05/2020 | 6 | 19/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 3
F121436.35 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/05/2020 | 9 | 26/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F129710.3 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/05/2020 | 9 | 31/08/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F121436.34 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/05/2020 | 9 | 17/06/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F121436.33 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 25/05/2020 | 9 | 13/07/2020 | 0 | 15 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F121436.32 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/05/2020 | 9 | 25/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 2
F121436.31 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/05/2020 | 9 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 2
F122803.6 | Opened | JPC Project Management | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 22/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F122803.5 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/05/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.396139 | Open / Ongoing Works | ITP 02 Architectural>Quality Control & BC(A)R | QM-FRM-ARC-201 Benchmark / Sample Form | 21/05/2020 | 8 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F119863.43 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 21/05/2020 | 9 | 13/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F121436.30 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/05/2020 | 9 | 21/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F129710.4 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F129710.1 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F121436.29 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/05/2020 | 9 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.395084 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F122803.4 | Opened | EHS Inspections>JPC Project Management | AF3 - Thorough Examination of Excavations | 20/05/2020 | 9 | 20/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F1.394605 | Closed | 1338 - Kildare Village | AF3 - Thorough Examination of Excavations | 19/05/2020 | 9 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F1.394586 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/05/2020 | 9 | 7/9/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122841.3 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/05/2020 | 9 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F121436.28 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 19/05/2020 | 9 | 19/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F1.393992 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F121436.27 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 18/05/2020 | 9 | 18/05/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 2
F1.374249 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374246 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374244 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374243 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374239 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374237 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374234 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374233 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374230 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374228 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374225 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374220 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374219 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374216 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374199 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374198 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374196 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374195 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374194 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374189 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374186 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374185 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374183 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374180 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374177 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374176 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374174 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374173 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374169 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374165 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 3
F1.374164 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374162 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374160 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374159 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374156 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374151 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374149 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374148 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374147 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374146 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.374143 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/4/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.373789 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/4/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 3
F1.373785 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/4/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 3
F1.373779 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/4/2020 | 6 | 15/04/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 3
F1.373053 | 3rd Party Sign Off - Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 7/4/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F1.373038 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/4/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 3
F1.372656 | Open / Ongoing Works | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 6/4/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.372317 | Open / Ongoing Works | ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 6/4/2020 | 10 | 6/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.371347 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/4/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 3
F1.371343 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/4/2020 | 6 | 3/4/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 3
F1.371315 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/4/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 3
F1.371149 | Open / Ongoing Works | ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 2/4/2020 | 10 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F1.371140 | Open / Ongoing Works | ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 2/4/2020 | 10 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F1.371113 | Open / Ongoing Works | ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 2/4/2020 | 10 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F1.369515 | Closed JPC Sign Off | Lvl -00 Piling>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 31/03/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Closed | 4
F122846.13 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/03/2020 | 9 | 2/4/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.9 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/03/2020 | 9 | 5/8/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.8 | Closed JPC Sign Off | Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 27/03/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F119863.42 | Open | EHS Inspections>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 27/03/2020 | 9 | 27/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F119863.41 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 27/03/2020 | 9 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.7 | Closed JPC Sign Off | Lvl -00 Foundation>Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 26/03/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F119863.40 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 26/03/2020 | 9 | 13/07/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.39 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 26/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.5 | Closed JPC Sign Off | Lvl -00 Foundation>Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 26/03/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F122841.2 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/03/2020 | 9 | 7/9/2020 | 0 | 3 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F1.366821 | Open / Ongoing Works | ITP 02 Architectural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 25/03/2020 | 13 | 25/03/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F119863.38 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 25/03/2020 | 9 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122846.4 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 24/03/2020 | 9 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.37 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 24/03/2020 | 9 | 2/4/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.36 | Open / Ongoing Works | Retail>Foul & Storm Water>Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 24/03/2020 | 7 | 24/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F119863.35 | JPC Inspected | Retail>Foul & Storm Water>Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-108 Underground Services Test | 24/03/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F119863.34 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 24/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F1.365854 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 24/03/2020 | 9 | 15/04/2020 | 0 | 9 | parent | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 2
F119863.33 | Open / Ongoing Works | Retail>Foul & Storm Water>Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 23/03/2020 | 7 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F119863.32 | JPC Inspected | Retail>Foul & Storm Water>Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-108 Underground Services Test | 23/03/2020 | 11 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 4
F121436.25 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 23/03/2020 | 9 | 26/03/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.3 | Closed JPC Sign Off | Lvl -00 Foundation>Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 23/03/2020 | 11 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F119863.31 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 23/03/2020 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F1.365255 | Closed | Statuatory Forms>JPC Project Management | AF3 - Thorough Examination of Excavations | 23/03/2020 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F1.365250 | Closed | Statuatory Forms>JPC Project Management | AF3 - Thorough Examination of Excavations | 23/03/2020 | 9 | 23/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.30 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 20/03/2020 | 9 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F119863.29 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 19/03/2020 | 9 | 13/07/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.28 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 19/03/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.27 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 19/03/2020 | 9 | 2/4/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F122846.2 | Open / Ongoing Works | Lvl -00 Foundation>Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 19/03/2020 | 11 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Open | 4
F122846.1 | Closed JPC Sign Off | Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 19/03/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F121436.24 | Closed JPC Sign Off | Substation 5&6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 18/03/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F119863.26 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 18/03/2020 | 9 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.25 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 13/03/2020 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F123603.3 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 13/03/2020 | 9 | 13/03/2020 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 2
F119863.24 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 13/03/2020 | 9 | 2/4/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F121436.23 | Closed JPC Sign Off | Lvl -00 Foundation>Block A>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 13/03/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F119863.23 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 12/3/2020 | 9 | 31/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F123603.2 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 12/3/2020 | 9 | 12/3/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 2
F119863.22 | Closed JPC Sign Off | Lvl -00 Foundation>Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 11/3/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F119863.21 | Closed JPC Sign Off | Lvl -00 Piling>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 11/3/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Closed | 4
F119863.20 | Closed JPC Sign Off | Lvl -00 Piling>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 11/3/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Closed | 4
F119863.19 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 11/3/2020 | 9 | 2/4/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F123603.1 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/3/2020 | 9 | 2/4/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122803.3 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 9/3/2020 | 9 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Open | 2
F122803.2 | Open / Ongoing Works | Lvl -00 Foundation>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 9/3/2020 | 11 | 9/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Open | 4
F121436.22 | Closed JPC Sign Off | Lvl -00 Piling>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 6/3/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Closed | 4
F122803.1 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/3/2020 | 9 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F123599.1 | Open / Ongoing Works | Lvl -00 Foundation>Block A>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 6/3/2020 | 11 | 6/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F119863.18 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 5/3/2020 | 9 | 6/7/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F119863.17 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 5/3/2020 | 9 | 13/07/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F121436.20 | Closed JPC Sign Off | Lvl -00 Foundation>Block B>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 4/3/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F119863.16 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 4/3/2020 | 9 | 31/08/2020 | 0 | 6 | parent | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 2
F121436.11 | Closed JPC Sign Off | Lvl -00 Piling>Carpark>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 4/3/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Closed | 4
F122841.1 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 3/3/2020 | 9 | 7/9/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F119863.14 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 2/3/2020 | 9 | 1/4/2020 | 0 | 6 | parent | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 2
F121436.10 | Closed JPC Sign Off | Substation 7&8>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 2/3/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1338 | Closed | 4
F1.350425 | Open / Ongoing Works | Lvl -00 Foundation>Block B>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 28/02/2020 | 10 | 28/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F119863.10 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/02/2020 | 9 | 2/4/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F119863.9 | JPC Sign Off | Lvl -00 Foundation>Block A>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 28/02/2020 | 11 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 4
F121436.9 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/02/2020 | 9 | 2/4/2020 | 0 | 5 | parent | FALSE | FALSE | TRUE | FALSE | 1338 | Closed | 2
F119863.8 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 27/02/2020 | 9 | 13/07/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F121436.8 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/02/2020 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F121436.7 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 24/02/2020 | 9 | 1/3/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F121483.1 | Closed | Training Records - EHS & Quality>JPC Project Management | JPC-HR-FRM-001 - Training Record | 20/02/2020 | 2 | 21/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1338 | Closed | 3
F121354.1 | Open / Ongoing Works | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-BCAR-100 Structural BCAR Inspection | 20/02/2020 | 13 | 20/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 6
F121436.3 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/02/2020 | 9 | 1/3/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Closed | 2
F119863.7 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 18/02/2020 | 9 | 17/06/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.6 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 17/02/2020 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F119863.5 | Open / Ongoing Works | Permit to Work>JPC Project Management | QM-CL-CS-103 Excavation Inspection | 17/02/2020 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F119863.4 | Open / Ongoing Works | Permit to Work>JPC Project Management | QM-CL-CS-103 Excavation Inspection | 17/02/2020 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F119863.3 | Open / Ongoing Works | Permit to Work>JPC Project Management | QM-CL-CS-103 Excavation Inspection | 17/02/2020 | 11 | 17/02/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1338 | Open | 4
F119863.2 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 14/02/2020 | 9 | 2/4/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1338 | Closed | 2
F119863.1 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 13/02/2020 | 9 | 1/4/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1338 | Closed | 2
F122032.254 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 15/09/2020 | 9 | 15/09/2020 | 5 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 2
F132455.192 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 15/09/2020 | 6 | 15/09/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.253 | Open / Ongoing Works | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/09/2020 | 6 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 3
F132455.191 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 14/09/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.50 | Closed | Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 14/09/2020 | 10 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F122033.38 | Open / Ongoing Works | Audit & Assessment - EHS & Quality>JPC Project Management | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 14/09/2020 | 10 | 14/09/2020 | 1 | 1 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Open | 4
F132455.190 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/09/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F1.494888 | Open / Ongoing Works | Items to Be Deleted | SM-FRM-001 Daily Site Diary | 14/09/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 3
F122032.252 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/09/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.49 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132454.48 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 14/09/2020 | 10 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F122032.251 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/09/2020 | 9 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 2
F122033.37 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/09/2020 | 9 | 14/09/2020 | 2 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 2
F129642.252 | Open / Ongoing Works | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 14/09/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 3
F129642.251 | Open / Ongoing Works | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 14/09/2020 | 9 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 2
F132455.189 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/9/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.188 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 11/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.47 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/9/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122033.36 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/9/2020 | 9 | 11/9/2020 | 6 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 2
F129642.250 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 11/9/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.249 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 11/9/2020 | 9 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.186 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.45 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132455.185 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.184 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 10/9/2020 | 6 | 10/9/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.183 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/9/2020 | 9 | 10/9/2020 | 2 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 2
F129642.248 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 10/9/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.247 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 10/9/2020 | 9 | 14/09/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.182 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.181 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.180 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132454.44 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 9/9/2020 | 9 | 9/9/2020 | 2 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 2
F122033.35 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 9/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F129642.246 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 9/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.245 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 9/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.179 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.178 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.43 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 10/9/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132455.177 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 8/9/2020 | 6 | 8/9/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.244 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 8/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.250 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.243 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 8/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.176 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F1.488016 | 3rd Party Sign Off - Closed | CB-11>Zone 2>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-002 Design Team Inspection Report - Non BC(A)R | 7/9/2020 | 13 | 9/9/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 6
F122032.249 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/9/2020 | 9 | 7/9/2020 | 1 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 2
F132455.175 | Open / Ongoing Works | CB-11>Zone 2>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F132455.174 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.248 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.242 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 7/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.241 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 7/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.173 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132455.172 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122033.34 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 10/9/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.247 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.240 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 4/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.239 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 4/9/2020 | 9 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.170 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.169 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.168 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 3/9/2020 | 6 | 3/9/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122033.30 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 3/9/2020 | 9 | 10/9/2020 | 0 | 13 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.246 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.238 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 3/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.237 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 3/9/2020 | 9 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.167 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.166 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.42 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 2/9/2020 | 9 | 10/9/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.245 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.236 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 2/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F129642.235 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 2/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.165 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 1/9/2020 | 6 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.164 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.163 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 1/9/2020 | 9 | 1/9/2020 | 1 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 2
F132455.161 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 1/9/2020 | 6 | 1/9/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.244 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.234 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 1/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.233 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 1/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F1.482187 | 3rd Party Sign Off - Closed | CB-08>Zone 2>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 31/08/2020 | 13 | 1/9/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 6
F122032.243 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 31/08/2020 | 9 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 2
F132455.160 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.242 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.241 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 31/08/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 2
F132455.159 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.158 | Open / Ongoing Works | CB-08>Zone 2>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 31/08/2020 | 11 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 4
F129642.232 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 31/08/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.231 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 31/08/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.240 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/08/2020 | 9 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 2
F132455.157 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.156 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 28/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.155 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/08/2020 | 9 | 28/08/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 2
F1.481102 | Closed | EHS Inspections>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 28/08/2020 | 9 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132455.154 | Open / Ongoing Works | CB-07>Zone 2>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 28/08/2020 | 11 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F129642.229 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 28/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.239 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.228 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 28/08/2020 | 9 | 31/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.238 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.237 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.153 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.152 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 27/08/2020 | 6 | 27/08/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122033.29 | Closed | Main Site Set Up Plan>Site Logistics, Access & Deliveries | CM-EHS-FRM-001 EHS Daily Management Inspection | 27/08/2020 | 9 | 7/9/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F132455.151 | Closed | Zone 2>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 27/08/2020 | 10 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.227 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 27/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.226 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 27/08/2020 | 9 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.149 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.41 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 26/08/2020 | 9 | 10/9/2020 | 0 | 15 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132455.148 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.236 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.225 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 26/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.224 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 26/08/2020 | 9 | 28/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.147 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 25/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.146 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.145 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 25/08/2020 | 6 | 25/08/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.235 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 25/08/2020 | 9 | 28/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.223 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 25/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.233 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.222 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 25/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.144 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 24/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.143 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.232 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.142 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 24/08/2020 | 9 | 24/08/2020 | 0 | 13 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 2
F129642.221 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 24/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.219 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 24/08/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.141 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 21/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.140 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.40 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 21/08/2020 | 9 | 28/08/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.231 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.217 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 21/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F129642.216 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 21/08/2020 | 9 | 24/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.139 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.138 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 20/08/2020 | 6 | 20/08/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.137 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.215 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.230 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 20/08/2020 | 9 | 20/08/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 2
F122032.228 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.118 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 20/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.117 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 20/08/2020 | 9 | 21/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.136 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.135 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 19/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.214 | Open / Ongoing Works | ESB Retaining Wall 02>Civil & External Works>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 19/08/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 4
F132454.39 | Opened | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/08/2020 | 9 | 19/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 2
F1.471359 | 3rd Party Sign Off - Closed | ESB Substation>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 19/08/2020 | 13 | 1/9/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 6
F1.471302 | 3rd Party Sign Off - Closed | ESB Substation>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 19/08/2020 | 13 | 20/08/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 6
F129642.213 | Open / Ongoing Works | CB-07>Zone 2>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 19/08/2020 | 11 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F122032.227 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.116 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 19/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.115 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 19/08/2020 | 9 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.134 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/08/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.38 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 18/08/2020 | 9 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 2
F132455.133 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 18/08/2020 | 6 | 1/9/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.132 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 18/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.212 | Open / Ongoing Works | CB-13>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 18/08/2020 | 11 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 4
F132455.131 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 18/08/2020 | 9 | 24/08/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.114 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 18/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.225 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/08/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.113 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 18/08/2020 | 9 | 19/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.130 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/08/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.129 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.209 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 17/08/2020 | 9 | 18/08/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.208 | Open / Ongoing Works | CB-14>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 17/08/2020 | 11 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F122032.224 | Open / Ongoing Works | Daily Site Diary & Allocation Sheets>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 17/08/2020 | 10 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 4
F132457.112 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 17/08/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.111 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 17/08/2020 | 9 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.222 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.207 | Closed | Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 14/08/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.128 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 14/08/2020 | 6 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.37 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 14/08/2020 | 9 | 18/08/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.221 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.127 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.36 | Closed | Training Records - EHS & Quality>JPC Project Management | CM-EHS-FRM-103 - Toolbox Training Record & Sign In Sheet | 14/08/2020 | 9 | 18/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.219 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 14/08/2020 | 9 | 14/08/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.110 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 14/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.109 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 14/08/2020 | 9 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.126 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 13/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.35 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 13/08/2020 | 9 | 18/08/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.206 | Open / Ongoing Works | CB-18>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 13/08/2020 | 11 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 4
F132455.125 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.123 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 13/08/2020 | 6 | 13/08/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.108 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 13/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.216 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/08/2020 | 6 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.107 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 13/08/2020 | 9 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.122 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132455.121 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 12/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.120 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 12/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.204 | Open / Ongoing Works | Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 12/8/2020 | 11 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F132455.119 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 12/8/2020 | 9 | 28/08/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.106 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 12/8/2020 | 6 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.215 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.105 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 12/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F129642.203 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 11/8/2020 | 6 | 11/8/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.202 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/8/2020 | 9 | 12/8/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132454.34 | Closed | Training Records - EHS & Quality>JPC Project Management | CM-EHS-FRM-103 - Toolbox Training Record & Sign In Sheet | 11/8/2020 | 9 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | TRUE | 1340 | Closed | 2
F129642.201 | Open / Ongoing Works | CB-22>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 11/8/2020 | 11 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F122032.214 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.104 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 11/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.103 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 11/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132454.33 | Closed | Meeting Records>JPC Project Management | CM-EHS-FRM-103 - Toolbox Training Record & Sign In Sheet | 10/8/2020 | 9 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.200 | Open / Ongoing Works | CB-26>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 10/8/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F122032.213 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/8/2020 | 9 | 18/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.212 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/8/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.102 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 10/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.101 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 10/8/2020 | 6 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.211 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 3
F132457.99 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 8/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.118 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.117 | Open / Ongoing Works | CB-01>Zone 1>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/8/2020 | 11 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F132454.32 | Closed | Training Records - EHS & Quality>JPC Project Management | CM-EHS-FRM-103 - Toolbox Training Record & Sign In Sheet | 7/8/2020 | 9 | 11/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.116 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 7/8/2020 | 6 | 7/8/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122033.28 | Closed | Main Site Set Up Plan>Site Logistics, Access & Deliveries | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 7/8/2020 | 9 | 10/9/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132454.31 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 7/8/2020 | 9 | 14/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.209 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.98 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 7/8/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.97 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 7/8/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132455.115 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.30 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 6/8/2020 | 9 | 14/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132455.114 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 6/8/2020 | 6 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.113 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/8/2020 | 9 | 14/08/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.96 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 6/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.208 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.95 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 6/8/2020 | 9 | 7/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F129642.199 | Open / Ongoing Works | CB-01>Zone 1>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 5/8/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 4
F132455.112 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.110 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.109 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 5/8/2020 | 6 | 5/8/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F1.458016 | 3rd Party Sign Off - Closed | CB-26>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 5/8/2020 | 13 | 1/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 6
F129642.198 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 5/8/2020 | 9 | 7/8/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.207 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.94 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 5/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.91 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 5/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.108 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.107 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/8/2020 | 6 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.197 | Open / Ongoing Works | CB-26>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 4/8/2020 | 11 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F122032.206 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 4/8/2020 | 9 | 12/8/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.205 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.86 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 4/8/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.85 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 4/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132454.29 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 31/07/2020 | 9 | 14/08/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.194 | Open / Ongoing Works | CB-26>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 31/07/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F132454.28 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 31/07/2020 | 9 | 11/8/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F136447.13 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/07/2020 | 6 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.83 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 31/07/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.78 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 31/07/2020 | 6 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.106 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/07/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.105 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 30/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F136447.12 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.193 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 30/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.192 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 30/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.191 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 30/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.190 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 30/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.189 | Open / Ongoing Works | CB-26>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 30/07/2020 | 11 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F122033.27 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 30/07/2020 | 9 | 10/9/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.104 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 30/07/2020 | 6 | 30/07/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122033.24 | Closed | EHS Inspections>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 30/07/2020 | 9 | 30/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.103 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 30/07/2020 | 9 | 6/8/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.77 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 30/07/2020 | 6 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.76 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 30/07/2020 | 9 | 4/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132454.27 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/07/2020 | 9 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132455.102 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.101 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.188 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/07/2020 | 9 | 30/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132454.26 | Open / Ongoing Works | EHS Inspections>JPC Project Management | EHS-FRM-SUB-001 Weekly EHS Submission Record | 29/07/2020 | 12 | 29/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 5
F129642.187 | Open / Ongoing Works | CB-26>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 29/07/2020 | 11 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 4
F132457.75 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 29/07/2020 | 6 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F136447.11 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.74 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 29/07/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132455.100 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 28/07/2020 | 6 | 28/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.99 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 28/07/2020 | 6 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.98 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/07/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.186 | Works Complete / Resolved | CB-26>Zone 3>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 28/07/2020 | 11 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 4
F132454.25 | Closed | Training Records - EHS & Quality>JPC Project Management | CM-EHS-FRM-103 - Toolbox Training Record & Sign In Sheet | 28/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F136447.10 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/07/2020 | 9 | 30/07/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F1.449060 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/07/2020 | 6 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.73 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 28/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.72 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 28/07/2020 | 9 | 29/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132455.97 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/07/2020 | 6 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F1.448632 | Open / Ongoing Works | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 27/07/2020 | 10 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Open | 4
F132455.96 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/07/2020 | 6 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.24 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/07/2020 | 9 | 30/07/2020 | 0 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F136447.9 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/07/2020 | 6 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.185 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 27/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132457.71 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 27/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.70 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 27/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F129642.184 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 24/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 4
F129642.183 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.182 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.181 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.180 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 24/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132455.95 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.94 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.23 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 24/07/2020 | 9 | 11/8/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F136447.8 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.93 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 24/07/2020 | 9 | 27/07/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.67 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 24/07/2020 | 6 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.65 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 24/07/2020 | 9 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132455.92 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.91 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 23/07/2020 | 6 | 23/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.90 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.179 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 23/07/2020 | 9 | 28/07/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.177 | Closed JPC Sign Off | Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 23/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F136447.7 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.61 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 23/07/2020 | 6 | 27/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.60 | Completed and signed off | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 23/07/2020 | 9 | 27/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132454.22 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/07/2020 | 9 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132455.89 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.88 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F136447.6 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.175 | Works Complete / Resolved | CB-05>Zone 1>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 22/07/2020 | 11 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 4
F129642.173 | Works Complete / Resolved | CB-06>Zone 1>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 22/07/2020 | 11 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Open | 4
F129642.170 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 22/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132454.21 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/07/2020 | 9 | 30/07/2020 | 0 | 14 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132457.59 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 22/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.58 | Completed and signed off | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 22/07/2020 | 9 | 24/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132455.86 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.85 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 21/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F1.442978 | 3rd Party Sign Off - Closed | CB-03>Zone 1>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 21/07/2020 | 13 | 5/8/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 6
F129642.169 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 21/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132454.20 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 21/07/2020 | 9 | 27/07/2020 | 0 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132455.83 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 21/07/2020 | 6 | 21/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F136447.5 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/07/2020 | 6 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.56 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 21/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.55 | Completed and signed off | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 21/07/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.82 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.81 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.80 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 20/07/2020 | 9 | 22/07/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F129642.168 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 20/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F136447.4 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.53 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 20/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.51 | Completed and signed off | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 20/07/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132457.48 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 18/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.167 | Closed | Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.165 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.164 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 17/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.79 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F1.440661 | 3rd Party Sign Off - Closed | CB-02>Zone 1>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 17/07/2020 | 13 | 5/8/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 6
F129642.163 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 17/07/2020 | 11 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.78 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.19 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 17/07/2020 | 9 | 27/07/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F136447.3 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.45 | Completed and signed off | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 17/07/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132457.44 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 17/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.162 | Closed JPC Sign Off | CB-03>Zone 1>Pile Capping Beam>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 16/07/2020 | 11 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 4
F132455.77 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.76 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 16/07/2020 | 6 | 16/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.75 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F136447.2 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.161 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 16/07/2020 | 11 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F122032.204 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 16/07/2020 | 9 | 21/07/2020 | 0 | 15 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.203 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.39 | Completed and signed off | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 16/07/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132457.38 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 16/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F136447.1 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.160 | Closed | B2 - Zone 3>Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 15/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.159 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 15/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.158 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 15/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.157 | Closed | Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 15/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132454.18 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 15/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.156 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.155 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.154 | Closed | B2 - Zone 1>Lvl -02 Basement & Foundations>Main Building>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 15/07/2020 | 10 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132454.17 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 15/07/2020 | 9 | 22/07/2020 | 0 | 13 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.151 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 15/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F122032.202 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132455.70 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 15/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.69 | Completed and signed off | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 15/07/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F132457.35 | Completed and signed off | Access & Deliveries>Site Logistics, Access & Deliveries | 1340 - CM-EHS-FRM-008 Daily Site Access Register | 14/07/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.68 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.66 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 14/07/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.150 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 14/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.64 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 14/07/2020 | 6 | 14/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.63 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 14/07/2020 | 9 | 22/07/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.34 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 14/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F122032.201 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/07/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.62 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.61 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 13/07/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.149 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 13/07/2020 | 9 | 11/8/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.199 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.198 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/07/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 3
F129642.147 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 13/07/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.146 | Closed | Listed Wall - Miltery Rd>Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 13/07/2020 | 10 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.145 | Closed | Listed Wall - Miltery Rd>Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 13/07/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132457.33 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 13/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F122032.197 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/7/2020 | 6 | 11/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.144 | Closed | Listed Wall - Miltery Rd>Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.60 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.16 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 10/7/2020 | 9 | 14/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.143 | JPC Signed Off / Closed | Main Site Set Up Plan>Site Logistics, Access & Deliveries | QM-FRM-SUB-101 Subcontractor Quality Control Record | 10/7/2020 | 12 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 5
F129642.142 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 10/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F122033.23 | Closed | Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-FRM-QC-006 Contracts Manager Quality Control Assessment | 10/7/2020 | 10 | 10/7/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 4
F132455.59 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/7/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.141 | Closed | Listed Wall - Miltery Rd>Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 10/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F122033.22 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/7/2020 | 9 | 6/8/2020 | 0 | 13 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.195 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.32 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 10/7/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F129642.139 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 9/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 4
F129642.138 | Closed | Listed Wall - Miltery Rd>Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 9/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.58 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.57 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.15 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 9/7/2020 | 9 | 14/07/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.136 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 9/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.56 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 9/7/2020 | 6 | 9/7/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.31 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 9/7/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F122032.194 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.135 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 8/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 4
F129642.134 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 8/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.55 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.54 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 8/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.132 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 8/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.131 | Closed | Listed Wall - Miltery Rd>Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 8/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.130 | Closed | Listed Wall - Miltery Rd>Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 8/7/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132455.53 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2020 | 9 | 10/7/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.193 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/7/2020 | 6 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.30 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 8/7/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132455.52 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.14 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 7/7/2020 | 9 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132455.51 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 7/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.129 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 7/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.128 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 7/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.49 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 7/7/2020 | 6 | 7/7/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F1.430583 | 3rd Party Sign Off - Closed | Civil & External Works>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-002 Design Team Inspection Report - Non BC(A)R | 7/7/2020 | 13 | 19/08/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | TRUE | 1340 | Closed | 6
F1.430568 | Open / Ongoing Works | Training Area | QM-FRM-QC-001 Benchmark / Sample Form | 7/7/2020 | 10 | 7/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Open | 4
F122032.192 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.127 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 7/7/2020 | 9 | 22/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132457.29 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 7/7/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F129642.126 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 6/7/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.48 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 6/7/2020 | 6 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.124 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 6/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.122 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 6/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132455.46 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.191 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/7/2020 | 9 | 6/7/2020 | 0 | 7 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.190 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/7/2020 | 6 | 6/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.28 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 6/7/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132454.13 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/7/2020 | 6 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.12 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 4/7/2020 | 11 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132455.45 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.44 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.121 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 3/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.119 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 3/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.118 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 3/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132454.10 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 3/7/2020 | 9 | 14/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132457.27 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 3/7/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F122032.189 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/7/2020 | 6 | 3/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.43 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/7/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.117 | Closed | Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 2/7/2020 | 10 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F129642.116 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 2/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.115 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 2/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132454.9 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 2/7/2020 | 9 | 14/07/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132455.42 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 2/7/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.114 | Closed | Overall Ground Floor Plan>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-FRM-QC-004 QC Observation Report | 2/7/2020 | 10 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122032.188 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 2/7/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 3
F122032.187 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/7/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.112 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 2/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.40 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 2/7/2020 | 9 | 10/7/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.39 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 2/7/2020 | 6 | 2/7/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.26 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 2/7/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132455.38 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.37 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.111 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 1/7/2020 | 9 | 14/07/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F129642.110 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 1/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.109 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 1/7/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132457.25 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 1/7/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F122032.186 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 1/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.108 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 30/06/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 4
F132455.36 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 30/06/2020 | 6 | 30/06/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.35 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132455.34 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.107 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 30/06/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.106 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 30/06/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F122032.185 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 30/06/2020 | 9 | 5/8/2020 | 0 | 10 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F132457.24 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 30/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F122032.181 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.33 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.32 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 29/06/2020 | 6 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.105 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 29/06/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.104 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 29/06/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132454.8 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/06/2020 | 9 | 14/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.103 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 29/06/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122032.180 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.22 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 29/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F122033.21 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/06/2020 | 6 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122033.20 | Closed | EHS Inspections>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 26/06/2020 | 9 | 3/7/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.31 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.30 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/06/2020 | 6 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.7 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 26/06/2020 | 9 | 14/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.102 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 26/06/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F122032.179 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/06/2020 | 6 | 26/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.101 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 26/06/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.27 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/06/2020 | 9 | 10/7/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F129642.100 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 26/06/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132457.21 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 26/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132455.26 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 25/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.98 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 25/06/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.97 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 25/06/2020 | 11 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132455.25 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.24 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 25/06/2020 | 6 | 25/06/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.177 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.96 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/06/2020 | 9 | 8/7/2020 | 0 | 10 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.18 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 25/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132455.23 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F1.419833 | 3rd Party Sign Off - Closed | Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-002 Design Team Inspection Report - Non BC(A)R | 24/06/2020 | 13 | 24/06/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 6
F132455.22 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 24/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.17 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 24/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 3
F129642.94 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 24/06/2020 | 11 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.93 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 24/06/2020 | 11 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122032.175 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 24/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.174 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 24/06/2020 | 9 | 24/06/2020 | 0 | 11 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F132457.16 | Closed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 24/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132455.21 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/06/2020 | 6 | 25/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.6 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 23/06/2020 | 9 | 3/7/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | TRUE | 1340 | Closed | 2
F132455.20 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 23/06/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.92 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 23/06/2020 | 11 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1340 | Closed | 4
F129642.90 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 23/06/2020 | 11 | 8/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 4
F132457.15 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 23/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F122032.172 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/06/2020 | 6 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.18 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.17 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 22/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.16 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/06/2020 | 9 | 25/06/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F129642.89 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 22/06/2020 | 11 | 8/7/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.88 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 22/06/2020 | 11 | 7/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122032.170 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/06/2020 | 6 | 22/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.14 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 22/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132454.5 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 20/06/2020 | 9 | 3/7/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132454.4 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/06/2020 | 6 | 27/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132457.13 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 20/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132454.3 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 19/06/2020 | 9 | 14/07/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132455.15 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 19/06/2020 | 6 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.14 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/06/2020 | 6 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.87 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 19/06/2020 | 11 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.86 | Closed JPC Sign Off | Zone 3>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 19/06/2020 | 11 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.85 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/06/2020 | 9 | 2/7/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.168 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/06/2020 | 6 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.11 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 19/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132455.13 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/06/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.12 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 18/06/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.82 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 18/06/2020 | 11 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.81 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 18/06/2020 | 11 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122032.167 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/06/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.10 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 18/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F129642.80 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 18/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.11 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 18/06/2020 | 6 | 18/06/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.166 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 18/06/2020 | 9 | 18/06/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F132457.9 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 18/06/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.10 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.9 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.2 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 17/06/2020 | 9 | 3/7/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F129642.77 | Closed JPC Sign Off | Zone 2>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 17/06/2020 | 11 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.76 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 17/06/2020 | 11 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122032.165 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 17/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.8 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 17/06/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F132455.8 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 16/06/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.7 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.75 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 16/06/2020 | 11 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.74 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 16/06/2020 | 11 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F132455.6 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 16/06/2020 | 9 | 18/06/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.164 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F132457.6 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 16/06/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F129642.73 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 15/06/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F1.412172 | 3rd Party Sign Off - Closed | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | DT-QC-RP-001 Design Team BC(A)R Inspection Report | 15/06/2020 | 13 | 23/06/2020 | 0 | 2 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 6
F132455.4 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 15/06/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132455.2 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/06/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.163 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/06/2020 | 6 | 16/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.72 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 15/06/2020 | 9 | 15/06/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F132457.5 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 15/06/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 3
F129642.71 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 13/06/2020 | 6 | 15/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.70 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 13/06/2020 | 9 | 13/06/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | TRUE | 1340 | Closed | 2
F132457.3 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 13/06/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.162 | Closed | Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 12/6/2020 | 10 | 14/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F132455.1 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 12/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F132454.1 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 12/6/2020 | 9 | 3/7/2020 | 0 | 9 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F132457.2 | Closed JPC Reviewed | Access & Deliveries>Site Logistics, Access & Deliveries | SM-FRM-011 Material Delivery Record | 12/6/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.161 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.160 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 12/6/2020 | 9 | 3/7/2020 | 0 | 3 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.68 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 12/6/2020 | 11 | 2/7/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 4
F122032.159 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/6/2020 | 6 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.67 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 11/6/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122032.158 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2020 | 9 | 3/7/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.156 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/6/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.66 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 11/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.154 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.65 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 11/6/2020 | 6 | 11/6/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.64 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/6/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.153 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/6/2020 | 9 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.152 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/6/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.63 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 10/6/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122033.19 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 10/6/2020 | 9 | 3/7/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.61 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/6/2020 | 9 | 18/06/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.151 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/6/2020 | 9 | 14/07/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F129642.60 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 9/6/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122032.150 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 9/6/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.58 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 9/6/2020 | 9 | 13/06/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.149 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.56 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 8/6/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F129642.55 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | QM-CL-CS-105 Piling Inspection | 8/6/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1340 | Closed | 4
F122032.148 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/6/2020 | 9 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.147 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 8/6/2020 | 9 | 8/6/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.145 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.144 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/6/2020 | 6 | 6/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.48 | Closed JPC Sign Off | Zone 1>Secant Pile Wall>Main Building>ITP 01 Civil & Structural>Quality Control & BC(A)R | JPC-QC-CL-106 Pile Mat Inspection | 5/6/2020 | 11 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1340 | Closed | 4
F129642.47 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 5/6/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.42 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 5/6/2020 | 9 | 30/06/2020 | 0 | 4 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.143 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 5/6/2020 | 6 | 6/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 3
F122032.141 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.41 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 5/6/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.140 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/6/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.40 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 4/6/2020 | 9 | 30/06/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F129642.39 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 4/6/2020 | 6 | 18/06/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.38 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 4/6/2020 | 9 | 18/06/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.139 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/6/2020 | 9 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.138 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/6/2020 | 6 | 4/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.37 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/6/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.137 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/6/2020 | 9 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F129642.30 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 3/6/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F129642.23 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 3/6/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.136 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F129642.21 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/6/2020 | 9 | 23/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.134 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 2/6/2020 | 9 | 3/6/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.133 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/6/2020 | 6 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122033.13 | Closed | EHS Inspections>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 29/05/2020 | 9 | 12/6/2020 | 0 | 1 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.129 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/05/2020 | 6 | 4/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 3
F129642.19 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 29/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.127 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/05/2020 | 9 | 18/06/2020 | 0 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.126 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F129642.18 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 29/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.125 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.17 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 28/05/2020 | 6 | 18/06/2020 | 0 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.124 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 28/05/2020 | 9 | 18/06/2020 | 0 | 6 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.122 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F129642.10 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 28/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.121 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/05/2020 | 9 | 18/06/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.120 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.5 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.4 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/05/2020 | 9 | 12/6/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1340 | Closed | 2
F122032.119 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.118 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.3 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.117 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/05/2020 | 9 | 18/06/2020 | 0 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.116 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.115 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.2 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 26/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.114 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122033.1 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 25/05/2020 | 9 | 12/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 2
F122032.113 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/05/2020 | 9 | 18/06/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.112 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F129642.1 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 23/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.111 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.110 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.109 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.108 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 22/05/2020 | 9 | 18/06/2020 | 0 | 7 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.107 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 18/06/2020 | 0 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.106 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.105 | Closed | Mechanical>Schematic Drawings>ITP 02 To Be Developed (ARC & MEP)>Quality Control & BC(A)R | QM-CL-ME-403 Mechanical Inspection | 21/05/2020 | 1 | 18/06/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 4
F122032.104 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.103 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 21/05/2020 | 9 | 18/06/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.102 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 21/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.101 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.100 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 20/05/2020 | 9 | 18/06/2020 | 0 | 5 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.99 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 19/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.98 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 19/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.97 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.96 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 18/05/2020 | 9 | 18/06/2020 | 0 | 3 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.94 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 18/05/2020 | 9 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.93 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.92 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/05/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.91 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/5/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.90 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/5/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.89 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/5/2020 | 6 | 12/5/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.88 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/04/2020 | 6 | 18/06/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.87 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 27/03/2020 | 9 | 18/06/2020 | 0 | 8 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.86 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.85 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.84 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 27/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.83 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 27/03/2020 | 9 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.82 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.81 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/03/2020 | 9 | 10/6/2020 | 0 | 5 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.80 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 26/03/2020 | 9 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.79 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 25/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.78 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/03/2020 | 9 | 10/6/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.77 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.76 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 25/03/2020 | 9 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.75 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 24/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.74 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 24/03/2020 | 9 | 10/6/2020 | 0 | 3 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.73 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.72 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 24/03/2020 | 9 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.71 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 23/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.70 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 23/03/2020 | 9 | 10/6/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.69 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.68 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 23/03/2020 | 9 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.66 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 21/03/2020 | 9 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.65 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1340 | Closed | 3
F122032.64 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 20/03/2020 | 9 | 24/06/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.62 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 20/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.61 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 20/03/2020 | 9 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.60 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.59 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 20/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.58 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/03/2020 | 6 | 10/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.57 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/03/2020 | 9 | 10/6/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.56 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 19/03/2020 | 9 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.55 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 18/03/2020 | 9 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.54 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 18/03/2020 | 9 | 9/6/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.53 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 18/03/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.52 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/03/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.51 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 13/03/2020 | 9 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.50 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 12/3/2020 | 9 | 5/8/2020 | 0 | 4 | parent | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 2
F122032.49 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 12/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.48 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 11/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.47 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.45 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.44 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/3/2020 | 9 | 9/6/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.43 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 10/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.42 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 9/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.41 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 9/3/2020 | 9 | 9/6/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.40 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 9/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.39 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.37 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/3/2020 | 9 | 9/6/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.36 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 6/3/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.35 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.34 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.33 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 5/3/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.32 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 5/3/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.31 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/3/2020 | 6 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.30 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 5/3/2020 | 9 | 8/6/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.29 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 4/3/2020 | 9 | 24/06/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.28 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 4/3/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.27 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/3/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.26 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-004 Daily White Board Meeting | 4/3/2020 | 6 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.25 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/3/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.24 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/3/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.22 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 3/3/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.21 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 3/3/2020 | 9 | 5/6/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.20 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 3/3/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.19 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/3/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.18 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 28/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.17 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/02/2020 | 9 | 5/6/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.16 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.15 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 27/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.14 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.13 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/02/2020 | 9 | 5/6/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.12 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.11 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 26/02/2020 | 6 | 6/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.10 | Closed JPC Reviewed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-002 Progress Record | 26/02/2020 | 6 | 6/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.8 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/02/2020 | 9 | 5/6/2020 | 0 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 2
F122032.6 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 26/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.5 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 26/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.4 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.3 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1340 | Closed | 3
F122032.2 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 25/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F122032.1 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-003 Daily Allocation Sheet | 25/02/2020 | 6 | 5/6/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1340 | Closed | 3
F1.364480 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 3
F1.364547 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.365298 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.366224 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/03/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.366717 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 25/03/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.366904 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.367406 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.368170 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.393230 | Closed | Site Logistics Plan | CM-EHS-FRM-007 COVID-19 Inspection | 18/05/2020 | 9 | 19/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.393443 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 3
F1.394092 | Closed | 1343 - Project ABC | CM-EHS-FRM-007 COVID-19 Inspection | 19/05/2020 | 9 | 20/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.394399 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 3
F1.395339 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 3
F1.395565 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 20/05/2020 | 9 | 16/07/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 2
F1.396050 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 21/05/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.396209 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 3
F1.396867 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.396870 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.397056 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 3
F1.397315 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/05/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.397371 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.397847 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/05/2020 | 9 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.398261 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.398601 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 27/05/2020 | 9 | 16/07/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 2
F1.399079 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 27/05/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.399134 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/05/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 3
F1.399901 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.400848 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/05/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.401270 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.401273 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.401292 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 30/05/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.402580 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/6/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.402628 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 2/6/2020 | 9 | 16/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.402948 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/6/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.403827 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.404748 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/6/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.406833 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.406908 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.406978 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 8/6/2020 | 9 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 2
F1.407586 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 9/6/2020 | 9 | 16/07/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.407680 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/6/2020 | 9 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.408621 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/6/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.409829 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/6/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.410593 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.412902 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.413384 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 16/06/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1343 | Closed | 2
F1.413982 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.414196 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 17/06/2020 | 9 | 16/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.415088 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/06/2020 | 6 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.416106 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/06/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.418762 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/06/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.420274 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.421072 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/06/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F1.421120 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.424656 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.425648 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.425977 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.429445 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/7/2020 | 9 | 16/07/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.430038 | Closed | 1343 - Project ABC | CM-EHS-FRM-007 COVID-19 Inspection | 6/7/2020 | 9 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.431237 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.433394 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.434587 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.434643 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.437821 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.438176 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 15/07/2020 | 9 | 20/07/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.440060 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.442245 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.442779 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/07/2020 | 9 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F1.442964 | Closed | Lessons Learned & Alerts - EHS & Quality>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 21/07/2020 | 10 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F1.443891 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.444737 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.445924 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.446726 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 24/07/2020 | 9 | 4/8/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.447304 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.450379 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.451153 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.453319 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/07/2020 | 6 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.455545 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.458299 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 5/8/2020 | 9 | 6/8/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.458331 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.459173 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.460177 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.461264 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.462176 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/8/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F1.463248 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.466934 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 3
F1.467031 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/08/2020 | 9 | 17/08/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F1.467448 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 3
F1.469267 | Closed JPC Reviewed | 1343 - Project ABC | QM-FRM-QC005 - Training Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 4
F1.495225 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/09/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F125681.1 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 19/03/2020 | 9 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.10 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/05/2020 | 9 | 11/6/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F125681.11 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/05/2020 | 9 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.12 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.13 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 29/05/2020 | 9 | 14/07/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F125681.14 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/6/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.15 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 3/6/2020 | 9 | 11/6/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.16 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 5/6/2020 | 9 | 14/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.17 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/6/2020 | 9 | 22/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.18 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 18/06/2020 | 9 | 29/06/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.19 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 19/06/2020 | 9 | 14/07/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.2 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 20/03/2020 | 9 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.20 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 26/06/2020 | 9 | 14/07/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.21 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/06/2020 | 9 | 22/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.22 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 1/7/2020 | 9 | 14/07/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F125681.23 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 9/7/2020 | 9 | 14/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.24 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 15/07/2020 | 9 | 21/07/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.25 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 16/07/2020 | 9 | 21/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.26 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 17/07/2020 | 9 | 22/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.27 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 23/07/2020 | 9 | 31/07/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F125681.28 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/07/2020 | 9 | 6/8/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F125681.29 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 30/07/2020 | 9 | 4/8/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.3 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 23/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.30 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 7/8/2020 | 9 | 12/8/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F125681.31 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 12/8/2020 | 9 | 20/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.32 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 18/08/2020 | 9 | 26/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.33 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 19/08/2020 | 9 | 27/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.34 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 27/08/2020 | 9 | 8/9/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.36 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/08/2020 | 9 | 31/08/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.4 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 24/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.5 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 25/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.6 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 26/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.7 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.8 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 27/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F125681.9 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/03/2020 | 9 | 11/6/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129719.1 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129719.3 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129719.4 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129719.5 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129719.6 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 7/7/2020 | 9 | 16/07/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129719.7 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.1 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/05/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.100 | Closed JPC Sign Off | lvl (-01) Foundation>Block 5>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 14/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.101 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 15/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.102 | Closed JPC Sign Off | Lvl -01 Foundation>Block 1>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 15/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.103 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 15/07/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.104 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 16/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.105 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 17/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.106 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 20/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.107 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 20/07/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.108 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 21/07/2020 | 9 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.109 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 22/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.110 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 23/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.111 | Closed | EHS Inspections>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 23/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.112 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 23/07/2020 | 9 | 28/07/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.114 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/07/2020 | 9 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.115 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/07/2020 | 9 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.117 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 31/07/2020 | 9 | 4/8/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.118 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/8/2020 | 9 | 4/8/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.119 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 6/8/2020 | 9 | 26/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.120 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/8/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.121 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 12/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.125 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 17/08/2020 | 13 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 6
F129825.126 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 17/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.127 | JPC Sign Off | Block 1>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 18/08/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 6
F129825.128 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 18/08/2020 | 11 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.129 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 18/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.13 | Closed | Lvl 00 Ground Floor>Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129825.130 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 18/08/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.131 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 19/08/2020 | 11 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.132 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 19/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.133 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 19/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.136 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 20/08/2020 | 9 | 20/08/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.137 | Works Complete / Resolved | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 20/08/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Open | 4
F129825.138 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 20/08/2020 | 13 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 6
F129825.139 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 20/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129825.14 | Completed and signed off | Staturatury Forms>JPC Project Management | EHS Managment Inspection - Daily | 5/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.140 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-007 Lessons Learned Report | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129825.141 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 20/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.142 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 21/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.143 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 21/08/2020 | 13 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 6
F129825.144 | Closed | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 21/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.145 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 24/08/2020 | 9 | 26/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.148 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 25/08/2020 | 9 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.150 | Closed | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 25/08/2020 | 10 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129825.152 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 25/08/2020 | 10 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.153 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 26/08/2020 | 10 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.154 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 27/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.155 | Closed | Staturatury Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 27/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.156 | Closed JPC Sign Off | ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 27/08/2020 | 11 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.157 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 27/08/2020 | 10 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.158 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 28/08/2020 | 13 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 6
F129825.159 | Works Complete / Resolved | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 28/08/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Open | 4
F129825.160 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.161 | Closed JPC Sign Off | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 31/08/2020 | 7 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.162 | JPC Sign Off | ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 31/08/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.163 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 31/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.165 | Closed | Material Delivery Records>JPC Project Management | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129825.166 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 1/9/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.167 | Works Complete / Resolved | Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 1/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Open | 4
F129825.169 | Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/9/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1343 | Closed | 4
F129825.170 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 3/9/2020 | 13 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 6
F129825.172 | Works Complete / Resolved | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 3/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Open | 4
F129825.173 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 4/9/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.174 | Open / Ongoing Works | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129825.175 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 9/9/2020 | 9 | 9/9/2020 | 1 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Open | 2
F129825.176 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129825.177 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 10/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.178 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/9/2020 | 9 | 10/9/2020 | 1 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.179 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/9/2020 | 9 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.18 | Closed | Staturatury Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/6/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.180 | Closed | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 11/9/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129825.19 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 5/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.2 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1343 | Closed | 2
F129825.21 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | QM-CL-CS-102 Demolition Inspection | 5/6/2020 | 11 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.22 | Closed | Audit & Assessment - EHS & Quality>JPC Project Management | QM-CL-CS-102 Demolition Inspection | 8/6/2020 | 11 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.23 | Closed | Audit & Assessment - EHS & Quality>JPC Project Management | QM-CL-CS-102 Demolition Inspection | 8/6/2020 | 11 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 4
F129825.24 | Closed | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 9/6/2020 | 11 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.25 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/6/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.26 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/6/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.27 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2020 | 9 | 16/07/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.28 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.29 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 12/6/2020 | 9 | 29/06/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.30 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 15/06/2020 | 9 | 14/07/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 2
F129825.31 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/06/2020 | 9 | 16/07/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.32 | Closed | Staturatury Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/06/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.33 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/06/2020 | 9 | 29/06/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.34 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 23/06/2020 | 9 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.35 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 23/06/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.36 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 26/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Open | 4
F129825.37 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/06/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.38 | Works Complete / Resolved | ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 29/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Open | 4
F129825.39 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 29/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Open | 4
F129825.40 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 29/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Open | 4
F129825.41 | Closed | Audit & Assessment - EHS & Quality>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 29/06/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.42 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 30/06/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.43 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 30/06/2020 | 9 | 16/07/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.44 | Works Complete / Resolved | ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Open | 4
F129825.45 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 30/06/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.46 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 30/06/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.47 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 30/06/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.48 | Works Complete / Resolved | Block 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129825.49 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 1/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Open | 4
F129825.50 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 1/7/2020 | 9 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129825.52 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 1/7/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.53 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 1/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.54 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 1/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Open | 4
F129825.63 | Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 2/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.64 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 2/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129825.65 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 2/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.66 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 2/7/2020 | 11 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.67 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 3/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Open | 4
F129825.68 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 3/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.69 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 3/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129825.7 | Closed | Lvl 00 Ground Floor>Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 2/6/2020 | 11 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129825.70 | Closed | Block 6>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 6/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.71 | Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 6/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129825.72 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 6/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129825.74 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.75 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.76 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Open | 4
F129825.77 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 7/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.78 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.79 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.80 | Closed JPC Sign Off | Block 10>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/7/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.81 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 7/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129825.82 | Closed JPC Sign Off | Lvl -01 Foundation>Block 2>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 8/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.83 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 8/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129825.84 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 8/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Open | 4
F129825.85 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 8/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.86 | Closed | Block 11>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 8/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.87 | Closed JPC Sign Off | lvl (-01) Foundation>Block 6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 9/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.88 | Closed | Block 6>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 9/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.89 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 9/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129825.9 | Closed | Lvl 00 Ground Floor>Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 2/6/2020 | 11 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129825.90 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 9/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Open | 4
F129825.91 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 9/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129825.92 | Closed JPC Sign Off | lvl (-01) Foundation>Block 3>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 10/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.93 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 10/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.94 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/7/2020 | 9 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129825.95 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 10/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Open | 4
F129825.96 | Closed JPC Sign Off | Lvl -01 Foundation>Block 1>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 10/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.97 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 13/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129825.98 | Closed JPC Sign Off | lvl (-01) Foundation>Block 3>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 13/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129825.99 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 14/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.1 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 21/05/2020 | 9 | 14/07/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.11 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.12 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 20/07/2020 | 9 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.13 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/07/2020 | 9 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.14 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 23/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129826.15 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 24/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129826.16 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 24/07/2020 | 10 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129826.17 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 27/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.18 | Closed JPC Sign Off | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 27/07/2020 | 7 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129826.19 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 28/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.2 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/05/2020 | 9 | 22/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.21 | Closed JPC Sign Off | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 28/07/2020 | 7 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129826.22 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 28/07/2020 | 10 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129826.23 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 29/07/2020 | 10 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129826.24 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 29/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.25 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 30/07/2020 | 9 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.26 | Open / Ongoing Works | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 30/07/2020 | 7 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129826.27 | Open / Ongoing Works | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 31/07/2020 | 7 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129826.28 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 31/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.29 | Open / Ongoing Works | lvl (-01) Foundation>Block 6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 31/07/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129826.3 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.30 | JPC Sign Off | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 31/07/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129826.31 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 4/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.32 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 4/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129826.33 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 5/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.34 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.35 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.38 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 6/8/2020 | 10 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129826.39 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.4 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 2/7/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.40 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129826.41 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 10/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.42 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 10/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.43 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129826.44 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/8/2020 | 9 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.45 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 11/8/2020 | 9 | 12/8/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.46 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 11/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1343 | Closed | 4
F129826.47 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 11/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.49 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 12/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.5 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 3/7/2020 | 9 | 16/07/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.50 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 12/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.51 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 12/8/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129826.52 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 13/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.53 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 13/08/2020 | 13 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 6
F129826.54 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 14/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.55 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 17/08/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1343 | Closed | 4
F129826.56 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 17/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 4
F129826.57 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.58 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.59 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1343 | Closed | 3
F129826.6 | Closed | Staturatury Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/7/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.60 | Completed and signed off | Staturatury Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/08/2020 | 9 | 19/08/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.62 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.63 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 21/08/2020 | 9 | 21/08/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.64 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.65 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.66 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.67 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.68 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.69 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.7 | Completed and signed off | Staturatury Forms>JPC Project Management | EHS Managment Inspection - Daily | 9/7/2020 | 9 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.71 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.72 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 1/9/2020 | 9 | 1/9/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.73 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.74 | Closed | 1343 - Project ABC | CM-EHS-FRM-001 EHS Daily Management Inspection | 2/9/2020 | 9 | 4/9/2020 | 1 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.75 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.77 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 3/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F129826.78 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.79 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.8 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 13/07/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.80 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.81 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.82 | Open / Ongoing Works | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 9/9/2020 | 7 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 4
F129826.83 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/9/2020 | 9 | 10/9/2020 | 1 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F129826.84 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.85 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F129826.86 | Closed | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 4
F129826.88 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/09/2020 | 9 | 14/09/2020 | 3 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 2
F129826.9 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 14/07/2020 | 9 | 16/07/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1343 | Closed | 2
F130872.1 | Closed JPC Reviewed | Staturatury Forms>JPC Project Management | SM-FRM-002 Progress Record | 5/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 3
F136638.1 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/07/2020 | 9 | 30/07/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136638.2 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 30/07/2020 | 9 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.11 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.12 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 6/8/2020 | 9 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.14 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/8/2020 | 9 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.15 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.16 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/8/2020 | 9 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.17 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 13/08/2020 | 9 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.18 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 17/08/2020 | 9 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.2 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.23 | Completed and signed off | Daily Site Diary & Allocation Sheets>JPC Project Management | EHS Managment Inspection - Daily | 17/08/2020 | 9 | 17/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.25 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 19/08/2020 | 9 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.26 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/08/2020 | 9 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.27 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/08/2020 | 9 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.28 | Closed | EHS Inspections>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 21/08/2020 | 9 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.29 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/08/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.30 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.31 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.32 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 26/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.33 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.34 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 31/08/2020 | 9 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.35 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 1/9/2020 | 9 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.36 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/9/2020 | 9 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.37 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.38 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/9/2020 | 9 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.39 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 7/9/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.4 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.40 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.41 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/9/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.42 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.43 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 10/9/2020 | 9 | 10/9/2020 | 1 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 2
F136639.44 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.45 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/09/2020 | 9 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.46 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 15/09/2020 | 9 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Open | 2
F136639.5 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.6 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/07/2020 | 9 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.7 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 31/07/2020 | 9 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.8 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/8/2020 | 9 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.9 | Closed | JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F143862.1 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 3/9/2020 | 9 | 8/9/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F143862.2 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/9/2020 | 9 | 8/9/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1343 | Closed | 2
F136639.46 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 15/09/2020 | 9 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 2
F136639.45 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 14/09/2020 | 9 | 15/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.495225 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/09/2020 | 6 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.88 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/09/2020 | 9 | 14/09/2020 | 3 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 2
F129826.86 | Closed | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 14/09/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129825.180 | Closed | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 11/9/2020 | 10 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129826.85 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/9/2020 | 6 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.179 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 11/9/2020 | 9 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.178 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/9/2020 | 9 | 10/9/2020 | 1 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.177 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-002 - Contracts Manager Site Safety Walk (General). | 10/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.44 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.84 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/9/2020 | 6 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F136639.43 | Opened | EHS Inspections>JPC Project Management | EHS Inspection. | 10/9/2020 | 9 | 10/9/2020 | 1 | 11 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 2
F136639.42 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/9/2020 | 9 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.83 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 10/9/2020 | 9 | 10/9/2020 | 1 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.176 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/9/2020 | 6 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.82 | Open / Ongoing Works | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 9/9/2020 | 7 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F129825.175 | Open / Ongoing Works | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 9/9/2020 | 9 | 9/9/2020 | 1 | 5 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Open | 2
F136639.41 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 8/9/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.40 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 8/9/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.81 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/9/2020 | 6 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.174 | Open / Ongoing Works | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-107 Underground Services Install Inspection | 7/9/2020 | 11 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F136639.39 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 7/9/2020 | 9 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F143862.2 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 7/9/2020 | 9 | 8/9/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.80 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/9/2020 | 6 | 7/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.79 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/9/2020 | 6 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.173 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/9/2020 | 9 | 4/9/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.38 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/9/2020 | 9 | 4/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.172 | Works Complete / Resolved | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 3/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Open | 4
F136639.37 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F143862.1 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 3/9/2020 | 9 | 8/9/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.78 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/9/2020 | 6 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.77 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 3/9/2020 | 9 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.170 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 3/9/2020 | 13 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 6
F129826.75 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/9/2020 | 6 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F136639.36 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/9/2020 | 9 | 2/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.74 | Closed | 1343 - Project ABC | CM-EHS-FRM-001 EHS Daily Management Inspection | 2/9/2020 | 9 | 4/9/2020 | 1 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.169 | Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-009 Quality Control Record | 2/9/2020 | 10 | 9/9/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | TRUE | 1345 | Closed | 4
F129825.167 | Works Complete / Resolved | Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 1/9/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Open | 4
F136639.35 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 1/9/2020 | 9 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.166 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 1/9/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129826.73 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/9/2020 | 6 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.72 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 1/9/2020 | 9 | 1/9/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.165 | Closed | Material Delivery Records>JPC Project Management | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 1/9/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129825.163 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 31/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F136639.34 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 31/08/2020 | 9 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.71 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/08/2020 | 6 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.162 | JPC Sign Off | ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 31/08/2020 | 10 | 1/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.161 | Closed JPC Sign Off | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 31/08/2020 | 7 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.160 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 31/08/2020 | 9 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F125681.36 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 28/08/2020 | 9 | 31/08/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.159 | Works Complete / Resolved | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 28/08/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Open | 4
F129826.69 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/08/2020 | 6 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.158 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 28/08/2020 | 13 | 31/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 6
F129826.68 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/08/2020 | 6 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F125681.34 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 27/08/2020 | 9 | 8/9/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.157 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 27/08/2020 | 10 | 28/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.156 | Closed JPC Sign Off | ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-113 Intumescent Painting Inspection | 27/08/2020 | 11 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.155 | Closed | Staturatury Forms>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 27/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.154 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 27/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F136639.33 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.153 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 26/08/2020 | 10 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129826.67 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/08/2020 | 6 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F136639.32 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 26/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.31 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.30 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/08/2020 | 9 | 27/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.152 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 25/08/2020 | 10 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F136639.29 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/08/2020 | 9 | 26/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.66 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/08/2020 | 6 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.150 | Closed | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 25/08/2020 | 10 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129825.148 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 25/08/2020 | 9 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.145 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 24/08/2020 | 9 | 26/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.65 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/08/2020 | 6 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.144 | Closed | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 21/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F136639.28 | Closed | EHS Inspections>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 21/08/2020 | 9 | 25/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.27 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/08/2020 | 9 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.64 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/08/2020 | 6 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.143 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 21/08/2020 | 13 | 21/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 6
F129826.63 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 21/08/2020 | 9 | 21/08/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.142 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 21/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.141 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 20/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F136639.26 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/08/2020 | 9 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.140 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-007 Lessons Learned Report | 20/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129826.62 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.139 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 20/08/2020 | 10 | 24/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129825.138 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 20/08/2020 | 13 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 6
F129825.137 | Works Complete / Resolved | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-104 Fill Placement Inspection | 20/08/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Open | 4
F129825.136 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 20/08/2020 | 9 | 20/08/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.33 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 19/08/2020 | 9 | 27/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.133 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 19/08/2020 | 10 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129826.60 | Completed and signed off | Staturatury Forms>JPC Project Management | EHS Managment Inspection - Daily | 19/08/2020 | 9 | 19/08/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129826.59 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/08/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 3
F136639.25 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 19/08/2020 | 9 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.132 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 19/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.131 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 19/08/2020 | 11 | 14/09/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.130 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-001 Benchmark / Sample Form | 18/08/2020 | 10 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.129 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-109 Waterproofing / Barrier Layer Inspection | 18/08/2020 | 11 | 8/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129826.58 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/08/2020 | 6 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F125681.32 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 18/08/2020 | 9 | 26/08/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.128 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 18/08/2020 | 11 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.127 | JPC Sign Off | Block 1>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 18/08/2020 | 13 | 18/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 6
F1.469267 | Closed JPC Reviewed | 1343 - Project ABC | QM-FRM-QC005 - Training Record | 17/08/2020 | 10 | 17/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 4
F129826.57 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/08/2020 | 6 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.126 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 17/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.125 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 17/08/2020 | 13 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 6
F136639.23 | Completed and signed off | Daily Site Diary & Allocation Sheets>JPC Project Management | EHS Managment Inspection - Daily | 17/08/2020 | 9 | 17/08/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.18 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 17/08/2020 | 9 | 17/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.56 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 17/08/2020 | 10 | 19/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129826.55 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 17/08/2020 | 11 | 10/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.467448 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 3
F1.467031 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 14/08/2020 | 9 | 17/08/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.466934 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 14/08/2020 | 6 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F129826.54 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 14/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F136639.17 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 13/08/2020 | 9 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.53 | JPC Sign Off | Block 3>ITP 01 Structural>Quality Control & BC(A)R | DT-QC-RP-003 Design Team Area Snag Report (Final Snag) | 13/08/2020 | 13 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 6
F129826.52 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 13/08/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F136639.16 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/8/2020 | 9 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.31 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 12/8/2020 | 9 | 20/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.121 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 12/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129826.51 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 12/8/2020 | 10 | 13/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129826.50 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 12/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129826.49 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 12/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.463248 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/8/2020 | 6 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F136639.15 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/8/2020 | 9 | 12/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.47 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 11/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129826.46 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 11/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129826.45 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 11/8/2020 | 9 | 12/8/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.44 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/8/2020 | 9 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.462176 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/8/2020 | 6 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.120 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/8/2020 | 9 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129826.43 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 10/8/2020 | 10 | 11/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129826.42 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 10/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129826.41 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 10/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.461264 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/8/2020 | 6 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F125681.30 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 7/8/2020 | 9 | 12/8/2020 | 0 | 6 | parent | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F129826.40 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129826.39 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.460177 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.38 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 6/8/2020 | 10 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.119 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 6/8/2020 | 9 | 26/08/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.14 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/8/2020 | 9 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.12 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 6/8/2020 | 9 | 7/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.459173 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 6/8/2020 | 6 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.35 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129826.34 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.458331 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 5/8/2020 | 6 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F1.458299 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 5/8/2020 | 9 | 6/8/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.11 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.9 | Closed | JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/8/2020 | 9 | 6/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.33 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 5/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F136639.8 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 4/8/2020 | 9 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.32 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 4/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.118 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 4/8/2020 | 9 | 4/8/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129826.31 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 4/8/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.455545 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/8/2020 | 6 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.117 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 31/07/2020 | 9 | 4/8/2020 | 0 | 3 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129826.30 | JPC Sign Off | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 31/07/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129826.29 | Open / Ongoing Works | lvl (-01) Foundation>Block 6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 31/07/2020 | 11 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F136639.7 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 31/07/2020 | 9 | 4/8/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.28 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 31/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.453319 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 31/07/2020 | 6 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.27 | Open / Ongoing Works | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 31/07/2020 | 7 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F125681.29 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 30/07/2020 | 9 | 4/8/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136638.2 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 30/07/2020 | 9 | 31/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.26 | Open / Ongoing Works | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 30/07/2020 | 7 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F129826.25 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 30/07/2020 | 9 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.24 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 29/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F136639.6 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/07/2020 | 9 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.451153 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.23 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 29/07/2020 | 10 | 30/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.115 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/07/2020 | 9 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F1.450379 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 29/07/2020 | 6 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.114 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/07/2020 | 9 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.28 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/07/2020 | 9 | 6/8/2020 | 0 | 5 | parent | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F136638.1 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/07/2020 | 9 | 30/07/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.22 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 28/07/2020 | 10 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129826.21 | Closed JPC Sign Off | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 28/07/2020 | 7 | 11/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129826.19 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 28/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F136639.5 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.4 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F136639.2 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.18 | Closed JPC Sign Off | Utilities & Drainage>ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-306 Underground Drainage & Manahole Install Inspection | 27/07/2020 | 7 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129826.17 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 27/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.447304 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/07/2020 | 6 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.16 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 24/07/2020 | 10 | 29/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F1.446726 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 24/07/2020 | 9 | 4/8/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.15 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 24/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.112 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-001 EHS Daily Management Inspection | 23/07/2020 | 9 | 28/07/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.445924 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/07/2020 | 6 | 23/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F125681.27 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 23/07/2020 | 9 | 31/07/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129826.14 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 23/07/2020 | 10 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129825.111 | Closed | EHS Inspections>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 23/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.110 | Closed | Block 4>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 23/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.444737 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.13 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/07/2020 | 9 | 24/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.443891 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/07/2020 | 6 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.109 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 22/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.442964 | Closed | Lessons Learned & Alerts - EHS & Quality>JPC Project Management | QM-FRM-QC-007 Lessons Learned Report | 21/07/2020 | 10 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.442779 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/07/2020 | 9 | 23/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F129825.108 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 21/07/2020 | 9 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.107 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 20/07/2020 | 10 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F1.442245 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/07/2020 | 6 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.12 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 20/07/2020 | 9 | 20/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129826.11 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/07/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.106 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 20/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F125681.26 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 17/07/2020 | 9 | 22/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.105 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 17/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.440060 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/07/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F125681.25 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 16/07/2020 | 9 | 21/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.104 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 16/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F125681.24 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 15/07/2020 | 9 | 21/07/2020 | 0 | 9 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.103 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 15/07/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.102 | Closed JPC Sign Off | Lvl -01 Foundation>Block 1>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 15/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F1.438176 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 15/07/2020 | 9 | 20/07/2020 | 0 | 10 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.437821 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 15/07/2020 | 6 | 15/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.101 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 15/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129826.9 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 14/07/2020 | 9 | 16/07/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.100 | Closed JPC Sign Off | lvl (-01) Foundation>Block 5>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 14/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.99 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 14/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129826.8 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 13/07/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.98 | Closed JPC Sign Off | lvl (-01) Foundation>Block 3>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 13/07/2020 | 11 | 14/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.97 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 13/07/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.434643 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F1.434587 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.96 | Closed JPC Sign Off | Lvl -01 Foundation>Block 1>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 10/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.95 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 10/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Open | 4
F129825.94 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/7/2020 | 9 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.93 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 10/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.92 | Closed JPC Sign Off | lvl (-01) Foundation>Block 3>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 10/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.91 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 9/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.90 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 9/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Open | 4
F125681.23 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 9/7/2020 | 9 | 14/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.433394 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 9/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129826.7 | Completed and signed off | Staturatury Forms>JPC Project Management | EHS Managment Inspection - Daily | 9/7/2020 | 9 | 9/7/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129826.6 | Closed | Staturatury Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/7/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.89 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 9/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F129825.88 | Closed | Block 6>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 9/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.87 | Closed JPC Sign Off | lvl (-01) Foundation>Block 6>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 9/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.86 | Closed | Block 11>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 8/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129719.7 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 8/7/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.85 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 8/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.84 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 8/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Open | 4
F129825.83 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 8/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F129825.82 | Closed JPC Sign Off | Lvl -01 Foundation>Block 2>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 8/7/2020 | 11 | 10/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.81 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 7/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F1.431237 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 7/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129719.6 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 7/7/2020 | 9 | 16/07/2020 | 0 | 1 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.80 | Closed JPC Sign Off | Block 10>ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/7/2020 | 11 | 5/8/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.79 | Closed | Block 3>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.78 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 7/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.77 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 7/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.76 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 7/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Open | 4
F1.430038 | Closed | 1343 - Project ABC | CM-EHS-FRM-007 COVID-19 Inspection | 6/7/2020 | 9 | 10/7/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F129825.75 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.74 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 6/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F1.429445 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 6/7/2020 | 9 | 16/07/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.72 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 6/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F129825.71 | Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 6/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129825.70 | Closed | Block 6>ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 6/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.69 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 3/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F129826.5 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 3/7/2020 | 9 | 16/07/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.68 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 3/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.67 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 3/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Open | 4
F129825.66 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 2/7/2020 | 11 | 9/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129825.65 | Closed | Block 5>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 2/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F129826.4 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 2/7/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.64 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 2/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F129825.63 | Closed | ITP 01 Structural>Quality Control & BC(A)R | QM-FRM-QC-010 RFIT - Request for Inspection or Test | 2/7/2020 | 10 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F125681.22 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 1/7/2020 | 9 | 14/07/2020 | 0 | 8 | parent | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F1.425977 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.54 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 1/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Open | 4
F129825.53 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 1/7/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F1.425648 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 1/7/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.52 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 1/7/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.50 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 1/7/2020 | 9 | 2/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.49 | JPC Inspected | ITP 03 Civil Works>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 1/7/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Open | 4
F129825.48 | Works Complete / Resolved | Block 2>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Open | 4
F129825.47 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 30/06/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.46 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 30/06/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 4
F129825.45 | Closed | Block 1>ITP 01 Structural>Quality Control & BC(A)R | Qm-CL-CS-112 Structural Steel Inspection | 30/06/2020 | 11 | 3/9/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 4
F1.424656 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.44 | Works Complete / Resolved | ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 30/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Open | 4
F129825.43 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 30/06/2020 | 9 | 16/07/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.42 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 30/06/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.41 | Closed | Audit & Assessment - EHS & Quality>JPC Project Management | CONTRACTS MANAGER SAFETY ASSESSMENT (monthly) | 29/06/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.21 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/06/2020 | 9 | 22/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.40 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 29/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Open | 4
F129825.39 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 29/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Open | 4
F129825.38 | Works Complete / Resolved | ITP 01 Structural>Quality Control & BC(A)R | JPC-QC-CL-110 Concrete Inspection (Pre/During/Post Pour) | 29/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Open | 4
F125681.20 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 26/06/2020 | 9 | 14/07/2020 | 0 | 8 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.37 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/06/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.36 | Works Complete / Resolved | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-103 Excavation Inspection | 26/06/2020 | 11 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Open | 4
F1.421120 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/06/2020 | 6 | 30/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F1.421072 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/06/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F1.420274 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/06/2020 | 6 | 10/7/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F129825.35 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 23/06/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.34 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 23/06/2020 | 9 | 29/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.418762 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/06/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.33 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/06/2020 | 9 | 29/06/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.32 | Closed | Staturatury Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/06/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.19 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 19/06/2020 | 9 | 14/07/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.31 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/06/2020 | 9 | 16/07/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.416106 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/06/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F1.415088 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/06/2020 | 6 | 19/06/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F125681.18 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 18/06/2020 | 9 | 29/06/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.414196 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 17/06/2020 | 9 | 16/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.413982 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 17/06/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F1.413384 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 16/06/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1345 | Closed | 2
F1.412902 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 16/06/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.30 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 15/06/2020 | 9 | 14/07/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F129825.29 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 12/6/2020 | 9 | 29/06/2020 | 0 | 1 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.28 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F1.410593 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 12/6/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F129825.27 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 11/6/2020 | 9 | 16/07/2020 | 0 | 2 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.409829 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 11/6/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.26 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 11/6/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.17 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 10/6/2020 | 9 | 22/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.408621 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 10/6/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.25 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 10/6/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.24 | Closed | ITP 03 Civil Works>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 9/6/2020 | 11 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F1.407680 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 9/6/2020 | 9 | 20/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F1.407586 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 9/6/2020 | 9 | 16/07/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.406978 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 8/6/2020 | 9 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 2
F1.406908 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F1.406833 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 8/6/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F129825.23 | Closed | Audit & Assessment - EHS & Quality>JPC Project Management | QM-CL-CS-102 Demolition Inspection | 8/6/2020 | 11 | 9/6/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 4
F129825.22 | Closed | Audit & Assessment - EHS & Quality>JPC Project Management | QM-CL-CS-102 Demolition Inspection | 8/6/2020 | 11 | 8/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F129825.21 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | QM-CL-CS-102 Demolition Inspection | 5/6/2020 | 11 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 4
F125681.16 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 5/6/2020 | 9 | 14/07/2020 | 0 | 5 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.19 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 5/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F130872.1 | Closed JPC Reviewed | Staturatury Forms>JPC Project Management | SM-FRM-002 Progress Record | 5/6/2020 | 6 | 9/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F129825.18 | Closed | Staturatury Forms>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 5/6/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F129825.14 | Completed and signed off | Staturatury Forms>JPC Project Management | EHS Managment Inspection - Daily | 5/6/2020 | 9 | 5/6/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F1.404748 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 4/6/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F129825.13 | Closed | Lvl 00 Ground Floor>Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 3/6/2020 | 11 | 3/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F1.403827 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 3/6/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F125681.15 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 3/6/2020 | 9 | 11/6/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.14 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 3/6/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.402948 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 2/6/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F129825.9 | Closed | Lvl 00 Ground Floor>Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 2/6/2020 | 11 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F129825.7 | Closed | Lvl 00 Ground Floor>Block 1>ITP 01 Structural>Quality Control & BC(A)R | QM-CL-CS-102 Demolition Inspection | 2/6/2020 | 11 | 2/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 4
F1.402628 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 2/6/2020 | 9 | 16/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.402580 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 2/6/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F1.401292 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 30/05/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.401273 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F1.401270 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 30/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F125681.13 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 29/05/2020 | 9 | 14/07/2020 | 0 | 7 | parent | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F1.400848 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 29/05/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F129825.2 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 29/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | TRUE | FALSE | 1345 | Closed | 2
F129719.5 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 28/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129719.4 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 28/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.399901 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 28/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F1.399134 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/05/2020 | 6 | 20/08/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 3
F125681.12 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129826.3 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 27/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.399079 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 27/05/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.398601 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 27/05/2020 | 9 | 16/07/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 2
F1.398261 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F1.397847 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 26/05/2020 | 9 | 21/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.397371 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F129826.2 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 25/05/2020 | 9 | 22/07/2020 | 0 | 4 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.397315 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 25/05/2020 | 9 | 22/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.397056 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 22/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 3
F1.396870 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F1.396867 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F129719.3 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 22/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129825.1 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 22/05/2020 | 9 | 28/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.396209 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 21/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 3
F129826.1 | Closed | EHS Inspections>JPC Project Management | EHS Inspection. | 21/05/2020 | 9 | 14/07/2020 | 0 | 9 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F1.396050 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 21/05/2020 | 9 | 16/07/2020 | 0 | 6 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F129719.1 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 21/05/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.395565 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 20/05/2020 | 9 | 16/07/2020 | 0 | 2 | parent | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 2
F1.395339 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 3
F125681.11 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-007 COVID-19 Inspection | 20/05/2020 | 9 | 20/05/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.10 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 19/05/2020 | 9 | 11/6/2020 | 0 | 4 | parent | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 2
F1.394399 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 19/05/2020 | 6 | 13/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | TRUE | 1345 | Closed | 3
F1.394092 | Closed | 1343 - Project ABC | CM-EHS-FRM-007 COVID-19 Inspection | 19/05/2020 | 9 | 20/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F1.393443 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 18/05/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | TRUE | FALSE | 1345 | Closed | 3
F1.393230 | Closed | Site Logistics Plan | CM-EHS-FRM-007 COVID-19 Inspection | 18/05/2020 | 9 | 19/05/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 2
F125681.9 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 27/03/2020 | 9 | 11/6/2020 | 0 | 7 | parent | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.368170 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 27/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F125681.8 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 27/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.7 | Completed and signed off | EHS Inspections>JPC Project Management | EHS Managment Inspection - Daily | 26/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.6 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 26/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.367406 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 26/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F125681.5 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 25/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.366904 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 25/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F1.366717 | Completed and signed off | 1343 - Project ABC | EHS Managment Inspection - Daily | 25/03/2020 | 9 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.366224 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 24/03/2020 | 6 | 17/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | TRUE | 1345 | Closed | 3
F125681.4 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 24/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.3 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 23/03/2020 | 9 | 11/6/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F1.365298 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 23/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F1.364547 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 3
F1.364480 | Closed | Daily Site Diary & Allocation Sheets>JPC Project Management | SM-FRM-001 Daily Site Diary | 20/03/2020 | 6 | 16/07/2020 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 1345 | Closed | 3
F125681.2 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 20/03/2020 | 9 | 20/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2
F125681.1 | Closed | EHS Inspections>JPC Project Management | CM-EHS-FRM-006 Site Welfare Inspection | 19/03/2020 | 9 | 19/03/2020 | 0 | 0 |  | FALSE | TRUE | FALSE | FALSE | 1345 | Closed | 2